## Sheet1
| Road Map for CCM Election Process |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER
| ACTIVITIES | RESPONSIBLE | W1, 1-5 | W2, 8-12 | W3, 15-19 | W4, 22-26/29-31 | W1, 1-2/5-9 | W2 12-16 | W3, 19-23 | W4, 26-30 | W1, 3-7 | W2 10-14 | W3, 17-21 | W4, 24-28
1 | Selection of the Electoral Committee | Ex Comm/CCM
2 | CCM approval for membership renewal road map | CCM |  |  |  | E-Vote
3 | Decisions on constituencies/term of service/Electoral Mannual/TOR/COI policy | CCM |  |  |  |  | E-Vote
4 | CCM Secrtariat makes open call for civil society representatives (advertise via newspapers, CSO networks, and internets) | CCM Secretariat
5 | Government representatives meeting to elect their representatives for CCM members | Facilitated by the Elecctoral Committee member (Dr. Bounpheng)
6 | Submission of new representative of government sectors (members and alternates) | Ministers and Head of Mass organizations
7 | Multilateral/Bilateral sectors meeting to select their representatives for CCM members | Facilitated by the Elecctoral Committee member (Ms. Fanny)
8 | Submision of new representatives of Multilateral/Bilateral sectors (members and alternates) | Facilitated by the Elecctoral Committee member (Ms. Fanny)
9 | CSO-KAP-PLWD Committee meeting to select their representatives for CCM members | Facilitated by the Elecctoral Committee member (Dr. Soulany)
10 | Submision of new representatives of the CSO-KAP-PLWD sub-sectors (members and alternates) | Facilitated by the Elecctoral Committee member (Ms. Fanny)
11 | INGOs network meeting to select their representatives for CCM members | Facilitated by the Elecctoral Committee member (Mr. John)
12 | Submision of new representatives of the INGO sub-sector (members and alternates) | Facilitated by the Elecctoral Committee member (Mr. John)
13 | Academic sub-sector meeting to select their representatives for CCM members | Facilitated by the Elecctoral Committee member (Dr. Philaysak)
14 | Submision of new representatives of the academic sub-sector (members and alternates) | Facilitated by the Elecctoral Committee member (Dr. Philaysak)
15 | Private sub-sector meeting to select their representatives for CCM members | Facilitated by the current CCM member (Ms. Keomanivone)
16 | Submision of new representatives of the private sub-sector (members and alternates) | Facilitated by the current CCM member (Ms. Keomanivone)
17 | Final deadline for the submission of any missing document related to membership renewal to the Secretariat | Sectors
18 | Meeting of CCM to endorse the proposed members of CCM and to elect chair and vice chairs, and elect its standing committees (ExCom, OC, RMC). | Electoral Committee/new CCM