Timeline for IBBS study 2017

- Female Sex Workers

| Activities | Time | Status | Remarks |
| --- | --- | --- | --- |
| - Meeting on preparing IBBS survey (FSW & MSM) at Bangkok with CDC team | Oct 2016 | Done |  |
| - Workshop on SOP of questionnaire(FSW & MSM) | 19 Nov 2016 | Done |  |
| - Preparation of Protocol | Dec 2016-Feb 2017 | Done |  |
| - Preparation of questionnaires | Jan 2017 | Done |  |
| - Pre-testing of questionnaires on S&D section | Jan 2017 | Done |  |
| - Review questionnaires | Feb 2017 | Done |  |
| - Preparation of questionnaire on PDA | Feb 2017 | Done |  |
| - Preparatory meeting of survey team | Sep 2017 | Not done |  |
| - Training of interviewers including lab technicians | Nov 2017 | Not done |  |
| - Procurement of equipment and materials | Sep 2017 | Not done |  |
| - Mapping of FSW in the survey in 6 provinces | Oct 2017 | Not done |  |
| - Field data collection In provinces: VTC, SVK, CPS, LPB, LNT and BK | Nov-Dec 2017 | Not done |  |
| 13. Data analysis & Preliminary Report | Dec 2017 | Not done | Will report to the GF in 2017 PUDR |
| 14. Final Report | Early 2018/Q1 2018 | Not done |  |

2. Men who have sex with men

| Activities | Time | Status | Remarks |
| --- | --- | --- | --- |
| - Meeting on preparing IBBS survey (FSW & MSM) at Bangkok with CDC team | Oct 2016 | Done |  |
| - Workshop on SOP of both questionnaire for FSW and MSM | 19 Nov 2016 | Done |  |
| - Preparation of Protocol | Dec 2016-Mar 2017 | Done |  |
| - Preparation of questionnaires | Jan 2017 | Done |  |
| - Pre-testing of questionnaires on S&D section | Jan 2017 | Done |  |
| - Review questionnaires | May 2017 | Done |  |
| - Preparation of PDA | Aug 2017 | In the process |  |
| - Training of interviewers including lab technicians | Sep 2017 | Not done |  |
| - Preparatory meeting of study team | Aug 2017 | Not done |  |
| - Procurement of equipment and materials | Aug 2017 | In the process |  |
| - Field data collection In provinces: VTC, SVK, CPS and LPB | Sep-Oct 2017 | Not done |  |
| 12. Data analysis & | Dec 2017 | Not done |  |
| - Preliminary Report | Dec 2017 | Not done | Will report to the GF in mid-Feb 2018 by PUDR |
| 14. Final report | Early 2018/Q1 2018 | Not done |  |