**Timeline for IBBS study 2017**

1. **Female Sex Workers**

|  |  |  |  |
| --- | --- | --- | --- |
| Activities | Time | Status | Remarks |
| 1. Meeting on preparing IBBS survey (FSW & MSM) at Bangkok with CDC team | Oct 2016 | Done |  |
| 1. Workshop on SOP of questionnaire(FSW & MSM) | 19 Nov 2016 | Done |  |
| 1. Preparation of Protocol | Dec 2016-Feb 2017 | Done |  |
| 1. Preparation of questionnaires | Jan 2017 | Done |  |
| 1. Pre-testing of questionnaires on S&D section | Jan 2017 | Done |  |
| 1. Review questionnaires | Feb 2017 | Done |  |
| 1. Preparation of questionnaire on PDA | Feb 2017 | Done |  |
| 1. Preparatory meeting of survey team | Sep 2017 | Not done |  |
| 1. Training of interviewers including lab technicians | Nov 2017 | Not done |  |
| 1. Procurement of equipment and materials | Sep 2017 | Not done |  |
| 1. Mapping of FSW in the survey in 6 provinces | Oct 2017 | Not done |  |
| 1. Field data collection   In provinces: VTC, SVK, CPS, LPB, LNT and BK | Nov-Dec 2017 | Not done |  |
| 13. Data analysis & Preliminary Report | Dec 2017 | Not done | Will report to the GF in 2017 PUDR |
| 14. Final Report | Early 2018/Q1 2018 | Not done |  |

2. **Men who have sex with men**

|  |  |  |  |
| --- | --- | --- | --- |
| Activities | Time | Status | Remarks |
| 1. Meeting on preparing IBBS survey (FSW & MSM) at Bangkok with CDC team | Oct 2016 | Done |  |
| 1. Workshop on SOP of both questionnaire for FSW and MSM | 19 Nov 2016 | Done |  |
| 1. Preparation of Protocol | Dec 2016-Mar 2017 | Done |  |
| 1. Preparation of questionnaires | Jan 2017 | Done |  |
| 1. Pre-testing of questionnaires on S&D section | Jan 2017 | Done |  |
| 1. Review questionnaires | May 2017 | Done |  |
| 1. Preparation of PDA | Aug 2017 | In the process |  |
| 1. Training of interviewers including lab technicians | Sep 2017 | Not done |  |
| 1. Preparatory meeting of study team | Aug 2017 | Not done |  |
| 1. Procurement of equipment and materials | Aug 2017 | In the process |  |
| 1. Field data collection   In provinces: VTC, SVK, CPS and LPB | Sep-Oct 2017 | Not done |  |
| 12. Data analysis & | Dec 2017 | Not done |  |
| 1. *Preliminary Report* | Dec 2017 | Not done | *Will report to the GF in mid-Feb 2018 by PUDR* |
| 14. Final report | Early 2018/Q1 2018 | Not done |  |