## Sheet1
Lao CCM Work Plan for Fiscal Year 2017-2018
Theme | Detail | Activity | Timeline | Indicator | Needs additional TA? | Source | Budget | Status
Oversight | Plan | Develop an oversight plan for fiscal year 2017-2018. | By end Dec 2017 | The oversight plan and budget has been approved by CCM | No |  |  | in progress
| Tools | Revitalize PR and CCM dashboard. |  | PR and CCM dashboards function | Yes |  |  | To discuss with PR, GMS and GF
| Implementation | Conduct oversight field visits. | Quarterly | Visit reports are available for CCM, GF and partners | No | GF | 5745 | in progress
|  | Gather data on GF grants through the grant performance routine reports and discussed in during OC and CCM meetings. | Bi-annually | Regular updates on dashboard, PU, PUDR, management letter | No
|  | Analyze information based on grant dashboards and other review processes. | Quarterly | Information has been analyzed and used for reporting | No |  |  | in progress
|  | Conduct Light Eligilbility and Performance Assessment (EPA). | By end June 2018 | EPA results have been approved by CCM | No
|  | Conduct overall CCM Secretariat Performance Assessment. | By end June 2018 | Assessement results have been approved by CCM | No
Membership | Membership | Update the membership regularly based on the changes in membership over times. |  | Membership is regularly updated. | No |  |  | in progress
| Training | Conduct re-orientation on the structure, roles and responsibilities of the CCM and its committees for the new members. |  | Re-orientation has been conducted when new members come on board. | No |  |  | in progress
Conflict of Interests (COI) | Policy | Review and endorse the CCM COI policy, if needed |  |  | No
| Implementation | The CCM COI policy applies to all members, and requires members in situations of COI to recuse from decision-making |  | CCM meeting minutes recorded the COI mitigation measures | No |  |  | in progress
|  | Update the current COI mitigation measure matrix, if needed. |  | New COI mitigation measure matrix proposed to CCM for approval, if applicable. | No
|  | Gather COI declaration form signed by the new CCM members |  | COI declaration form signed by all CCM | No |  |  | in progress
Structure | Organigram | Update the current organigram, if needed. |  | New organigram proposed to CCM for approval, if applicable. | No
| TOR | Update the current TOR, if needed. |  | New TOR proposed to CCM for approval, if applicable | No
CSO strengthening | Consultation within CSO | Support CSO Coordinating committee meetings. | Quarterly | Reports are available | No | GF | 4233 | in progress
Communication | Communication plan and activities | Regular Executive Committee (ExCom) meeting | Monthly | Meeting minutes | No | GF | 528 | in progress
|  | Quarterly CCM meeting (plus 2 ad-hoc meeting when required) | Quarterly | Meeting minutes | No | GF | 11402 | in progress
|  | Regular Resource Mobilization Committee (RMC) meeting (may have less meeting after completion of new funding application process 2017) | Quarterly | Meeting minutes | No | GF | 176 | in progress
|  | Regular Oversight Committee (OC) meeting | Quarterly | Meeting minutes | No | GF | 235 | in progress
|  | Document all CCM activities and reports to CCM, PRs, GF and partners (including translation key documents) | Quarterly | Documents and reports are available | No | GF | 2856 | in progress
|  | Regular update CCM Website (including TA cost) | Monthly | CCM website updated regularly | No | GF | 3772 | in progress
|  | Regular communication through email to CCM, its committees and partners for following up GF activities, sharing and requesting information to support oversee and grant implementation | Weekly | Regular communication taken place | No |  |  | in progress
|  | Total budget |  |  |  |  | 28947