## Sheet1
Lao CCM Work Plan for Fiscal Year 2016-2017
Theme | Detail | Activity | Timeline | Indicator | Needs additional AT? | Source | Budget | Status
Oversight | Plan | Review the implentation of the oversight action plan 2016 and approve the oversight action plan and budget for 2017. | By end Dec 2016 | CCM approved the oversight action plan and budget | no |  |  | in progress
| Structure & membership | Finish composition of OC; select chairman, review competencies of members, submit CV of members to Secretariat for inclusion in 2016 EPA | By end Dec 2016 | Completed committee. CVs submitted to GF in 2016 EPA | no |  |  | in progress
| Training | Review, repeat oversight slides presented during orientation both for OC and PR. | Q 1, 2017 | Oversight slides were reviewed by OC and PR | no
| Tools | Revitalize PR and CCM dashboard | Q 2, 2017 | PR and CCM dashboards are being used. | ?
|  | Train TB and Malaria programs on CCM dashboard | Q 2, 2017 | Malaria and TB complete/ submit info for CCM DB | ? |  |  | May have to buy the SAP license.
| Implementation | Conduct oversight field visits | Q 3, 2017 | Visit reports are available for CCM, GF and partners | no |  | 1913.4
|  | Gather data on GF grants through the grant performance routine reports and discussed it in CCM assemblies | Bi-annually | Regular updates on dashboard, PU, PUDR, management letter | no |  |  | in progress
Membership | Composition review | Based on new funding grant for 2017-2019, review CCM composition and change/include new constituencies if needed. |  | TORs & Electoral manual reviewed (if necessary). Electoral Committee selected |  |  |  | not started
| Renewal process | Connects to above activity
| Establishment of newly elected CCM | Connects to above activity
| Orientation | Connects to above activity
COI | Policy | Review and endorse the CCM COI policy, if needed |  | COI policy was endorsed by CCM | no
| Implementation | The CCM CoI policy applies to all members, and requires members in situations of COI to recuse from decision-making |  | CCM meeting minutes recorded the COI mitigation measures | no |  |  | in progress
|  | Review and endorse COI mitigation measure matrix | By end Dec 2016 | COI mitigation matrix endorsed by CCM | no |  |  | in progress
|  | Gather COI declaration form signed by CCM | By end Dec 2016 | COI declaration form signed by all CCM | no |  |  | in progress
Structure | Organigram | CCM retreat to facilitate CCM membership renewal process and orienttion of the new members | By end Dec 2016 | New organizational chart and membership endorsed by CCM |  |  | 5320.31 | in progress
| TOR | Review current TOR and made changes if needed |  | New TORS proposed for approval, if applicable |  |  |  | not started
CS strengthening | Consultation with CSO | Participation in regular CSO forum and committee meetings. |  |  | no |  |  | in progress
| CSO work plan | Final CSO work plan and associated budget approved by CCM. | 2016-11-25 | Draft plan of activities to be included in CCM plan |  |  |  | in progress
| CS strengthening | Strengthening of CS, specially of new constituencies. Detail of activities (Refer to CSO worplan) |  |  |  |  | ? | in progress
Communication | Communication plan and activities | Regular Executive Committee (ExCom) meeting | monthly | Meeting minutes | no |  | 385 | in progress
|  | Quarterly CCM meeting (plus 2 ad-hoc meeting when required) | Quarterly | Meeting minutes | no |  | 3510 | in progress
|  | Regular Resource Mobilization Committee (RMC) meeting (May have more meeting during new funding application process during Nov 2016 to Mar 2017) | Quarterly | Meeting minutes | no |  | 308 | in progress
|  | Regular Oversight Committee (OC) meeting | Quarterly | Meeting minutes | no |  | 192 | in progress
|  | Document all CCM activities and reports to key stakeholders (including translation key documents) | monthly | Updated documents and reports available | no |  | 997.6 | in progress
|  | Regular update CCM Website and drop box (including TA cost) | monthly | CCM website updated | no |  | 3650 | in progress
New funding application for Global Fund | Activities related to submission of new funding requests | Initial Planning discussions, CCM, implementers TOR, recruitment of TA | By end Dec 2016 | Numbers of TA recruited |  | FEI 5%, WHO, UNAIDS |  | in progress
|  | Submit formal letter to request TA support for the application development process to relevant source (TA providers) | By 25 Nov 2016 | Numbers of TA request submitted |  | FEI 5%, WHO, UNAIDS |  | in progress
|  | Coordinate with the programs to compile all disease programs workplans/ roadmaps and follow up their activities leading up to application submission | W3 Nov 2016 - W3 Mar 2017 | Workplan completed and followed |  |  |  | in progress
|  | Systematically document all key meetings and communicate with PR, disease programs and partners any related decisions | W3 Nov 2016 - W3 Mar 2017 | All key related documents collected |  |  |  | in progress
|  | Strategic Discussion after GF advice on country allocation on 15 Dec: potential for single application (HIV/TB/RSSH) or TB/RSSH & HIV/RSSH (& RAI/RSSH) | By 19 Dec 2016 | Decided on number of application
|  | CCM decisions: Disease Split; application: joint /single disease; OR disease/RSSH; tailored review | By 9 Jan 2017 | Decided on disese split
|  | Country-level consultations + development of application | Early 2016 - W3 Mar 2017 | Numbers of consultation
|  | CCM endorse/select PR/SRs | By 28 Jan 2017 | PRs and SRs selected and endorsed
|  | Coordinate and work with Ministries to complete the action plan for Willingness to Pay (WTP) | By 27 Feb 2017 | Action plan for WTP completed
|  | Complete the Eligibility Performance Assessment (EPA) | By 27 Feb 2017 | EPA completed |  |  |  | for ER 3-6 by 31 Dec 2017
|  | CCM endorse final draft Application for Malaria country component and submit to RSC | By 27 Feb 2017 | Malaria country component submitted to RSC
|  | CCM review and endorse final draft country application (s) | By 17 Mar 2017 | Final draft country applications endorsed
|  | Submit application (S) to the Global Fund | By 20 Mar 2017 | Country application submitted to GF
|  | Total budget |  |  |  |  | 16276.31