## Slide 1
Report of Oversight Field Visit
Louang Namtha Province
Date: 27thJune - 1st July 2016
Mornitoring:
HIV/AIDS, Tuberculosis and Malaria

## Slide 2
Main Purpose: To oversight the implementation of the projects supported by the Global Fund to Fight AIDS, Tuberculosis and Malaria (GFATM) at provincial, district and health center level accordingly to the oversight schedules, and focused on five key issues: Finance, Procurement, Implementation, Reporting​, Results(output/outcome)​

## Slide 3
Target sites:
1. Provincial Hospital and Provincial Health Department
Health Office of Namtha District
Chaleunsouk Health Center
Health Office of Sing District
Nam Dai Health Center
Phoudonthan Health Center
ARV Center (Provincial Hospital)
​Malaria Station​​
Nateuy Health Center

## Slide 4
Summary of finding on oversight field visit focused on the key progress and issues as below:

## Slide 5
Key Progress:
Under the guidance of the leaders, the projects were successfully implemented.
Good cooperation in the implementation among the project team and partners at all levels.
The project has a budget for the implementation (supported by the government and international organizations)
The local authorities cooperated as well.
For the patients: the access to ARV treatment resulted in the reduction of transmission and death rate.
Monitoring on implementing activities such as IEC materials have been broadly disseminated.

## Slide 6
The malaria control networks covered all target areas and villages.
Received the grant and materials from the Global Fund, ADB, CDCII and the government budget.
The staff that is responsible for the HIV/STI of each district successfully practiced their roles as assigned by the upper level, such as regular monthly report.
Surveillance systems for malaria at the provincial
There is device that can be quickly diagnosed the illness from malaria occurs.

## Slide 7
The bed net can be distributed to the target villages completely
The rate of illness from malaria is decreased
Overall, the implementation of the activities was conducted as planned.
The Tuberculosis case detection rate was increased.
The reports were usually submitted on time.
Most of the activities achieved the expected targets.
Ensured that the medicines will not be out of stock in the warehouse.
The staffs of Nam Dai Health Center are trained professionals together after completed their training and those staffs are able to work as representative to each other

## Slide 8
Key Issues:
Provincial Level
Lack of coordination between the province and district
The rate of TB patients is increasing and remaining MRD-TB patients and TB patients are not well cooperative
Activities can be extended to the district level only, have not been extended yet to the health center level
The budget for activities is limited and did not accessed the remote areas

## Slide 9
The transferring budget from province to district was delayed due to district failed to submit the report of activity conduction. Key activity of sending samples was not performed
Lack of staff especially for TB and analysis specialist at provincial hospital
Budget transfer from central to the province is still delayed

## Slide 10
Health Office of Luang Namtha District
The communication between the provincial health department and health office of district is uncomfortable and not continuous
The budget is delay and there is no budget to monitor health center
Provided counseling service only (Do not have treatment center)
The hospital roles are not implemented
No training course for staffs

## Slide 11
Chaleunsouk Health Center
Practicing of DOT is not well performed (give the drug to patients in advance)
Did not receive the budget to deliver bed nets and no allowance from the GF, it was supported by the government budget
In 2016 did not receive rapid test kits and malaria medicine
Difficulties in communication given that most of the local people are Khmu and Akha tribe
The budget for activities is limited and insufficient

## Slide 12
Health Office of Sing District
Most patients under our service are from Long District
Most rapid tests are given to Hospital of Sing District
Mostly malaria was infected from the border of Burma such as: Long and Lar District due to those local people are planting the rubber trees
Most TB patients are Akha tribe
Difficulty to communicate given that the population is mostly Khmu and Akha tribe
The budget for activities is limited and insufficient

## Slide 13
Nam Dai Health Center
The 13 TB patients under this health center are mostly Akha tribe
Practicing of DOT is not well performed (give the drug to patients in advance)
Uncheck the closest people of the TB patients
No budget to monitor the villages (the district conducted the monitoring itself)
No budget collect data, it was integrated with other projects
The report was not regularly submit due to its difficulty to communicate in the local language (Khmu and Akha tribe)
The budget for activity is limited and insufficient

## Slide 14
Phoudonthan Health Center
There is no sputum box available due to the staffs is missing coordination with district and rarely have patients to come for service
There is 1 TB patient named Mr. Aphor, Age 41 years, lived in Pa Kha village, Sing District, Akha tribe, he has not come for continue his TB medicine; he was advised to recheck, but preferred not to come.

## Slide 15
ARV Center (Provincial Hospital)
Most of the sputum samples are from Sing and Long District
There is a testing machine available, but it can not supply the services
Lack of standing analysis specialist
Lack of testing fluid detector, there is only a testing machine supported by China
The Gen-Expert Office has not standardize storage as several testing tools are kept at the same room and it is not clean.

## Slide 16
Receiving budget at the end of every quarter caused inconvenience in action
Owed the hospital for the patient services fee quarterly almost 6,000,000 kip
Sometimes the financer spended his own money in advance
No specific room for counselling service to patients
The medical warehouse has not air conditioning, which will cause the drugs to lost their quality
No specific room for TB patients

## Slide 17
Malaria Station
No budget for monitoring
Nateuy Health Center
No budget to monitoring patients and villages
Tested 21 suspected cases, 4 were positive patients
The testing was not done on March 2016 given there was no rapid test kits
The implementation of DOT has not been standardized as the health center provided the TB medicines directly to the patients - 1 month in advance
No budget to purchase office supplies

## Slide 18
Recommendation
Arrange the staffs appropriately for activities for each project
Make the budget plan to submit for the government budget to support 3 project diseases
THANK YOU