Meeting Minutes of

<Project Name>

1. input fields indicated by yellow boxes 

| MEETING DETAILS (Place “x” in the Relevant Box) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| LOCATION/VENUE |  | FF 1ST Floor CCM Secretariat Meeting Room, MoH |  |  |  |  |
| MEETING NUMBER |  |  |  | TOTAL NUMBER OF PARTICIPANTS/ (INCLUDING ALTERNATIVES & CCM SECRETARIAT STAFF) | OC MEMBERS | 5 |
| DATE (dd.mm.yy) |  | 02/06/2016 |  |  | ALTERNATIVE OF OC | 2 |
| MEETING SCHEDULE START |  | 13:30 |  |  | CCM SECRETARIAT STAFFS | 5 |
| MEETING ACTUAL STARTED |  | 13:40 |  |  | OTHERS | 2 |
| MEETING ACTUAL ENDED |  | 16:40 |  |  | TOTAL | 14 |
| DETAILS OF PERSON |  |  |  |  | MEETING TYPE |  |
| HIS / HER NAME & ORGANIZATION | First Name |  | Dr. Philaysak |  |  |  |
|  | Family Name |  | Naphayvong |  | Regular Meeting | x |
|  | Position/Title |  | Deputy Director |  | Extra-ordinary Meeting |  |
|  | Organization |  | Francophone Institute of Tropical Medicine |  | Other Meeting |  |
| HIS / HER ROLE ON THE MEETING | Chair |  | x | GLOBAL FUND SECRETARIAT / LFA ATTENDANCE AT THE MEETING | LFA |  |
|  | Vice-Chair |  |  |  | FPM / PO |  |
|  | CCM Member |  |  |  | OTHERS |  |
|  | Alternate |  |  |  | NONE |  |

2. AGENDA OF THE MEETING

| AGENDA SUMMARY |  |  |
| --- | --- | --- |
| AGENDA ITEM NO. | WRITE THE AGENDA TITLE OF EACH AGENDA ITEM/TOPIC | Responsible Person |
| Agenda #1 | Review and endorse the last OC meeting minute | OC Chair |
| Agenda #2 | Report on oversight field visit on 28 - 31 March 2016 in Borikhamxay Province and schedule the next visit | OC Chair and CCM Secretariat |
| Agenda #3 | Discuss a plan for the next 2 sessions of the CCM meeting - A tentative date and agenda for the next CCM meetings - Review TOR for the Technical Assistance for the CCM - Review the GF guideline regarding the CCM composition - Review and update the Terms of Reference of CCM, Ex-Com, OC, RMC, and four Task Forces | OC and CCM Secretariat |
| Agenda #4 | - AOB | OC Chair |

3. MINUTES OF EACH AGENDA ITEM

| Agenda Item #1 | Review and endorse the last OC meeting minute |
| --- | --- |
| SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED |  |
| The CCM secretariat updated the follow-up actions taken on the recommendations during the last OC meeting, i.e. the national programs have prepared the presentation on performance framework of the national programs, and the RAI coordinator has improved the presentation on RAI reprogramming and submitted the proposal to the CCM for reviewing and endorsing during the incoming CCM meeting The last OC meeting minutes was approved by the OC. |  |
| DECISIONS MADE |  |
| The last OC meeting minutes was approved |  |

| Agenda Item #2 | Report on oversight field visit on 28 - 31 March 2016 in Borikhamxay Province and schedule for the next visit |
| --- | --- |
| SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED |  |
| Report on oversight field visit was presented by the OC Chair. The same type of problems were found on each oversight field visit: - Adequately distribution of staff - Lack of qualified staff and too many duties for one person - Delay of report submission - Low budget absorption. The final report was circulated to the CCM, national programs, provincial health departments, and the Ministry of Health. Among others comment and discussion, the participants advised that the issues found during the oversight field visit can be presented in the upcoming Sector-wide Coordination's meeting which will be held on 24 June 2016 and chair by a Vice-Minister of Health in order to share and ask for a guidance and recommendation. This may also stimulate actions from the concerned department/sectors to address issues. |  |
| No decision |  |

| Agenda Item #3 | Discuss a plan for the next 2 sessions of the CCM meeting. - A tentative date and agenda for the next CCM meetings - Review TOR for the Technical Assistance for the CCM - Review the GF guideline regarding the CCM composition - Review and update the Terms of Reference of CCM, Ex-Com, OC, RMC, and four Task Forces |
| --- | --- |
| SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED |  |
| A tentative date and agenda for the next CCM meetings CCM Secretariat has updated on the tentative planned dates for the next 2 sessions of the CCM meeting. - Session 1: A whole day meeting will be taken place on 26 July 2016 at the hotel. The meeting will focus on review of CCM composition, TORs and selection of the new CCM members as the current term of service of the CCM chair, deputy chairs and members will expire by the end of this fiscal year. - Session 2: A whole day meeting will be taken place on 28 September 2016 at the hotel. The meeting will focus on conducting an orientation workshop for the new CCM members and a light Eligibility and Performance Assessment (EPA). Review TOR for the Technical Assistance for the CCM To ensure the achievement and facilitation of the process, the Global Fund is proceeding the recruitment of Technical Assistants (TA) to provide technical support to the Lao CCM in these two sessions. The TOR and CVs of the TAs were reviewed and discussed during the meeting. The participants proposed to add some points into the TOR: - Main objective of the consultancy: Review assessment CCM structure TOR and performance - Phase2. J: <….>, working in collaboration with the CCM member, National program and relevant stockholder. - Phase2.K: <….>, working in collaboration with the CCM member, the Secretariat, the PR and National program. The CCM secretariat will liaise with the GF CT to consider these suggestions. Review the GF guideline regarding the CCM composition The CCM Secretariat presented the CCM Composition to the participants, CCM members is compose by 24 members from 3 main constituencies: - 8 members (33.33%) from Government constituency - 5 members (20.8%) from Multi/Bilateral constituency - 11 members (45.8%) from Non-Government constituency, including CSOs, PLWD and private sector The CCM composition and members will be reviewed during the next CCM meeting which will be held in late July. Comment and recommendation from all key stakeholders will be important to prepare the process prior to the TA arrival. Discussions were extended regarding to some issues that need to be considered, such as a legal status of the CCM, more involvement of the national programs and key stakeholders in the CCM reforming process, and linkage of CCM to other existing mechanism. The participants suggested that a guidance from the leadership of the Ministry of Health is important and the CCM secretariat should consult this issue with the Executive Director of the CCM Secretariat. Review and update the Terms of Reference of CCM, Ex-Com, OC, RMC, and four Task Forces. Due to the time constraints, the CCM Secretariat invited the OC and participants to kindly review all TORs and provide their comments to the CCM Secretariat at their earliest convenient. |  |
| DECISIONS MADE |  |
| No decision made. |  |

| Agenda Item #4 | AOB |
| --- | --- |
| SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED |  |
| Update from PR: - Bank account Base on the Government policy on international grant’s bank account at the Bank of Lao (BOL), the PR has consulted with the concerned department of the Ministry of Finance. It was advised that the PR at this stage to keep the current account at the Commercial Bank and to register to the Division of Foreign Currency Administration at the BOL, until the new notice is applicable; - ACCPAC software for HSS program: Conforming to the Global Fund guideline, due to time constraints and given that no company (provider) in the country was responding to the public bidding invitation. Only one quotation was submitted from Thailand’s provider for the amount of 82.700 US. The PR needs for approval this purchase from the OC and the MOH procurement committee as single source (based on the guideline). The OC has approved the request in principle, but advised the PR to provide more information before the OC chair will sign the document. |  |
| DECISIONS MADE |  |
| The OC has approved the request in principle, but advised the PR to provide more information before the OC chair will sign the document. |  |

| 4. SUMMARY OF DICISIONS AND ACTION POINTS |  |  |  |
| --- | --- | --- | --- |
| AGENDA ITEM NO. | WRITE IN DETAIL THE DICISIONS | KEY PERSON RESPONSIBLE | DUE DATE |
| Agenda Item #1 | The last OC meeting minutes was approved |  |  |
| Agenda Item #2 | No decision |  |  |
| Agenda Item #3 | No decision |  |  |
| Agenda Item #4 | The OC has approved the request in principle, but advised the PR to provide more information before the OC chair will sign the document. | PR | By next week |

| 5. NEXT MEETING |  |
| --- | --- |
| LOCATION/VENUE | 1st Floor CCM Secretariat Meeting Room, MoH |
| DATE: | To be identified later |
| TIME |  |

| 6. OC MEETING MINUTES PREPARED BY: |  |  |  |
| --- | --- | --- | --- |
| TYPE/PRINT NAME | Phouvichit XONGMIXAY | DATE: |  |
| FUNTION/ POSITION | Technical Assistant | SIGNATURE |  |

| 7. OC MEETING MINUTES APPROVED BY: |  |  |  |
| --- | --- | --- | --- |
| TYPE/PRINT NAME | Dr. Philaysak Naphayvong | DATE: |  |
| FUNTION/ POSITION | OC Chair | SIGNATURE |  |