## Slide 1: Lao PDR Country Team Visit 8-12 August 2016 Debrief 12 August 2016
Patricia Kehoe, SFPM
Sylvester Rugumambaju, PSM Officer

## Slide 2: Agenda
PR Performance against Outcomes of March Mission
Timelines for next country allocation
Changes at the Global Fund
Lao : a Focused Portfolio
CCM changes
Malaria Program Outcomes
TB Program Outcomes
HIV Program Outcomes
HSS Program Outcomes

## Slide 3: Follow up to March Country Mission
What: to improve planning, coordination, technical capacities to address bottlenecks, accelerate implementation and timeliness of deliverables to the Global Fund.
How: The PR was to lead:
Regular coordination meetings between implementers to address grant management issues and assist in planning
Regular focal group meetings of implementer specialists (M&E, finance and procurement) to share lessons learned, address capacity building for new staff and familiarise with new GF tools and templates
Regular communication with the GF on progress
Regular support to new SR DPIC-PMU
Outcome:
This has happened to some extent – but is now not a regular feature.
Planning Meetings should be outcome / decision /solution focused to make best use of time.
Technical meetings should be regularly held to build capacities and avoid delays.
Communication protocol not agreed

## Slide 4: Performance against deliverables:
3 Disease Program PU/DRs due 15 April 2016 –
Received : TB: 27 May; Malaria & HIV: 1 June
PU and cash balance report due 15 August – not yet received
Completion of the Malaria and HIV audits and submission of audit reports by 31 May 2016.
HIV 2014 report received; 2015 malaria and HIV audits not yet received.
Timely PR Disbursement to SRs on receipt of GF disbursement
SRs report improved timing for receipt of funds
PR to circulate templates and checklists for disbursements
The PR to provide organogram of PR staff needs to manage programs and a plan how PR will assume funding of positions from 1 January 2018
Not provided
Overall the Global Fund considers the PR structure is not sustainable and needs to find efficiencies (currently 30 staff) and increase effective performance and staff accountability

## Slide 5: Critical Actions for PR Office Reform
The PR Office to:
Propose to the Global Fund by no later than 1 September 2016 options how to effectively manage grant management responsibilities and accountabilities and streamline the Office of the PR to find staff efficiencies.
The PR and Global Fund to agree by no later than 30 October 2016 on the way forward for the model for the PR Office.
The Global Fund will reduce the total PR Office budget based on an appropriate PR structure to take effect 1 January 2017.
Separately, the Global Fund to:
Pursue innovative approaches to grant management (eg Results Based Financing) as a potential option for grant funding beyond 2017 and advise the Minister by 30 October 2016

## Slide 6: Grant Management Actions for PR:
The PR Office to:
Finalise submission of PU and cash balance reports
Revised Deadlines:
TB & HSS PU and Cash Balance report - 15 September 2016
HIV & malaria PU and Cash Balance Report - 30 September 2016
Provide progress report against WTP commitments – 30 September 2016
Proceed with recruitment for NTC Finance manager; and PR finance TA
Finance TA deliverables to include revision of Finance Manual & SOPs
Find savings to secure TA to revise the HR manuals/ job descriptions
Risk Assessment & Mitigation Planning for all 3 disease programs ($80k funded by Luxembourg Government) planned for October 2016
PR to establish mechanism for fund release and secure TA
Work together with HSS program and each program to identify savings from each grant to assist with DHIS2 training to the district level and propose to the GF by 30 September 2016
GF to advise on final close out actions & deadlines for SSF & TFM grants – namely refund of (i) final ineligible amount; (ii) cash remaining at grant end; (iii) stolen/lost assets.

## Slide 7: PSM Issues - MoH – PR procurement Unit
MA follow up - PSM Manual
  Procurement manual, SOPs and trainings
    Translation completed & Trainings are ongoing.
    PR to report following final trainings (September and October 2016).
Procurements for 2016/2017.
  All PPM procurement for 2016 and 2017 are done, and only a few deliveries are pending.
  Local procurements are also on course with the last deliveries of OI/STI medicines expected in September 2016.

## Slide 8: Timelines for next country allocation
November 2016: Donor replenishment to the Global Fund determining total overall GF budget
Early 2017: Future country allocation to be advised. This is based on: (i) disease burden (ii) income level (iii) program expenditure October 2016
Immediate Lao focus: aim to increase implementation and expenditure (remaining 2 months)
Funds not expended (NFM grant) will be deducted from future country allocation
Global Fund will consider options re WTP commitments remaining un-met
Consider Sustainability planning for the future as the Global Fund funds between 30-40% of disease programs.

## Slide 9: Changes at the Global Fund:
Strategic framework 2017-22: differentiating to maximise impact
Scale-up evidence-based interventions with a focus on the highest burden countries with the lowest economic capacity and on key and vulnerable populations disproportionately affected by the three diseases
Support grant implementation success based on impact, effectiveness, risk analysis and value-for-money
Strategic Focus
Focus attention and engagement in few strategic areas where Global Fund support could maximize and sustain impact on the three diseases
Portfolio supervision –
portfolio supervision to focus on key portfolio risks
SFPM is the key focal point for all communications; supported by SFPA with strategic level inputs from finance, procurement & M&E specialists
Reduced involvement in day to day operational management and “hand-holding”.
Empower implementers to manage grants & leverage capacities.
LFA spot checks; CCM role in oversight.

## Slide 10: Lao – Focused portfolio: Streamlining Processes
  Concept Note Application
  Application process to be streamlined - TRP involvement only if material changes to the approach outlined and reviewed in 2015.
  Additional information to be advised regarding template and timelines for concept note and grant negotiations
  Potential one GF malaria grant
  Potential to consider innovative approaches differentiated to country needs
  Implementation
  Performance Framework to be streamlined to reduce indicators - opportunity to reinforce HSS and DHIS2 as one national system for data

## Slide 11: Lao – Focus Country Implementation Finance Reporting
PU/DR once a year covering periods January –December plus 6 months buffer
PU once a year covering periods January-June (no finance information)
Cash Balance (quarterly template) for 6 months January-June
Annual Tax Report
External audits to be undertaken using GF pre-selected auditor
Internal audit-once every two years
Budget and Financial Guidelines for all grants
Budget reallocation to be undertaken once a year (with PUDR)
Budget flexibility: do not need to request GF prior permission for increases that do not exceed 5% of a given cost input budget within an intervention’s annual budget (e.g. 5% of Per diems costs under “Policy, planning, coordination & management” for a given year of one grant). Document the rationale for the change
Exceptions where the PR must request GF pre-approval for expenditure increase:
Increases in the salary, grades, numbers or LOE of staff & allowances;
Increased budget for international travel; training budgets; vehicles /motorbikes;
Introduction of new activities or budget line items;
Increases in Health Products and pharmaceuticals
Please refer to http://www.theglobalfund.org/en/guidelines/

## Slide 12: CCM Oversight
Technical assistance currently in process to
Review CCM membership and composition and assist with Eligibility Performance Assessment
Increase members’ understanding and engagement in grant oversight.
CCM Secretariat to submit budget request to the Global Fund to extend the current agreement until December 2016 to align with financial year (31 August )
CSO Coordination Committee to elect CSO and disease representatives . Ongoing support from French 5% and FRC strengthening capacity to participate effectively.
Global Fund CCM Hub to be the primary focal point for matters CCM.
CCM agreement for 3 years – annual budget envelope based on past averages

## Slide 13: Malaria Program: Outcomes
Fully costed Malaria NSP currently with the Minister for approval.
Procurement in train for 84,000 LLINs for continuous distribution (pregnant women) and funding for distribution committed (MOH WTP contribution).
CMPE to send confirmation email of same.
DHIS2 rolled out to 50% of districts but only 20% are operational due to (i) lack of internet; (ii) lack of computer or (iii) lack of training.
All district staff should coordinate & share resources as districts can successfully report DHIS2 for other health programs (eg MCH and EPI)
HSS & Malaria programs to identify potential savings for DHIS2 training at the district level & submit proposal as part of cash balance report 30 September
Several surveys in the pipeline: re-stratification survey (September 2016); Pre-elimination survey; Social Indicator survey; RAI migrant population surveys 2016; survey on budget use; drug efficacy survey and MIS (Q5 &Q6).
CMPE to update the GF with a table listing surveys, districts, coverage and timelines - for final GF decision on MIS by 31 August
TWG to consider and recommend how to improve interface of mobile community outreach workers with village health workers and government partners eg develop guidelines, partnerships in order to ensure improved suspect referral pathways

## Slide 14: PSM Issues - CMPE
Over all there has been a 42% reduction in malaria cases. Although this is based on half year data, it is still a good indication. Challenges remain in HR and LMIS.
LMIS
  the ODK and mSupply are running concurrently but at different levels
  There's is still need to focus on long term systems development strategy and eventually integrate into 1 national LMIS system.
ACTS
CMPE confirmed that there are no gaps in the inventory of ACTs in the country.
There are concerns on the expired stocks at lower levels of the supply chain.
There is need for possible recall and safe disposal in line with FDD guidelines.
CMPE will share the stock status of ACTs and RDTs with the PR and GF by August 31st 2016.
LLIN procurement and distribution
  All LLINs arrived in the country and there are no gaps between now (2016), 2017 and 2018.
  They have all been distributed to end users.
  CMPE confirmed that all LLINs have now been distributed to end users.

## Slide 15: TB Program Outcomes
NTC to advise the Global Fund of agreed timelines for DHIS2 phased integration and reporting by 31 August 2016.
Drug resistance Survey – shortfall of funds as other donor contributions are no longer achievable. NTC to revert to the Global Fund with an outline of the planned approach – ie modified DRS and/or savings to be found from budget (with cash balance report due 15 September) .
TWG to consider and recommend how to improve the interface of mobile community outreach workers with village health workers and government partners eg develop guidelines, partnerships in order to ensure improved referral pathways and case detection.

## Slide 16: PSM Issues - NTC
There is good progress in the scale up of the geneXpert in the TB diagnosis and capacity utilizations of the machines is at 88.9%
There is still an estimated 60% of the cases that go undiagnosed and this need to be addressed.
The NTC has highlighted a number of key challenges affecting progress, these challenges need to be addressed and if a plan can be made before the end of this year, it would help improve the diagnosis.
HR Challenges remain in numbers, knowledge and skills and this has to be addressed.
The French 5% will help support diagnosis.
GF will review the cartridges forecast and the pediatric transition plan and provide feedback to the country by 31 August 2016.
Medicines and laboratory supplies
NTC confirmed that there are no gaps in supplies and orders have been made for 2017 supplies.
There is a plan to scale up use of geneXpert in 2017 but at the same time microscopy and x-ray will not be ignored.

## Slide 17: HIV Program Outcomes
Continued Blood Safety is critical, NBTC has submitted National Blood Strategy 2016-20 for Cabinet and General Assembly consideration. NBTC to find sustainable funding solution for the longer term
Policy and Protections Framework Assessment report agreed by the MOH.
Meeting 1 September to disseminate findings
CHAS to prioritize recommendations - grant budget of $50k allocated for this
Working with PEPFAR to address stigma and discrimination in health care settings
Follow up from STI Study is in progress – national STI guidelines reviewed and plans to implement measures to improve; STI Drug resistance survey – planning underway with Centre Merieux support.

## Slide 18: PSM Issues - CHAS
ARVS stock levels – expiries and treatment options.
  Procurements for all pharmaceuticals for 2016 and 2017 have been made.
  There are differences between the HPL and the actual procurements. GF and PR procurement team will finalize the HPL one the testing algorithm is confirmed by sept 30 2016.
HIV Testing algorithm
A final report is expected by September 2016.
If the report is not release, in view of lead times procurements for RDTs will be made as per current HPL based on current testing algorithm.
Condoms distributions
GF will confirm with PR the possibility of extending the PSI contract to ensure that the stocks in the country are distributed (estimated to take about 18 months). GF will confirm options by Friday 19 August 2016.
The extension will not cover new procurements.
NBTC
There are gaps in ensuring blood safety for 2016 ($80k) medical consumables & campaign financing. CHAS to propose use of HIV savings to the GF with cash balance report due 30 September 2016.

## Slide 19: HSS Program Outcomes
Proceeding with program implementation – DHIS2 some challenges at provincial level/district level – mainly due to lack of sharing resources/facilities. Imperative that programs encourage use - required by Government by March 2017.
Financial assessment report in process to address financial reporting of donor funding as part of the national budget. Considerable fragmentation/silo and duplication of resources/systems is noted. Issue for all donors
M&E Coordinator position to be re-advertised. Salary should be attractive but comparable to other programs.
WHO TA: DPIC-PMU to coordinate with SSRs and provide refinements as necessary to TA TORs; quarterly consultations with WHO on recruitment and performance.

## Slide 20: PSM Issues – HSS/MPSC/CHAI
HSS PSM activities:
  Long term priority is to develop a comprehensive unified approach to the supply chain (storage distribution and LMIS).
      There is significant progress in the roll out of LMIS and an integrated approach has been agreed.
      PR will work with MPSC/FDD/CHAI and other stake holders to propose a unified distribution system by 31 December 2016.
  TA: knowledge and skills transfer to nationals in a given timeframe – this cuts across all grants. All long term TA and national counterparts agree clear plans for 2017 by 30 November 2016.
  MPSC to share renovation plans and budget for the CMW and also a list of provincial and district stores that need refurbishment by 30 September 2016.
  HR challenges still cuts across all grants and this need to be carefully considered with initial phase focusing on the refresher trainings.