## Slide 1: CCM Meeting Tuesday 09th February 2021 PMU Update

## Slide 2: Contents
Grant Closure Planning for HIV and TB
Grant Expenditures as at 31 Dec 2020
Co-financing update as at 31 Dec 2020
Malaria RAI2E & RAI3E will be updated by UNOPS

## Slide 3: Grant Closure Planning
The DPC-PR/PMU is planning to close out of 2 grants: LAO-T-GFMOH ( 2018-2020)/RSSH and LAO-H-GFMOH(2018-2020) which has been consolidated into LAO-C-MOH (HANSA) in the Implementation Period 2021-2023
The Implementation Period of these two grants has been ended on 31 December 2020.
Closeout required deliverables:
  Closure budget for Sub-recipients who are not expected to continue under the New Grant : PSI, MPSC, HMIS ( Statistic UNIT of DPC),they will develop an itemized costed budget for all activities that will be implemented during the closure period after the Implementation Period end date 31 December 2020),submission due date 15 Sept 2020_DONE

## Slide 4: Grant Closure Planning
  The Closure Budget for Sub-recipients will need to be endorsed by the CCM Chair and Vice-Chair, and reviewed and verified by the Global Fund’s Local Fund Agent (“LFA”)._DONE and APPROVED
  ii. List of Program Assets and Receivables: Submission due date 15 Sept 2020
      DONE and will be reported once again in 2020 PU which will be submitted on 1st. March 2021
iii. All Health Products procured with Grant Funds that are not likely to be used / consumed before the Implementation Period end date;
    Other Program Assets (including, but not limited to, vehicles, equipment and infrastructure and non-physical assets such as copyright in any Information, Education and Communication (“IEC”) materials or television spots) created / acquired with Grant Funds); and
    All receivables owed to the Principal Recipient by a third party.

## Slide 5: Grant Closure Planning
iv. maintain Program Books and Records_In Negotiation with DOF/MOH to keep these records in Central Warehouse/MOH
  for at least seven years from the date of the last disbursement under the Grant.
  develop a plan to determine where and how the Program Books and Records will be stored for that period.
v. Final Progress Update for the Grant, Submission due date 1st March 2021_On Going
  This shall include:
    The programmatic and financial progress report for the period between the last progress report and the Implementation Period

## Slide 6: Grant Closure Planning
    The expenditure report for the period between the last expenditure report and the Implementation Period end date (including any extensions).
vi. Audit Report , Submission due date 30 June 2021_will be conducted in March-April
  This shall cover the last year of the Implementation Period (including any extensions). The Global Fund will inform the PR of the timelines of the audit as this is managed through the regional finance audit initiative by the Global Fund Secretariat
vii. Final Tax Report for the Grant, Submission due date 30 June 2021_Prepared by PMU
  This shall cover the final year of the Implementation Period (including any extensions).

## Slide 7: Grant Closure Planning
viii. Financial Closure Report, Submission due date 1August 2021_Will be prepared by PMU/Finance manager
  This shall include:
    The financial reconciliation of the cash balance as at the end of the Implementation Period (including any extensions);
    The expenditure report covering the period from the last submitted expenditure report up to the end of the closure period (i.e. six months after the end of the Implementation Period); and
    An updated list of financial commitments and financial obligations as at the Implementation Period end date.
The Grant Closure Reporting Documents will be reviewed and verified by the LFA and the Global Fund
Any remaining cash, non-compliant expenditures or recoverable amounts should be swiftly determined and returned to the Global Fund.

## Slide 8
TB Grant Update
PU 2020

## Slide 9: Programmatic Update
Indicator | Type of TB | Target | Achieve | %
1 | TB all forms New+ Relapse | 8592 | 8012 | 93,24
2 | Treatment out come | 90% /6808 | 6145 | 90
3 | MDR TB | 80 | 49 | 61
4 | MDRTB Receive SLD | 49 | 39 | 79.5
5 | TB’HIV ART | 364 | 292 | 80
6 | TB Regional | 724 | 169 | 23

## Slide 10: Financial Update : Budget vs Estimated Expenditure as at 31 Dec 2020 – By Module
Module | Budget 2020 | Expenditure 2020 | Cumulative Budget 2018 -2020 | Cumulative Expenditure 2018 -2020 | Burn Rate
TB care and prevention | $2,126,350 | $2,051,422 | $4,741,241 | $4,666,292 | 98%
Program management | $808,744 | $694,938 | $2,430,505 | $2,316,669 | 95%
MDR-TB | $299,398 | $150,932 | $542,675 | $394,209 | 73%
TB/HIV | $54,856 | $50,931 | $136,833 | $132,907 | 97%
RSSH: Health management information systems and M&E | $150,842 | $105,250 | $259,510 | $213,918 | 82%
RSSH: Procurement and supply chain management systems | $34,588 | $6,921 | $131,864 | $104,196 | 79%
COVID-19 | $404,390 | $100,127 | $404,390 | $100,127 | 25%
Grand Total | $3,879,168 | $3,160,520 | $8,647,017 | $7,928,318 | 92%

## Slide 11: Financial Update: Budget vs Estimated Expenditure as at 31 Dec 2020 – By Implementer
Implementers | Budget 2020 | Expenditure 2020 | Cumulative Budget 2018 -2020 | Cumulative Expenditure 2018 -2020 | Burn Rate
NTC and SSRs | $3,157,265 | $2,558,846 | $6,693,231 | $6,094,761 | 91%
HMIS | $153,079 | $144,539 | $418,072 | $409,532 | 98%
MPSC | $64,401 | $49,044 | $291,990 | $276,632 | 95%
LaoPHA | $112,048 | $106,795 | $267,369 | $262,116 | 98%
PEDA | $78,874 | $73,023 | $193,403 | $187,551 | 97%
PSI | $107,876 | $84,780 | $278,118 | $255,021 | 92%
PMU | $205,624 | $143,494 | $504,834 | $442,704 | 88%
Grand Total | $3,879,168 | $3,160,520 | $8,647,017 | $7,928,318 | 92%

## Slide 12: HIV Grant Update PU 2020

## Slide 13: Programmatic Update
Indicators | Target | Achievement | %
KP-1c: Percentage of sex workers reached with HIV prevention programs - defined package of services | 10,200 | 10,108 | 99%
KP-3c: Percentage of sex workers that have received an HIV test during the reporting period and know their results | 9,180 | 9,099 | 99%
KP-1a(M): Percentage of men who have sex with men reached with HIV prevention programs - defined package of services | 1,400 | 1,509 | 108%
KP-3a(M): Percentage of men who have sex with men that have received an HIV test during the reporting period and know their results | 1,260 | 1,419 | 113%
TCS-1(M): Percentage of people living with HIV currently receiving antiretroviral therapy | 7,526 | 8,182 | 109%

## Slide 14: Financial Update :Budget vs Estimated Expenditure as at 31 December 2020 – By Module
Module | Budget 2020 | Expenditure 2020 | Cumulative Budget 2018 -2020 | Cumulative Expenditure 2018 -2020 | Burn Rate
Comprehensive prevention programs for sex workers and their clients | $333,807 | $354,229 | $723,185 | $743,608 | 103%
Program management | $573,297 | $477,209 | $1,641,847 | $1,545,759 | 94%
Comprehensive prevention programs for MSM | $183,953 | $211,493 | $328,674 | $356,214 | 108%
Treatment, care and support | $1,537,966 | $1,300,035 | $3,024,600 | $2,786,670 | 92%
HIV Testing Services | $361,535 | $315,826 | $960,225 | $914,516 | 95%
TB/HIV | $1,964 | $2,270 | $5,083 | $5,388 | 106%
COVID-19 RM | $1,943,696 | $247,664 | $1,943,696 | $247,664 | 13%
Grand Total | $4,936,217 | $2,908,725 | $8,627,309 | $6,599,818 | 76%

## Slide 15: Financial Update : Budget vs Estimated Expenditure as at 31 December 2020 – By Implementer
Implementer | Budget 2020 | Expenditure 2020 | Cumulative Budget 2018 -2020 | Cumulative Expenditure 2018 -2020 | Burn Rate
CHAS | $3,247,234 | $2,345,118 | $5,760,740 | $4,858,624 | 84%
PEDA | $105,533 | $98,418 | $317,992 | $310,878 | 98%
PSI | $110,796 | $98,720 | $334,795 | $322,719 | 96%
LaoPHA | $253,752 | $203,418 | $675,519 | $625,185 | 93%
PMU | $575,051 | $163,052 | $894,411 | $482,412 | 54%
NTC | $487,852 | $0 | $487,852 | $0 | 0%
CMPE | $156,000 | $0 | $156,000 | $0 | 0%
Grand Total | $4,936,217 | $2,908,726 | $8,627,308 | $6,599,817 | 76%

## Slide 16
PSI Program Income Expenditures | Amount USD
Total receipt 2018-2020 | $571,467
Less: expenditure for Condom procurement for social marketing | $356,833
Less: Management cost for Condom Social Marketing +loss on exchange rates | $150,885
Balance Dec 2020 | $63,749

## Slide 17: Tuberculosis Elimination among Migrants ( TEAM) PUDR Dec 2020

## Slide 18: Financial Update: Budget vs Estimated Expenditure as at 31 Dec 2020 – by Module
Module | Budget 2020 | Expenditure 2020 | Cumulative Budget 2018 -2020 | Cumulative Expenditure 2018 -2020 | Burn Rate
TB care and prevention | 214,279.82 | 202,481.28 | 710,436.80 | 543,405.82 | 76%
Program management | 107,004.13 | 95,205.00 | 196,784.09 | 148,540.87 | 75%
RSSH: Health management information systems and M&E | 20,019.61 | 10,881.92 | 28,562.68 | 14,329.04 | 50%
Grand Total | $341,304 | $308,568 | $935,784 | 706,275.73 | 75%

## Slide 19: Financial update : Budget vs Estimated Expenditure as at 31 Dec 2020 – by implementer
Implementers | Budget 2020 | Expenditure 2020 | Cumulative Budget 2018 -2020 | Cumulative Expenditure 2018 -2020 | Burn Rate
NTC | $201,204 | $177,118 | $697,670 | $521,705 | 75%
LaoPHA | $67,426 | $73,639 | $113,631 | $97,872 | 86%
PEDA | $66,007 | $57,811 | $111,149 | $86,699 | 78%
PMU | $6,667 | $0 | $13,333 | $0 | 0%
Grand Total | $341,304 | $308,568 | $935,784 | $706,276 | 75%

## Slide 20: Sustainability of HIV services for Key Populations in Asia (SKPA)_HIV Regional Grant
Implementer | Budget 2020 | Expenditure 2020 | Cumulative Budget 2018 -2020 | Cumulative Expenditure 2018 -2020 | Burn Rate
LaoPHA | $617,629 | $172,185 | $732,175 | $195,451 | 27%
Grand Total | $617,629 | $172,185 | $732,175 | $195,451 | 27%

## Slide 21: Summary of Co-Financing Expenditures 2018-2020
Component | Approved budget 2018-2020 | Cumulative Expenditures 01/2018-12/2020 | Obligation carried over to Q1/2021 | Projected burn rate
TB | $1,567,200 | $947,063 | $435,113 | 88%
HIV | $1,482,942 | $1,474,373 | $235,154 | 115%
Mal RAI2E | $1,604,623 | $1,664,288 |  | 104%
Total | $4,654,765 | $4,085,724 | $670,267 | 102%

## Slide 22
Thank you