## Slide 1: CCM Meeting 6 April 2021 PMU UPDATE: PU 2020 Report for TB Country Grants ( 2018-2020)

## Slide 2: TB Case Notification and Treatment Success
 | Target | Result | Achievement Ratio | Comments
TB Case Notification | 8592 | 8014 | 93% | The number of cases notified in collaboration with CSOs/Private Partners is PSI (289/232=124%), Laopha (256/173=147%), PEDA (93/113=82%), HPP (55/113), and Lao Youth (0 ) The case detection is increased compare to previous year. The main reasons for this are: 1. SOP of sample transportation was improved even project sites are affected by Covid; 2. Decentralization of ACF Team to province level, now there are 7 teams in the country; 3. Gene Xpert coverage is close to 90% in 2020; 4. Increased sensitive screening for TB using Digital X ray, and increased clinical diagnosis; 5. Case detection activities restarted immediately after Covid 19 pandemic country lockdown; 6. Good collaboration and committed from each level of central and local authorities NTC, province, districts, Health centers and CSOs; 7. NTC used additional funding (PAAR) to fill some gaps e.g: providing additional equipment‘ : computers, cool boxes and refrigerator to store specimens at health center level. 8 NTC staffs provided technical training and coaching to local ACF teams for building their capacity.
Treatment Success | 6485(N#) 7205(D#) 90.00% | 6145 (N#) 6808 (D#) 90.3% | 100% | Jan- Dec. 2020: reported treatment outcome of the cohort 2019 of TB cases all forms (New and relapse) registered and started on treatment. Total 6,145 among 6,808 (90.3%) were treated successfully.

## Slide 3: MDR TB Notification and 2nd Line Treatment
 | Target | Result | Achievement Ratio | Comments
MDR Case Notification | 90 | 49 | 54% | Treatment coverage for MR/RR-TB compared to estimated WHO incidence is lower due to limited Xpert MTB testing coverage for diagnosis of rifampicin resistance (66% in 2019). NTP has increased Xpert testing coverage in 2020 close to 90%,
MDR began 2nd line treatment | 81 | 39 | 48% | Enrollment rate of MDR/RR-TB patients is lower than 90% due to late diagnosis and patients dying before treatment or refusing treatment. NTC is promoting more decentralized programmatic management of MDR/RR-TB

## Slide 4: TB/HIV Cases Receive ART
 | Target | Result | Achievement Ratio | Comments
TB/HIV Cases Receive ART | 338(N#) 376(D#) 89.89% | 292(N#) 364(D#) 80.21% | 89% | Jan- Dec. 2020: total 292 among 364 (80%) TB HIV positive patients were started on ART with breakdown by provinces as follows: VTC (162) PSL (1) LNT (2) ODX(2) BK (1) LPB(8) HP (2) SBL(3) XK(0) VTP (5) BLS (0) KM (10) SVK(43) SLV (1) SK (1) CPS (51) ATP(0) SSB(0). Low uptake of early ART treatment for all TB HIV positive patients by the physicians; NTC and CHAS recently updated their joint TB-HIV guidelines to promote early ART treatment based on latest WHO recommendations

## Slide 5: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (1)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
1. Human Resources | $556,608 | $506,493 | $50,115 | 91.0% | The balance includes $45k (a bit grater than initial amount) approved amount for some staff extension during grant closure period Jan-Jun 2021. The details are as follows: NTC= $10.3k; PEDA=$2.7k; PSI= $3.1k; LaoPHA=$2k; PR=$26.9k
2.Travel related costs (TRC) | $683,944 | $580,982 | $102,962 | 84.9% | Of the balance, $52.8k carry over for the Xpert training and monitoring which have been budgeted under Covid module using Covid flexibility budget. The remaining is saving, that is due to some activities were not fully implemented as planned during Covid 19 affected months and savings from different exchange rates.

## Slide 6: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (2)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
3.External Professional services (EPS) | $188,154 | $157,086 | $31,067 | 83.5% | The balance mainly includes as follows: NTC= $9.6k - a financial obligation for 2020 audit fee (vs initial approved amount $15.7k); PR=$13.6k a saving from budget revision to be added to the saving identified in Covid flexibilities.
4. Health Products - Pharmaceutical Products (HPPP) | $310,711 | $310,711 | $0 | 100.0% | Fully completed
5. Health Products - Non-Pharmaceuticals (HPNP) | $183,355 | $98,740 | $84,615 | 53.9% | The balance includes $57.7k- a financial obligation for ongoing procurement of Covid health commodities and products. The rest goes to the saving. The saving is due to over budgeting/lower cost comparing to the approved budget for lab supplies and consumables

## Slide 7: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (3)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
6. Health Products - Equipment (HPE) | $1,084,066 | $878,451 | $205,615 | 81.0% | Of the balance, $74.6k is financial obligations for some procurements those are now under process and include as follows: - $59.5k for Monitor and Ventilator for ICU bed budgeted under Covid module; -$15k for health products and equipment for MDR TB ward sand laboratory. if added up these obligation, total expenditure absorption rate will reach 88%. Estimated saving of $131k is mainly due to Xpert Xpress SARS-CoV-2 cartridges were not fully procured as planned 1000 test kits, but only 376 kits were procured in the reporting period, 503 test kits of the remaining have been moved and procured under HIV grant budget.

## Slide 8: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (4)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
7.Procurement and Supply-Chain Management costs (PSM) | $133,609 | $97,919 | $35,690 | 73.3% | The balance goes to savings. That is mainly due to PSM costs budgeted at 15% of 1000 test Kits of Xpert Xpress SARS-CoV-2 cartridges were not fully procured as planned, but only 376 kits were procured in the reporting period and health products and equipment procured locally do not require PSM costs separately, but are included in the goods prices.
8.Infrastructure (INF) | $95,773 | $3,664 | $92,109 | 3.8% | Of the balance, $65k is financial obligations for ongoing process of MDR TB wards renovation in two provinces. The saving is due to lower cost comparing to the initial budget.
9.Non-health equipment (NHP) | $241,329 | $205,981 | $35,348 | 85.4% | NTC: $45.7k a financial obligation reported in this reporting period includes $39.2k for on process of 38 computer procurements to support DHIS2 in targeted districts; $6.5k for MDR TB wards. If added up this obligated amount, total expenditure rate will reach 104%. There will be a negative balance, it’s because of the higher price of computers comparing to initial plan.

## Slide 9: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (5)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
10. Communication Material and Publications (CMP) | $17,819 | $16,485 | $1,334 | 92.5% | small balance
11. Indirect and Overhead Costs | $137,012 | $121,137 | $15,875 | 88.4% | Of the balance, $4.1k carry over for office administrative cost during grant closure period. That carried over amount includes $3.2k for PR and $0.9k for PSI office running costs.
12. Living support to client/ target population (LSCTP) | $121,205 | $90,637 | $30,568 | 74.8% | The balance is mainly due to the lower MDR TB cases comparing to the initial targeted numbers were found during implementation period. Of the balance, $27.1k relates to underspending of MDR TB patient living supports.
13. Payment for Results | $125,585 | $127,579 | -$1,995 | 101.6% | Fully completed
Grand Total | $3,879,168 | $3,195,863 | $683,304 | 82.4% | 

## Slide 10: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (1)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
1.TB care and prevention/cases detection and diagnosis | $1,658,239 | $1,585,269 | $72,970 | 95.6% | 
2.TB care and prevention/Engaging all care providers ( TB Care and prevention) | $45,639 | $40,413 | $5,226 | 88.5% | The balance is mainly from PSI ($5.2k since PSI could not implement activities fully as planned during the Covid pandemic especially the activates of regular provider’s behavior change communication (PBCC) with all SQH clinics and pharmacies providing TB case detection (bl#73) and PSI Performance Based Financing including transportation (bl#64).
3.TB care and prevention/Engaging all care providers (TB/HIV) | $7,047 | $6,000 | $1,047 | 85.1% | This is about incentive payment for 5 contracted provincial coordinators, the balance from the gain on different exchange rate.
4.Program management/Grant Management | $643,186 | $563,797 | $79,389 | 87.7% | Of the balance, $9.6k is reported as financial obligation for audit 2020 and $49.9k is carried over for some contracted staff extension during grant closure period Jan-Jun 2021 as per approved grant closure budget.

## Slide 11: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (2)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
5,Program management/other Program management intervention | $97,773 | $96,915 | $858 | 99.1% | 
6.TB care and prevention/treatment | $276,942 | $281,548 | -$4,606 | 101.7% | 
7.MDR-TB/treatment MDR-TB. | $294,125 | $145,023 | $149,102 | 49.3% | Of the balance, $78k is financial obligation for ongoing procurement of MDR TB ward equipment and renovation of two MDR TB wards in Savanakhet and Champasack. The rest is saving, that is due to the lower costs of above procurements comparing to the initial budget and lower MDR TB patient cases found (Patient living support is paid based on the actual number of patients) in the reporting period.

## Slide 12: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (3)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
8.TB/HIV/TB/HIV collaboration Interventions | $47,809 | $44,931 | $2,878 | 94.0% | The balance includes: - overspending on Training workshops in ICF and IPT and Training on HIV counseling and care -$12k (NTC did conduct more trainings); - over budgeting and unspent amount in the reporting period =$14.8k includes $6.1k for ongoing procurement/financial obligation for HIV Viral Load Testing using GX.
9. Program management/ Policy, Planning, Coordination and Management of National Disease Control Program | $67,785 | $69,032 | -$1,247 | 101.8% | 
10.TB care and prevention/Community TB Care Delivery | $145,530 | $144,730 | $800 | 99.5% | 

## Slide 13: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (4)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
11.RSSH: Health management information systems and M&E/Program and data quality | $140,098 | $95,185 | $44,913 | 67.9% | Of the balance, $39.2k is financial obligation for ongoing procurement of 38 computers to support DHIS2 in some targeted districts. Small balance goes to savings
12.RSSH: Health management information systems and M&E/Analysis, review and transparency | $2,080 | $2,169 | -$89 | 104.3% | 
13. RSSH: Health management information systems and M&E/other health information system and M&E intervention | $8,665 | $7,896 | $769 | 91.1% | 

## Slide 14: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (5)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
14.RSSH: Procurement and supply chain management systems/other procurement supply chain management intervention | $33,423 | $6,921 | $26,502 | 20.7% | The balance includes: - MPSC $13k- activities of Monitoring and supervision visits and Training of Trainers - Capacity building of provincial level (bl#132&133) were not fully implemented because of Covid pandemic; -PMU $13k- Saving from budget revision (bl#247) be added to the saving for Covid flexibility
15.MDR-TB/Case Detection and Diagnosis: MDR TB | $5,273 | $5,909 | -$636 | 112.1% | small negative balance
16. MDR-TB/Prevention for MDR TB | $0 | $0 | $0 | N/A | 

## Slide 15: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (6)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
17.RSSH: Procurement and supply chain management systems/Supply Chain infrastructure and development of tools | $1,166 | $0 | $1,166 | 0.0% | MPSC Printing of eLMIS Manuals for Training is cancelled since the manual has not been finalized in the implementation period.
18. COVID-19/Risk mitigation for disease programs | $349,790 | $100,127 | $249,663 | 28.6% | The balance includes: - NTC $110k_ financial obligation for local procuring Monitor and Ventilator for ICU bed (bl#237) and QIAamp viral RNA Mini Kit (bl#240) , which are now under process; - NTC $52.8k_carry over for trainings on Xpert - Training (bl# 235) and Xpert - Monitoring and supervision visits (bl#240). If added this amount, the expenditure rate of this line will reach 75%. The reaming (25%)/saving relates mainly to the Xpert Xpress SARS-CoV-2 cartridges (bl#233&234) were not fully procured as planned 1000 test kits, but only 376 kits were procured in the reporting period, 503 test kits of the remaining have been moved and procured under HIV grant budget

## Slide 16: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (6)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
19. COVID-19/Covid 19 Control and containment including health system strengthening | $54,600 | $0 | $54,600 | 0.0% | The balance includes $22.6k a financial obligation reported in the reporting period for ongoing procurement of Covid health commodities (Surgical mask bl#238). The remaining is saving, that is due to the lower costs comparing to the initial budget and unspent PSM cost since a local procurement does not present PSM cost separately, but included in unit price.
Grand total | $3,879,168 | $3,195,863 | $683,304 | 82.4% | 

## Slide 17: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (1)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
The National Tuberculosis Center | $3,068,058 | $2,492,589 | $575,470 | 81.2% | Of the balance, - NTC has a financial obligation amounting to $265.5k for ongoing activity implementations and procurements. Those include as follows: i) $132.5k- for activities budgeted under Covid 19 (Covid Flexibility budget, bl#237,238 &240); ii) 132.9k- for non Covid activities (bl#53, 209, 227, 231, 232, 243 and 244). - NTC carried over activities $63.1k includes $52.8k for Covid activities (bl#235&236) and $10.3k non covid activities or grant closure budget approved for some staff extension Jan-Mar 2021. If added up these amounts, the total expenditure rate will reach 92%. - the major savings come from the Xpert Xpress SARS-CoV-2 cartridges (bl#233&234) were not fully procured as planned 1000 test kits, but only 376 kits were procured in the reporting period; lower cost of some health products and equipment comparing to the initial budget, underspending for MDR TB patients (cases based), some activities were not fully implemented during covid affected months especially AFC activities and etc.

## Slide 18: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (2)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
Centre D' Infectiologie Lao-Merieux (CILM) | $20,484 | $22,272 | -$1,788 | 108.7% | The negative balance is due to higher costs of Lab consumables. there was non major budget adjustment internally for this higher costs.
Ministry of Health of the Lao People's Democratic Republic | $205,624 | $143,494 | $62,130 | 69.8% | The balance includes: i) $3.5k financial obligation for autoclave procured on behalf of NTC (bl# 247); ii) $30.2k grant closure budget for some staff extension Jan-Jun $26.9k and office administrative cost $3.2k including estimated cost for expired drugs and broken assets disposal. if added up this amount, expenditure rate will reach 86%. The remaining/saving 14% is mainly due to lower cost of autoclave procured locally and saving identified from the budget revision (bl# 247) to be added to the Covid flexibility.

## Slide 19: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (3)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
Population Services International (PSI) | $107,876 | $88,279 | $19,597 | 81.8% | PSI was not able to implement the activities fully as planned in the reporting period because of Covid pandemic especially the activates of regular provider’s behavior change communication (PBCC) with all SQH clinics and pharmacies providing TB case detection (bl#73) and PSI Performance Based Financing including transportation (bl#64) and underspending for office administrative cost. Of the balance, $4k is carried over for some staff extension and small amount for the office running costs as per approved grant closure budget.
Promotion for Education and Development Association (PEDA) | $78,874 | $73,023 | $5,851 | 92.6% | The balance includes $2.7k carried over for some staff extension during grant closure as per approved budget. If added up this amount, PEDA total expenditure will reach 96%

## Slide 20: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (4)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
Mutual Assistance for Attapeu People (MAAP) | $5 | $4 | $0 | 96.7% | 
Lao Positive Health Association (LaoPHA) | $112,048 | $106,795 | $5,253 | 95.3% | 
Lao Yout Union (LYU) | $3,338 | $3,812 | -$474 | 114.2% | not major negative balance
Humana People to People (HPP) | $65,380 | $72,014 | -$6,634 | 110.1% | The negative balance is mainly from HPP implemented more activities for raising awareness about TB in target villages (bl#183) in the reporting period. However, the overspending presented in the cumulative period is about 104% which is still in the non-major budget adjustment.

## Slide 21: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (5)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | AbsorptionRate | Reasons for Variance
Medical Procurement and Supply Centre (MPSC) | $64,401 | $49,044 | $15,357 | 76.2% | The balance includes: - $13k- activities of Monitoring and supervision visits and Training of Trainers - Capacity building of provincial level (bl#132&133) were not fully implemented because of Copid pandemic; - some balance from cancelled activities especially printing of eLMIS Manuals for Training and over budgeting (mistake) on office running costs (internet cost).
Health Management Information System (HMIS/DPC) | $153,079 | $144,539 | $8,540 | 94.4% | most of activities were completed, small balance from different exchange rates.
Grand total | $3,879,168 | $3,195,863 | $683,304 | 82.4% | 

## Slide 22: Budget vs Expenditure for the cumulative Period 1Jan 2018-31 Dec 2020_ By Cost grouping (1)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
1. Human Resources | $1,543,038 | $1,492,923 | $50,115 | 96.8%
2.Travel related costs (TRC) | $1,748,802 | $1,645,841 | $102,962 | 94.1%
3.External Professional services (EPS | $578,661 | $547,593 | $31,067 | 94.6%
4. Health Products - Pharmaceutical Products (HPPP) | $671,643 | $671,643 | $0 | 100.0%
5. Health Products - Non-Pharmaceuticals (HPNP) | $298,854 | $214,239 | $84,615 | 71.7%
6. Health Products - Equipment (HPE) | $1,897,833 | $1,692,218 | $205,615 | 89.2%

## Slide 23: Budget vs Expenditure for the cumulative Period 1Jan 2018-31 Dec 2020_ By Cost grouping (2)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
7.Procurement and Supply-Chain Management costs (PSM) | $247,968 | $212,278 | $35,690 | 85.6%
8.Infrastructure (INF) | $117,925 | $25,816 | $92,109 | 21.9%
9.Non-health equipment (NHP) | $522,645 | $487,928 | $34,716 | 93.4%
10. Communication Material and Publications (CMP) | $65,383 | $64,049 | $1,334 | 98.0%
11. Indirect and Overhead Costs | $384,923 | $368,365 | $16,558 | 95.7%
12. Living support to client/ target population (LSCTP) | $304,839 | $274,272 | $30,568 | 90.0%
13. Payment for Results | $264,502 | $266,497 | -$1,995 | 100.8%
Grand Total | $8,647,017 | $7,963,662 | $683,355 | 92.1%

## Slide 24: Budget vs Expenditure for the Cumulative Period 1 Jan 2018- 31 Dec 2020_ By Module intervention (1)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
1.TB care and prevention/cases detection and diagnosis | $3,668,514 | $3,595,523 | $72,991 | 98.0%
2.TB care and prevention/Engaging all care providers ( TB Care and prevention) | $104,593 | $99,368 | $5,226 | 95.0%
3.TB care and prevention/Engaging all care providers (TB/HIV) | $21,445 | $20,398 | $1,047 | 95.1%
4.Program management/Grant Management | $1,868,494 | $1,789,075 | $79,419 | 95.7%
5.Program management/other Program management intervention | $299,952 | $299,094 | $858 | 99.7%
6, TB care and prevention/treatment | $643,365 | $647,971 | -$4,606 | 100.7%
7. MDR-TB/Treatment : MDR-TB | $525,997 | $376,895 | $149,102 | 71.7%

## Slide 25: Budget vs Expenditure for the Cumulative Period 1 Jan 2018- 31 Dec 2020_ By Module intervention (2)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
8.TB/HIV/TB/HIV collaboration Interventions | $115,388 | $112,510 | $2,878 | 97.5%
9. Program management/ Policy, Planning, Coordination and Management of National Disease Control Program | $262,059 | $263,306 | -$1,247 | 100.5%
10.TB care and prevention/Community TB Care Delivery | $324,768 | $323,968 | $800 | 99.8%
11.RSSH: Health management information systems and M&E/Program and data quality | $237,380 | $192,467 | $44,913 | 81.1%
12.RSSH: Health management information systems and M&E/Analysis, review and transparency | $2,080 | $2,169 | -$89 | 104.3%

## Slide 26: Budget vs Expenditure for the Cumulative Period 1 Jan 2018- 31 Dec 2020_ By Module intervention (3)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
13. RSSH: Health management information systems and M&E/other health information system and M&E intervention | $20,050 | $19,282 | $769 | 96.2%
14.RSSH: Procurement and supply chain management systems/other procurement supply chain management intervention | $130,698 | $104,196 | $26,502 | 79.7%
15.MDR-TB/Case Detection and Diagnosis: MDR TB | $16,678 | $17,314 | -$636 | 103.8%
16. MDR-TB/Prevention for MDR TB | $0 | $0 | $0 | N/A
17.RSSH: Procurement and supply chain management systems/Supply Chain infrastructure and development of tools | $1,166 | $0 | $1,166 | 0.0%

## Slide 27: Budget vs Expenditure for the Cumulative Period 1 Jan 2018- 31 Dec 2020_ By Module intervention (4)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
18. COVID-19/Risk mitigation for disease programs | $349,790 | $100,127 | $249,663 | 28.6%
19. COVID-19/Covid 19 Control and containment including health system strengthening | $54,600 | $0 | $54,600 | 0.0%
Grand Total | $8,647,017 | $7,963,662 | $683,355 | 92.1%

## Slide 28: Budget vs Expenditure for the Cumulative Period 1 Jan 2018- 31 Dec 2020_ By Implementing Entity (1)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
The National Tuberculosis Center | $6,404,551 | $5,829,031 | $575,521 | 91.0%
Centre D' Infectiologie Lao-Merieux (CILM) | $61,209 | $62,997 | -$1,788 | 102.9%
Ministry of Health of the Lao People's Democratic Republic | $504,834 | $442,704 | $62,130 | 87.7%
Population Services International (PSI) | $278,118 | $258,521 | $19,597 | 93.0%
Promotion for Education and Development Association (PEDA) | $193,403 | $187,551 | $5,851 | 97.0%

## Slide 29: Budget vs Expenditure for the Cumulative Period 1 Jan 2018- 31 Dec 2020_ By Implementing Entity (2)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
Mutual Assistance for Attapeu People (MAAP) | $1,079 | $1,079 | $0 | 100.0%
Lao Positive Health Association (LaoPHA) | $267,369 | $262,116 | $5,253 | 98.0%
Lao Yout Union (LYU) | $69,217 | $69,690 | -$474 | 100.7%
Humana People to People (HPP) | $157,175 | $163,808 | -$6,634 | 104.2%
Medical Procurement and Supply Centre (MPSC) | $291,990 | $276,632 | $15,357 | 94.7%
Health Management Information System (HMIS/DPC) | $418,072 | $409,532 | $8,540 | 98.0%
Grant Total | $8,647,017 | $7,963,662 | $683,355 | 92.1%

## Slide 30: Government Co-financing committed and expended overview (in USD) 2018-2020
2018 |  | 2019 |  | 2020 |  | Comments
Committed | expended | Committed | expended | Committed | expended | 
782,194 | 432,675 | 401,096 | 514,388 | 620,136 | In progress | Reference is made to the Executive report with ref. No.0373/MOH dated 25 March 2020 of Government Co-Financing Commitment to the Global Fund supported TB Programs for the Period of 2018-2020. The Lao Government commitment for co-financing was USD 782,194 for 2018, USD 401,096 for 2019 and USD 383,909 for 2020, in total USD 1,567,199. For 2018, the allocated amount by Lao PDR Government was utilized for different activities, including procurement of two Gene-Expert machines and accessories; active case finding and the national TB consultative meeting. The total actual expenditures versus the Lao Government allocation for 2018 was USD 432,675. Therefore, the unmet amount of 2018 was USD 349, 519 (782,194 - 432,675). The gap was planned to be compensated in 2019. For 2019, the allocated and expended amount by Lao PDR Government for TB program activities was USD 514,388 (including expenditures at provincial level committed by the local authorities for an amount of USD 72,166). Thus, the total expenditures by the government for the period of 2018-2019 was USD 947,063. The unmet target in reference to the initial commitment is $ 620,136 which is planned to be allocated in 2020. For 2020, .the allocated amount by the Government was USD 435,113 and NTC is in process of conducting of activities as approved by the Government till the due date as at 31 March 2021. If compared to the total amount committed to TGF as planned, the percentage of the commitment is 88%.

## Slide 31: LAO PDR GF Disease Grant Risk Management_ update 2020
Major risks to TB Grant |  |  | 
Risks | Risk management actions_ March 2017 | Status 2019 | Status 2020
1. Estimated 60% of TB cases remain undiagnosed | Explore innovative ways of improving TB case notification, including expansion of community outreach role beyond IEC – link to sputum collection and DOTS. Include in new funding application | Currently the coverage is 50% in 2017 and estimated to be 58% in 2018 (WHO report will be distributed in Q3 2019). This increase is owed to increase the coverage by Xpert and increased detection by ACF. ACF has contributed to 19.5% (1269 cases) of the new case findings in 2018. | TB treatment coverage increased up to 61% in 2019 and 73% in 2020 (8,014 notified TB cases in NTC/HMIS DHIS2, WHO will release 2020 incidence estimate in Q3 2021); 90% Xpert testing coverage in 2020; 27% of TB cases diagnosed by ACF in 2020.
2. Financial and administrative constraints in testing sputum samples, including weak coordination and inefficient use of transportation allowances | Improved organization of transportation of sputum samples and appropriate utilization of transportation allowances | The new SOP has been developed, released and shared with GF. | Transportation of specimens between health centres and districts and from districts to provincial GeneXpert laboratories was improved.

## Slide 32: LAO PDR GF Disease Grant Risk Management_ update 2020
Major risks to TB Grant |  |  | 
Risks | Risk management actions_ March 2017 | Status 2019 | Status 2020
3. Limited integration of HIV/TB services | Expand integrated HIV/TB community-led service package. Include in new funding application | At the time of writing of two funding requests (2018-2020), representatives from both disease programmes had joint meetings and discussed about the implementation target, budget and joint interventions. Currently the services are integrated and 81% of the all TB cases are tested for HIV in 2018. This difference was because of the shortage of RDTs in some periods in the year. CHAS is implementing 3Is and almost 100% TB screening for all HIV cases and 90% of HIV/TB cases were under ART in 2018. There are quarterly joint meetings between focal points of the diseases. In addition, there are joint monitoring field visits by both disease programmes. | Both programmes developed: joint TB-HIV successful Global Fund new grant (2021-2023) under HANSA project and joint use of GeneXpert for HIV viral load (budget COVID19 RM) Updated TB-HIV guidelines quarterly meetings and monitoring field visits. 83% TB patients with HIV test result(% among all TB) 80.2% TB-HIV patients received ART treatment