## Slide 1: TB CATALYTIC FUNDING: Tuberculosis Elimination among Migrants ( TEAM)

## Slide 2: TB Indicators among migrants

## Slide 3: TB Indicators among migrants
Coverage | Target | Result | Achievement ratio | Comments
TCP-6b: Number of TB cases (all forms) notified among key affected populations/ high risk groups (other than prisoners) | 724.00 | 169.00 | 23% | According to the lockdown has started in March 2020 until now due to COVID 19, some targeted districts did not allow us to conduct the activity as our targeted population is the foreign workers/migrants (Chinese, Vietnamese, Myanmar, and Thai) who work in the risk location/areas. Therefore, those activities are postponed to Q3-Q4 2020 depending on the situation of COVID 19 and the declaration of the MOH. Therefore, it does not achieve the goals and plans set.

## Slide 4: TB Migrants – Challenges and Mitigations
Challenges | Mitigations
Access to migrant population Data collection has not been updated Language communication has also been difficult Information System is being scaled up countrywide but not yet fully functional Cross border exchange for patient follow up COVID 19 situation and no access to foreign workers camps even before the Lao Government lock-down | Update of Mapping of migrant population by Coordinating with government agencies, especially PHO, DHO, Labour and Community based by CSOs. M&E (TB tracker) supports (capacity building, supervision and material) Link the cross border info system Coordinate with COVID teams to conduct ACF in Quarantine sites IEC video clip in 4 different languages (Lao, English, Chinese and Vietnamese) Publish IEC materials (Lao, English, Chinese and Vietnamese) LED monitor signboard about health messages has already been installed at 3 border points: Luangnumtha Province, Savannakhet Province, and Borkeo Province. Plan with partners and 8 target provincials for implementing the catch-up plan: Advocacy, Quarterly re-mapping, and consultative and planning meeting at provincial level

## Slide 5: Budget vs Expenditure for the reporting period Jan-Dec 2020
Budget | Expenditure | Variance | Comments
$ 201,204.13 | 177,102.65 | 24,101.48 | The balance is saving to be carried forward in Q1 2021

## Slide 6: HIV CATALYTIC FUNDING Sustainability of HIV services for Key Populations in Asia (SKPA)

## Slide 7: HIV Regional Grant (SKPA)– Progress, Challenges and Mitigations
Activities planned in the reporting Quarter | Activities Implemented/ Major Accomplishments | Challenges faced and mitigation measures during implementation of this activity
1. Community Base Monitoring(CBM) consultation training in Khammoune Province | 33 representatives from peer counselors, healthcare worker and stakeholders which outcomes of the meeting are: 1.Identified CBM model/ approach 2.Identified focus areas. 3.CBM data collections tools (draft) 4.Identified potential sites for CBM. 5.Identified target population Comprehensive consultation meeting report | CBM tools are new in Laos which healthcare workers still not understand what CBM is? And also CBM tools need to agree by all healthcare worker and community throughout the country
2. Community Base Monitoring(CBM) consultation training in Vientiane Capital | 35 Representatives from stakeholders attended this meeting which outcome of the meeting are: 1.Finalize CBM data collections tools 2.Agreement of potential sites for CBM. 3.Agreement for target population 4.Agreement of potential site 5.Understanding about KP review report 6.Make sure the QI data collection is not 7.different from CBM data collection Comprehensive consultation meeting report – English language | CBM tools it’s self still not clear in utilization due to it has many tools inside which health care workers and stake holder worry that it might be overlap with the existing tools, therefore healthcare worker suggest to conduct another meeting to harmonize the tools and adapt the tools to utilize in over the country

## Slide 8: HIV Regional Grant (SKPA)– Progress, Challenges and Mitigations
Activities planned in the reporting Quarter | Activities Implemented/ Major Accomplishments | Challenges faced and mitigation measures during implementation of this activity
3. Stigma & Discrimination training for health care workers and Peer supporters | 27 Peer counselors, 30 healthcare workers attend this consultation workshop which the outcomes of the training are: Health care worker sensitize on stigma and discrimination Healthcare worker and peer counselor know about feedback mechanism and feedback mechanism has been reviewed | Feedback mechanism is new in Laos which it needs to implement by community, we are not sure that how much community understand and know how to use it? How can community implement efficiency?
4. Demand Creation detail activity work plan and budget with APCOM | DG detail activity work plan and budget has been completed and submitted to AFAO and shared with CHAS partner in August 2020 and expected to implement the activity by January 2021 | CHias is still waiting for the approval from AFAO in terms of reprogramming budget for 2021

## Slide 9: HIV Regional Grant (SKPA)– Progress, Challenges and Mitigations
Activities planned in the reporting Quarter | Activities Implemented/ Major Accomplishments | Challenges faced and mitigation measures during implementation of this activity
5. focus group discussion(FGD) on community demands | 20 MSM & TG will be attended Through this FGD consultation meeting, a comprehensive report will be developed which will include, but not limited to the following; MSM/TGW behavior and perception for the creation of demand generation activities in VTE city; Effective messages to promote demand generation activities in VTE city; Bottlenecks and challenges, along with its mitigation strategy, and recommendations for developing sustainable and robust campaign in VTE city. | Too many questions for participant and most of questions are technical which very hard to understand in terms of IT information. PrEP is also new in Laos which participant may not understand and response the question
6. The budget for PrEP and tests (OralQuick) to cover 200 MSM/TG has been approved and in process of purchasing. | Completed development plan for PrEP and tests (OralQuick) for the 1st year and also that PrEP costs to cover 200 MSM/TG and MoH has been approved. | The main challenging of the plan development is the advocating to national partners about the drug procurement due to partners have their plan of activity but no cost for PrEP and testing kits procurement budget,

## Slide 10: HIV Regional Grant (SKPA)– Progress, Challenges and Mitigations
Activities planned in the reporting Quarter | Activities Implemented/ Major Accomplishments | Challenges faced and mitigation measures during implementation of this activity
7. Recruited PWID consultant, developing protocol and costing developing. | The selection committee completed of selection consultant for PWID and the consultant’s contract has been developed. The implementing of the project will be started in January 2021 | Delayed of implementation due to the COVID-19 pandemic. Therefore, only one consultant applied for this call due to whole countries lockdown and external people could not travel

## Slide 11: Y2 2020 Budget vs Expenditure for the reporting period_CHIAs
Budget | Expenditure | Variance | Comments
$ 617,628.65 | $ 172,184.52 | $ 445,444.13 | Absorption rate is 27.9%. only few activities were taken place during reporting period (2020), that is due to Covid 19 pandemic. Most TRC activities are carried over and reprogrammed in 2021 in order to catch up and reach the targets as planned.