## Slide 1: CCM Meeting 6 April 2021 PMU UPDATE: PU 2020 Report for HIV Country Grant ( 2018-2020)

## Slide 2: Key Population reached _ CSWs
 | Target | Result | Achievement Ratio | Comments
KP-1c(M): Percentage of sex workers reached with HIV prevention programs - defined package of services | 10,200 | 10,108 | 99% | This indicator is implemented by PEDA and PSI in five targeted provinces together with CHAS/PCCA and DCCA. Peers provided HIV prevention service package to each FSW including HIV & STI information, BCC, provision of condom and referral to HTC. The achievement rate is 99% due to the C-19 pandemic in the country. PEDA reached this number of the target population in three provinces, KM (1331), SVK (1427), and CPS (1109). PSI reached this number of the target population in two provinces, VTC (4816) and VTP (1425). In the Year 2020, total 10,108 FSW has received the HIV prevention package and this indicator attained 99% Achievement Ratio.
KP-3c(M): Percentage of sex workers that have received an HIV test during the reporting period and know their results | 9,180 | 9,099 | 99% | This indicator is implemented by PEDA and PSI in five targeted provinces together with CHAS/PCCA and DCCA in fivs targeted provinces. The achievement rate is 99%. PEDA in collaboration with provincial health staff tested this number of the target population in three provinces, KM (1138), SVK (1219) and CPS (1099). PSI in collaboration with provincial health staff tested this number of the target population in two provinces, VTC (4315) and VTP (1328). However, we can say that this indicator is slidely achievement.

## Slide 3: Key Population reached _ MSM
 | Target | Result | Achievement Ratio | Comments
KP-1a(M): Percentage of men who have sex with men reached with HIV prevention programs - defined package of services | 1,400 | 1,509 | 108% | This indicator is implemented by CHias together with CHAS/PCCAs at the targeted provinces. Peers provided HIV prevention service package to each MSM and TG client including HIV & STI information, BCC, provision of condom and referral to HTC. This activity has been done by CHias (LaoPHA) in two provinces and their achievement rate is higher than 100%. CHias reached this number of the target population in two provinces, KM (942) and VTP (567). Total 1,509 MSM/TG has been reached by the HIV service package in 2020 and this indicator met 108% of the achievement ratio
KP-3a(M): Percentage of men who have sex with men that have received an HIV test during the reporting period and know their results | 1,260 | 1,419 | 113% | This indicator is implemented by CHias and CHAS/PCCAs from 2 provinces. The achievement rate is higher than 100%. CHias in collaboration with provincial health staff tested this number of the target population in two provinces, KM (909) and VTP (510). This data reported for the Year 2020 is 1,419 and this indicator met 113% achievement ratio. In compared with indicator target, it has been improved. CHAS will continue to work closely with NGOs and CBOs implementing partners and peer educators to provide friendly HIV testing services to the MSM/TG community for further improvement of this indicator

## Slide 4: Anti-Retroviral Therapy (ART) Coverage - CHAS
 | Target | Result | Achievement Ratio | Comments
TCS-1(M): Percentage of people living with HIV currently receiving antiretroviral therapy | 7,526 | 8,189 | 109% | At the end of the reporting period, 8189 patients were on ART including Male: 4,658 and Female: 3,531 had reported from each ART site are as follows: SVK: 1,339 (615 female,724 male), STT: 2,675 ( 1,063 female, 1612 male), MHS: 1,360 (591 female, 769 male), LPB: 588 (267 female, 321 male), CPS: 930 (403 female, 527 male), BK: 170 (92 female, 78 male), LNT :176 (85 female, 91 male), KM: 420 (212 female, 208 male), TP District : 50 (25 female, 25 male), HP: 76 (38 female, 38 male), FH: 405 (140 female, 265 male). In 2020, 8,182 people living with HIV were receiving antiretroviral therapy (ART). This indicator result reach 109% of the achievement ratio.

## Slide 5: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (1)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
1. Human Resources | $409,803 | $372,857 | $36,946 | 91.0% | The balance includes $29.7k _Support to lab technicians to take up TB, HIV and COVID testing (bl#121) carried over to Jan-Jun 2021. Additionally, $18k will be reported against this budget line which relates to the extension of some staffs for the grant closure activities Jan-Mar 2021 as per approved grant closure budget.
2.Travel related costs (TRC) | $845,425 | $717,500 | $127,925 | 84.9% | "The balance includes overspending for National survey (IBBS among FSW&MSM amounting to -$52.1k (approved budget adjustment bl#79 &80); Without above overspending, the balance includes $170.6k carried over for Covid activities/ trainings (BL# 111, 114-118, 128 and 129)"

## Slide 6: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (2)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | AbsorptionRate | Reasons for Variance
3.External Professional services (EPS) | $97,373 | $61,301 | $36,072 | 63.0% | Balance includes $9.6k _a financial obligation for audit fee 2020 (bl#13), the remaining is savings (over budgeting for audit fee)
4. Health Products - Pharmaceutical Products (HPPP) | $1,090,936 | $1,070,737 | $20,199 | 98.1% | 
5. Health Products - Non-Pharmaceuticals (HPNP) | $573,232 | $176,590 | $396,641 | 30.8% | "The balance includes as follows: i) $290.1_ financial obligation for Covid 19 health commodities and products which are now under procurement processes (bl#104, 105, 107, 112, 113, 124 and 125) ii) $93k is carried over for procuring of BD Universal Viral Transport Standard Kit, 50/pk, cat#220221 (bl#106. All carried over amounts are expected to be completed before end of Jun 2021."

## Slide 7: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (3)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
6. Health Products - Equipment (HPE) | $958,755 | $315,826 | $642,929 | 32.9% | similar as above, most of balance relates to the Covid 19 health commodities and products procurements and those include $474k - financial obligation is reported (bl#109, 119, 122& 123) and $155.k is for activities carried over (bl#120) and new budget line for Xpert Xpress SARS-CoV-2 cartridges (moved from pending procurement that was initially budgeted/Covid flexibility budget under TB grant)
7.Procurement and Supply-Chain Management costs (PSM) | $511,722 | $138,643 | $373,079 | 27.1% | Of the balance, $100k financial obligation for ongoing procurement of Covid health products (bl#108) and $45.5k carried over for Covid health products as well (pending from 2020 and just start procuring in 2021)

## Slide 8: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (4)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
8.Infrastructure (INF) | $0 | $0 | $0 | N/A | 
9.Non-health equipment (NHP) | $6,737 | $5,024 | $1,713 | 74.6% | 
10. Communication Material and Publications (CMP) | $94,206 | $5,111 | $89,095 | 5.4% | Of the balance, $89k is carried over for the IEC material development of radio messages and printing pamphlets; work with village chiefs to disseminate messages budgeted under Covid module (bl#126)

## Slide 9: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Cost grouping (5)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
11. Indirect and Overhead Costs | $254,979 | $130,757 | $124,222 | 51.3% | "- Expenditure of this line includes PSI program income expenditure (management cost relates to the condom social marketing) = $54.1k. If excluded this PSI PI expenditure, the grant expenditure for this line will be only $76.6k;- Actual balance without PSI's is $178.3k. Of this balance, $132.7k is carried over for the Covid activities (bl#110 & 130); and $30k is carried over for the PR staff extension during grant "
12. Living support to client/ target population (LSCTP) | $85,626 | $92,213 | -$6,587 | 107.7% | CHAS did more activities of Lab test of OI diagnosis (bl#01), a negative balance will be reduced or less than 105% comparing to the budget in the cumulative implementation period.
13. Payment for Results | $7,424 | $6,052 | $1,373 | 81.5% | not major balance
Grand Total | $4,936,217 | $3,092,611 | $1,843,606 | 62.7% | 

## Slide 10: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (1)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
1.Comprehensive prevention programs for sex workers and their clients/Behavioral intervention for sex workers | $236,621 | $265,421 | -$28,800 | 112.2% | "The negative balance includes : CHAS: -$24.3k - budget adjustment for overspending on IBBS survey among FSW (bl#79); and CHAS: -$6k - conducted more activities on Lab test for OI diagnosis."
2.Comprehensive prevention programs for MSM/HIV testing services for MSM | $15,806 | $17,633 | -$1,827 | 111.6% | Small negative balance is from LaoPHA overspending on Referral of MSM/TGs to HTC - Travel cost to refer target group for HIV testing in KM and VTP (bl# 03)
3.Program management/Grant management | $541,429 | $451,959 | $89,470 | 83.5% | "The balance includes :i) $9.6k- financial obligation for audit fee 2020;ii) $48.8k - approved grant closure budget for some staff extension during grant close out period Jan-Jun 2021;ii) remaining $31k -saving from overbidding for audit fee (error in the budget revision) and gain on different exchange rate."
4.Program management/ other Program management Intervention | $13,157 | $67,048 | -$53,891 | 509.6% | There is a negative balance because the expenditure covers PSI program income expenditure for condom social marketing =$54.1k. It moved out this amount, the actual expenditure vs this line is only $12.9k. Completed.

## Slide 11: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (2)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
5.Comprehensive prevention programs for MSM/Diagnostic and treatment of STIs and other sexual health services for MSM | $1,054 | $318 | $736 | 30.2% | LaoPHA: under spending in the current reporting period. Saving
6.Treatment, care and support/Counselling and psychosocial support | $43,377 | $46,119 | -$2,742 | 106.3% | small negative balance is from LaoPHA bl# 19, 38 and 39
7.Treatment, care and support/Prevention, diagnosis and treatment of opportunistic infections | $79,015 | $65,082 | $13,933 | 82.4% | The balance relates to DRD procurement (bl#30), which is not full payment has been completed comparing to the signed PQ.
8.Treatment, care and support/HIV Care | $21,400 | $17,580 | $3,821 | 82.1% | CHAS: small balance from underspending for in con

## Slide 12: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (3)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
9.Program management / Policy, Planning, coordination and management of national Program | $18,711 | $18,943 | -$232 | 101.2% | 
10. Comprehensive prevention programs for MSM/other | $53,640 | $52,490 | $1,151 | 97.9% | 
11. Comprehensive prevention programs for sex workers and their clients/HIV testing services for sex workers | $40,469 | $38,400 | $2,069 | 94.9% | 
12.Comprehensive prevention programs for sex workers and their clients/ Addressing stigma, discrimination and violence against sex workers | $18,776 | $18,355 | $421 | 97.8% | 

## Slide 13: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (4)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance 5.
13.Comprehensive prevention programs for sex workers and their clients/ Prevention and management of co-infection and morbidities for sex workers | $1,337 | $89 | $1,248 | 6.6% | PSI: the balance is due to some patients refused to go to ART sites because they live far away from the sites and faced with difficulty on travelling. COVID19 also impacted as the activity was not carried out during the period of lockdown.
14.Comprehensive prevention programs for sex workers and their clients/other interventions for sex worker and their clients | $35,796 | $157,504 | -$121,708 | 440.0% | The expenditure includes PSI PI expenditure as condom procurement for social marketing = $125.8k. If moved out this amount the actual expenditure will be only $31.7k. Small balance of $4k is mainly from the gain on different exchange.
15. Treatment, care and support/Differentiated ART services delivery | $1,394,173 | $1,170,919 | $223,254 | 84.0% | CHAS: Relates to the ARV procurement which is completed. The balance is due to over budgeting for PSM costs $210k (bl#21)

## Slide 14: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (5)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | AbsorptionRate | Reasons for Variance
16. HIV Testing Services/Differentiated HIV testing services | $361,535 | $315,826 | $45,709 | 87.4% | CHAS: it's mainly from underspending for Viral Load testing ,EID testing, MDR testing $42k (bl# 29)
17. Comprehensive prevention programs for sex workers and their clients/Diagnosis and treatment of STIs and other productive health services for sex workers | $807 | $151 | $656 | 18.7% | small balance
18. TB/HIV/Key populations(TB/HIV)-others | $1,964 | $2,270 | -$305 | 115.5% | small negative balance from PSI (bl#56)
19. Comprehensive prevention programs for MSM/behavioral interventions for MSM | $113,453 | $141,241 | -$27,788 | 124.5% | the expenditure includes approved budget adjustment for National survey (IBBS among MSM) bl#80.

## Slide 15: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Module intervention (6)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | AbsorptionRate | Reasons for Variance
20. COVID-19/Risk mitigations for disease program | $1,123,631 | $240,153 | $883,478 | 21.4% | "The balance includes 4472.5k - financial obligations for Covid 19 health commodities and products procurement (bl#104, 105, 107, 108, 109, 123 &124); $324k carried over for Covid 19 activities and lab reagent (bl# 106, 108, 110, 111, 115,120); estimated savings from this line = $87k are from lower cost of local procuring for Covid 19 health commodities and products."
21. COVID-19/COVID 19 Control and containment including health system strengthening | $820,065 | $5,111 | $814,955 | 0.6% | includes $391.7 - financial obligations for Covid 19 health product procurements and $392k is carried over for Covid activities and pending procurement.
Grand Total | $4,936,217 | $3,092,611 | $1,843,606 | 62.7% | 

## Slide 16: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (1)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
CHAS | $3,247,234 | $2,344,783 | $902,451 | 72.2% | "The balance includes as follows:i) $184.9 - finance obligation relates to the Covid 19 health commodities, products and equipment which are now under process (bl#104,105; 107 and 109);ii) $446.4k - carried over for Covid activities $436.6k (bl#106, 110, 111, 114, 116, 117, 118, 129, 126 & 130) and approved grant closure budget for some staff extension Jan-Mar 2021 = $9.7k;iii) the balance/estimated saving of$271.1k- That is mainly from under spending for Viral Load testing EID, testing, MDR testing; over budgeting for PSM cost of ARV drugs; and lower costs of local procuring for Covid 19 health commodities, products and equipment."
PSI | $110,796 | $279,788 | -$168,993 | 252.5% | "The negative balance is due to PSI expenditure covers program income expenditure (condom procurement and condom social marketing) in amount of $180k reported in the current reporting period. It moved out this amount, total PSM expenditures vs budget of a year will be only $99.8k. However, PSI will need to report in the final grant close out report the actual expenditure vs approved budget for grant closure activities ($3.1k)"

## Slide 17: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (2)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
PEDA | $105,533 | $98,418 | $7,114 | 93.3% | "The balance is mainly from underspending of peer educators' transportation and communications (bl#93 & 94, actual payment is made based on PE's performance) and some savings are from gain on different exchange rate. As per approved grant closure budget, $2.9k is carried over for some staff extension from Jan-Mar to prepare the closeout of the grant. "
LAOPHA | $253,752 | $203,418 | $50,334 | 80.2% | Balance includes mainly two Covid activities carried over in amount of $52k.
Ministry of Health of the Lao People's Democratic Republic | $575,051 | $166,203 | $408,847 | 28.9% | "The balance includes: i) $199k - financial obligations for ongoing Covid health commodities and product procurement $1,889.4k (bl#108, 112, 113) ; for 2020 audit fee $9.6k (bl#16);ii) $175.1 k - carried over for Xpert Xpress SARS-CoV-2 cartridges and PSM costs (new item pending procurement moved from TB Covid flexibility budget as per GF recommendation) = $145.1k and approved grant closure budget for some PMU staff extension during grant closure preparation Jan-Jun 2021 =$30k (bl#101).if added up both financial obligations and Covid activities carried over, then the total expenditure will reach 94%."

## Slide 18: Budget vs Expenditure for the Reporting Period Jan-Dec 2020_ By Implementing Entity (3)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate | Reasons for Variance
CMPE | $156,000 | $0 | $156,000 | 0.0% | It relates to the Covid budget as ongoing procurement of Malaria RDTs @$0.50 x 200,000 tests (bl#124) and 20,000 Malaria LLINs through Wambo.
NTC | $487,852 | $0 | $487,852 | 0.0% | "Of the balance, - $350.3k (bl#119, 122 &123) are reported as financial obligations including prepayment made to Cepheid for 5 Gene Xpert machines $87.5k (bl#123); - $82.1k carried over for Covid activities and - $55.3k savings identified from lower costs of some Covid health products and equipment comparing to the initial budget."
Grand Total | $4,936,217 | $3,092,611 | $1,843,606 | 62.7% | 

## Slide 19: Budget vs Expenditure for the cumulative Period 1 Jan 2018-31 Dec 2020_ By Cost grouping (1)
 | Cumulative Budget | Cumulative Actual Expenditures | Budget Vs Actual Variances | Absorption Rate
1. Human Resources | $1,182,387 | $1,145,441 | $36,946 | 96.9%
2.Travel related costs (TRC) | $1,270,307 | $1,142,382 | $127,925 | 89.9%
3.External Professional services (EPS) | $211,761 | $175,689 | $36,072 | 83.0%
4. Health Products - Pharmaceutical Products (HPPP | $2,172,018 | $2,151,819 | $20,199 | 99.1%
5. Health Products - Non-Pharmaceuticals (HPNP) | $682,734 | $517,075 | $165,658 | 75.7%
6. Health Products - Equipment (HPE) | $1,557,445 | $914,516 | $642,929 | 58.7%
7.Procurement and Supply-Chain Management costs (PSM) | $716,264 | $343,186 | $373,079 | 47.9%

## Slide 20: Budget vs Expenditure for the cumulative Period 1 Jan 2018-31 Dec 2020_ By Cost grouping (2)
 | Budget for Reporting Period | Actual Expenditures | Budget Vs Actual Variances | Absorption Rate
8.Infrastructure (INF) | $0 | $0 | $0 | N/A
9.Non-health equipment (NHP) | $18,471 | $16,758 | $1,713 | 90.7%
10. Communication Material and Publications (CMP) | $94,206 | $5,111 | $89,095 | 5.4%
11. Indirect and Overhead Costs | $424,709 | $391,364 | $33,345 | 92.1%
12. Living support to client/ target population (LSCTP) | $275,856 | $282,443 | -$6,587 | 102.4%
13. Payment for Results | $21,150 | $19,778 | $1,373 | 93.5%
Grand Total | $8,627,308 | $7,105,562 | $1,521,746 | 82.4%

## Slide 21: Budget vs Expenditure for the Cumulative Period 1 Jan 2018-31 Dec 2020_ By Module intervention (1)
 | Cumulative Budget | Cumulative Actual Expenditures | Budget Vs Actual Variances | Absorption Rate
1.Comprehensive prevention programs for sex workers and their clients/Behavioral intervention for sex workers | $438,111 | $466,911 | -$28,800 | 106.6%
2.Comprehensive prevention programs for MSM/HIV testing services for MSM | $48,910 | $50,737 | -$1,827 | 103.7%
3.Program management/Grant management | $1,475,818 | $1,386,348 | $89,470 | 93.9%
4.Program management/ other Program management Intervention | $40,548 | $185,316 | -$144,768 | 457.0%
5.Comprehensive prevention programs for MSM/Diagnostic and treatment of STIs and other sexual health services for MSM | $1,269 | $533 | $736 | 42.0%
6.Treatment, care and support/Counselling and psychosocial support | $134,885 | $137,627 | -$2,742 | 102.0%

## Slide 22: Budget vs Expenditure for the Cumulative Period 1 Jan 2018-31 Dec 2020_ By Module intervention (2)
 | Cumulative Budget | Cumulative Actual Expenditures | Budget Vs Actual Variances | Absorption Rate
7.Treatment, care and support/Prevention, diagnosis and treatment of opportunistic infections | $267,926 | $253,992 | $13,933 | 94.8%
8.Treatment, care and support/HIV Care | $55,260 | $51,439 | $3,821 | 93.1%
9.Program management / Policy, Planning, coordination and management of national Program | $125,481 | $125,713 | -$232 | 100.2%
10. Comprehensive prevention programs for MSM/other interventions for MSM | $165,043 | $163,892 | $1,151 | 99.3%
11. Comprehensive prevention programs for sex workers and their clients/HIV testing services for sex workers | $119,255 | $117,185 | $2,069 | 98.3%
12.Comprehensive prevention programs for sex workers and their clients/ Addressing stigma, discrimination and violence against sex workers | $59,926 | $59,504 | $421 | 99.3%

## Slide 23: Budget vs Expenditure for the Cumulative Period 1 Jan 2018-31 Dec 2020_ By Module intervention (3)
 | Cumulative Budget | Cumulative Actual Expenditures | Budget Vs Actual Variances | Absorption Rate
13.Comprehensive prevention programs for sex workers and their clients/ Prevention and management of co-infection and morbidities for sex workers | $1,550 | $302 | $1,248 | 19.5%
14.Comprehensive prevention programs for sex workers and their clients/other interventions for sex worker and their clients | $102,750 | $455,441 | -$352,691 | 443.2%
15. Treatment, care and support/Differentiated ART services delivery | $2,566,530 | $2,343,276 | $223,254 | 91.3%
16. HIV Testing Services/Differentiated HIV testing services | $960,225 | $914,516 | $45,709 | 95.2%
17. Comprehensive prevention programs for sex workers and their clients/Diagnosis and treatment of STIs and other productive health services for sex workers | $1,592 | $936 | $656 | 58.8%

## Slide 24: Budget vs Expenditure for the Cumulative Period 1 Jan 2018-31 Dec 2020_ By Module intervention (5)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
18. TB/HIV/Key populations(TB/HIV)-others | $5,083 | $5,388 | -$305 | 106.0%
19. Comprehensive prevention programs for MSM/behavioral interventions for MSM | $113,453 | $141,241 | -$27,788 | 124.5%
20. COVID-19/Risk mitigations for disease program | $1,123,631 | $240,153 | $883,478 | 21.4%
21. COVID-19/COVID 19 Control and containment including health system strengthening | $820,065 | $5,111 | $814,955 | 0.6%
Grand Total | $8,627,308 | $7,105,562 | $1,521,746 | 82.4%

## Slide 25: Budget vs Expenditure for the Cumulative Period 1Jan 208- 31Dec 2020_ By Implementing Entity (1)
 | Cumulative Budget | Cumulative Actual Expenditures | Cumulative Budget Vs Actual Variances | Absorption Rate
CHAS | $5,760,740 | $4,858,289 | $902,451 | 84.3%
PSI | $334,795 | $825,647 | -$490,852 | 246.6%
PEDA | $317,992 | $310,878 | $7,114 | 97.8%
LAOPHA | $675,519 | $625,185 | $50,334 | 92.5%
Ministry of Health of the Lao People's Democratic Republic | $894,411 | $485,564 | $408,847 | 54.3%
CMPE | $156,000 | $0 | $156,000 | 0.0%
NTC | $487,852 | $0 | $487,852 | 0.0%
Grand Total | $8,627,308 | $7,105,562 | $1,521,746 | 82.4%

## Slide 26: Budget vs Expenditure for the Cumulative Period 1 Jan 2018- 31 Dec 2020_ By Implementing Entity (1)
 | Cumulative Budget | Cumulative Actual Expenditures | Budget Vs Actual Variances | Absorption Rate
CHAS | $5,760,740 | $4,858,289 | $902,451 | 84.3%
PSI | $334,795 | $825,647 | -$490,852 | 246.6%
PEDA | $317,992 | $310,878 | $7,114 | 97.8%
LAOPHA | $675,519 | $625,185 | $50,334 | 92.5%
Ministry of Health of the Lao People's Democratic Republic | $894,411 | $485,564 | $408,847 | 54.3%
CMPE | $156,000 | $0 | $156,000 | 0.0%
NTC | $487,852 | $0 | $487,852 | 0.0%
Grand Total | $8,627,308 | $7,105,562 | $1,521,746 | 82.4%

## Slide 27: Government Co-financing committed and expended overview (in USD) 2018-2020
27
2018 |  | 2019 |  | 2020 |  | Comments
Committed | expended | Committed | expended | Committed | expended | 
462,033 | 553,499 | 473,575 | 1,158,097 | 547,334 | 428,165 | Reference is made to the Executive report with ref. No.0373/MOH dated 25 March 2020 of Government Co-Financing Commitment to the Global Fund supported TB and HIV Programs for the Period of 2018-2020. The Lao Government commitment for co-financing was USD 462,033 for 2018, USD 473,575 for 2019 and USD 547,334 for 2020, in total USD 1,482,942. For 2018, the allocated amount by Lao PDR Government was utilized for different HIV activities such as planning and holding annual meetings, field monitoring and supervision, development of IEC materials, and condom promotion activities. The total expenditures for the HIV activities in the reporting period of 2018 were USD 553,499. For 2019, the allocated and expended amount by the Lao PDR Government for HIV activities was USD 492,710. Thus, the cumulative expenditures by the government for the period of 2018-2019 were USD 1,046,209. Additionally, there was a specific financial investment in 2019 for ARV and RDTs procurement from national resources, amounted to USD 111,888. The actual payment was made in Feb 2020. Hence, the total expenditure is USD 1,158,097 For 2020, the allocated amount by the Government was USD 663,318, actual expenditures incurred in current reporting period was $428,165 and the remaining of USD 235,154 the financial obligations for ongoing local procurement for OI and STI drugs= USD 103,445 and for the ARV direct procurement through Wambo = USD 131,709. these actual payments were made in Feb 2021. The total cumulative expenditures from 1/2018-12/2020 (including obligation paid in Feb 2021) is USD 1,709,528 or reaching 115% comparing to the initial committed amount.

## Slide 28: LAO PDR GF Disease Grant Risk Management_ update 2020
Major risks to HIV Grant |  |  | 
Risks | Risk management actions_ March 2017 | Status 2019 | Status 2020
1. Hidden high-risk populations not being reached for VCT and services | Revise strategy to reach hidden high-risk populations, including community testing/treatment monitoring. Include in new funding application 2018-2020 | Two methods of EPM (Enhanced Peer Mobilization) and snowballing are planned to be compared by a TA supported from GF. Furthermore, there are some discussions at the country level to have some revisions to service provision to MSMs based on the findings from recent IBBS. In collaboration with UNAIDS, funds are mobilized to conduct trainings for peers working in MSMs, FSWs and PWIDs projects in 5 GF implementing provinces. | The activities have been continued under the GF support for MSM in 2 provinces and Linkages support 3 provinces . PEDA with 5 PCCAs implemented the outreach activities and HIV testing FSW in 5 provinces. It is going on.

## Slide 29: LAO PDR GF Disease Grant Risk Management_ update 2020
Major risks to HIV Grant |  |  | 
Risks | Risk management actions_ March 2017 | Status 2019 | Status 2020
2.Limited data on people who inject drugs PWID | Research on PWID – include in new funding application | There is a plan to conduct an IBBS among PWIDs by the end of 2019. The fund is included in catalytic fund and the PR (AFAO) is in the process of getting approval from Ministry of Foreign Affairs for working in Lao PDR. As soon as catalytic funds gets available planning for next steps including getting approval from ethic committee will be started. This should be noted that as per these different steps the implementation of this IBBS might have some delays | the Catalytic Fund/GF - AFAO or SKPA Program in collaboration with French 5% and CHAS have discussed and completed the PWID Rapid Assessment and planned to conduct the study and field data collection in April-May 2021. 2020 is the year for preparation with the funding support from GF with the amount of 125,000 USD and French 5% 117,000 Euro.

## Slide 30: LAO PDR GF Disease Grant Risk Management_ update 2020
Major risks to HIV Grant |  |  | 
Risks | Risk management actions_ March 2017 | Status 2019 | Status 2020
3. No strategy for condom procurement and distribution | Commission condom market research. Include in new funding application Revive and strengthen NCC | The committee has been active and distributed about 1 million condoms in 18 provinces during 2018. This number will be increased to 1.5 and 2 million in 2019 and 2020 respectively. The committee also had some concerns about the quality of the condoms. FDD was assigned to assess the quality of the all condoms in the market. The review revealed that just “Number One” condom, imported by PSI, can meet the quality standards. NCC requested the authorities to collect and retract all the low quality condoms from the market. In addition, provincial and district health authorities was assigned to have a close monitoring on the condom market and report about the sub-standard condoms. FDD also took relevant measures to create a ban on import for non-compliant sub-standard commercial condoms. | Condom Social Marketing implemented by PSI in close collaboration with CHAS as National AIDS Program ad FDD. It is going on.

## Slide 31: LAO PDR GF Disease Grant Risk Management_ update 2020
Major risks to HIV Grant |  |  | 
Risks | Risk management actions_ March 2017 | Status 2019 | Status 2020
4. Concerns about service quality, including discrimination against KPs by health staff/VCT staff | Refresher training of health staff | There is a project in the country called “Health Queal”. This project uses an electronic version of questionnaire for monitoring the stigma and discrimination situation in the hospitals. All the ARV staff and a randomly chosen of other staff who are in contact with patients fill this questionnaire on a quarterly basis. There are core trainers in 4 hospitals who provide training about stigma and discrimination to all relevant wards. In addition, central experts do field visits quarterly and provide coaching as per the analysis of the collected data about stigma and discrimination. National training materials is also planned to be developed as per the availability of resources from catalytic fund. | Also continuing under the National AIDS Program in collaboration with Health Queal/UCSF, CDC/PEPFAR, GF-SKPA. These activities were implemented at 11 ART sites and some communities where PLWH living. Up to now it is going on.