## Slide 1: RAI2E Jul-Dec 2020 Progress Update RAI3E Jan-Mar 2021 Status
CCM meeting
06 Apr 2021

## Slide 2: Presentation outline
Budget absorption
PR support
Programmatic achievement
Performance targets and results
RAI3E Progress
Challenges
Notes: Desk reviews

## Slide 3
Budget absorption

## Slide 4: Budget Absorption RAI2E 2018 – 2020 (duration of the grant) - By Module
Chart: Budget absorption by Modules (2018-2020)
| Case management | COVID-19 | Program management | RSSH: HMIS and M&E | RSSH: National health strategies | RSSH: PSM | Vector control | Grand Total
Budget absorption | 0.98669 | 0.94064 | 0.98951 | 0.96868 | 0.99449 | 0.96573 | 0.99932 | 0.98541
3.5M
400K
2.7M
1.2M
1.3M
350K
1.4M
11M

## Slide 5: Budget Absorption RAI2E 2018 – 2020 (duration of the grant) - by Cost Grouping
Chart: Budget absorption by Cost Grouping (2018-2020)
| 1.0 HR | 2.0 TRC | 3.0 EPS | 4.0 HPPP | 5.0 HPNP | 6.0 HPE | 7.0 PSM | 8.0 INF | 9.0 NHP | 10.0 CMP | 11.0 Overhead | Grand Total
Burn rate | 0.98359 | 0.97495 | 0.99683 | 0.92815 | 1.0042 | 1.1956 | 0.95108 | 1 | 1.0313 | 0.99115 | 0.96585 | 0.98541
2M
3.7M
1.5M
133K
2M
19K
374K
6K
391K
91K
576K
11M
HR: Human Resources
TRC: Travel Related Cost
EPS: External Professional Services
HPPP: Health Products – Pharmaceutical Products
HPNP: Health Products – Non-Pharmaceuticals
HPE: Health Products – Equipment
PSM: Procurement & Supply Chain Management costs
INF: Infrastructure
NHP: Non-health equipment
CMP: Communication and Pulibcations

## Slide 6: Budget Absorption RAI2E 2018 – 2020 (duration of the grant) - by Implementer
CMPE: Center for Malaria Parasitology and Entomology
HPA: Health Poverty Actoin
CHias: Community Health and Inclusion Association
PEDA: Population Education and Development Association
PMU-MOH: Project Management Unit – MOH
WHO: World Health Organization
Chart: Budget absorption by Implementers (2018-2020)
| CMPE | HPA | CHias | PEDA | PMU-MOH | WHO | Grand Total
Burn rate | 0.98751 | 0.97365 | 0.99002 | 0.98772 | 0.94803 | 0.99437 | 0.98541
6.7M
845K
653K
629K
577K
1.6K
11M

## Slide 7
Performance targets and results

## Slide 8: 21 indicators were reported for Jul-Dec 2020 PUDR.
4 impact indicators
6 outcome indicators
11 coverage indicators
1. API
2. # active foci
3. TPR
4. Inpatient malaria death
1. % slept under ITN previous night
2. % HH with 1 ITN/2 people
3. % existing ITN used previous night
4. ABER
5. % of MMP slept under ITN
6. % of MMP with fever who accessed malaria diagnosis
1. # LLINs - continuous
2. # testing – public
3. # testing – community
4. # testing – private
5. % treated – public
6. % treated – community
7. % treated - private
8. % no stock out
9. % cases investigated and classified
10. % foci investigated and classified
11. % timely reporting

## Slide 9: Impact indicators for 2020: targets and results
Chart: 
| Annual Parasite Incidence | Malaria test positivity rate
Target | 1.1539 | 1.72
Result | 0.4881 | 0.6112
Chart: 
| # active foci | Inpatient malaria deaths
Target | 4 | 0
Result | 27 | 0

## Slide 10: Outcome indicators for 2020: targets and results (1/2)
Chart: 
| % of population that slept under ITN previous night | % of HH with 1 ITN/2 people | % of existing ITN used previous night
Target | 0.9 | 1 | 0.95
Result | 0.7 | 0.44 | 0.89
Chart: 
| % of MMP that used ITN last time they slept in transmission area | % of MMP with fever in past 3 months that accessed malaria testing
Target | 0.8 | 0.95
Result | 0.91 | 0.81
HH = Household
ITN = Insecticide Treated Nets
MMP = Mobile Migrant Population

## Slide 11: Outcome indicators for 2020: targets and results (2/2)
Chart: 
| Annual Blood Examination Rate
Target | 0.128
Result | 0.195

## Slide 12: Coverage indicators Jul-Dec 2020: achievement % (1/2)
Chart: 
| # LLINs distributed for continuous distribution | # Tested in public sector | # Tested in community | # Tested in private sector
Achievement % | 0.83568 | 1.0457 | 1.2 | 1.2
Achievement % higher than 120% are cut off at 120%.
LLINs distribution is against the whole year’s target.

## Slide 13: Coverage indicators Jul-Dec 2020: achievement % (2/2)
Chart: 
| % Treated in public sector | % Treated in community | % Treated in private sector | % no stock out | % cases investigated and classified | % foci investigated | % on time reporting
Achievement % | 1 | 0.99 | 0.98 | 0.83158 | 0.8 | 0.52083 | 1.0211

## Slide 14: Contribution by sectors to whole country's testing and positive cases (Jul-Dec 2020)
Chart: Contribution by sectors to whole country's testing and positive cases (Jul-Dec 2020)
| Testing | Positive
Public sector | 0.59 | 0.55
Community | 0.29 | 0.39
Private sector | 0.12 | 0.06

## Slide 15
Programmatic achievement

## Slide 16: Key programmatic achievements Jul-Dec 2020 (1/3)
314,405 malaria tests for malaria suspected cases
77,935 LLINs distributed to MMPs, militaries and pregnant women.
2,423 malaria treatment for malaria positive cases
139 case investigation conducted
10 foci investigated and responded

## Slide 17: Key programmatic achievements Jul-Dec 2020 (2/3)
ICCM trainings for 18 provinces, 148 districts, > 1,000 health centers & ~ 1,800 VMWs
Surveillance trainings for 18 provinces & 148 districts
DHIS2 trainings for 18 provinces & 148 districts
Trainings
Meetings
RAI3E grant making
FTAT review
Bottom-up planning with all 18 provinces and 148 districts
Quarterly reviews and annual review
TWGs (Technical Working Groups)

## Slide 18: Key programmatic achievements Jul-Dec 2020 (3/3)
LLINs survey for LLINs coverage assessment after 2019 mass distribution campaigns
MMPs survey
Surveys
Others
Pv radical cure in all health centers
Active case detections and outbreak responses
Routine supervision to different levels
Recruitment of new VMWs for RAI3E

## Slide 19
PR support

## Slide 20: PR support to SRs (1/3)
Training on Prevention of Sexual Exploitation and Abuse for all CSOs
Financial compliance and reporting trainings for all provincial staff
Training on bottom-up planning for CMPE staff
Capacity building
Program management
Support to CMPE for bottom-up planning SOP development
Support to CMPE for bottom-up planning with all 18 provinces and 148 districts for Q4-2020
Quarterly review meetings with all SRs
Day to day program management support

## Slide 21: PR support to SRs (2/3)
Reprogramming to identify savings for COVID support and procurement of additional RDTs to avoid stockout
Grant Making for RAI3E: grant documents for RAI3E 2021 – 2023 approved by Global Fund in Q4 2020
RAI2E grant closure for all SRs
Grant management
Procurement & supply chain
Procurement of PPEs for COVID funded by reinvested RAI2 savings
Procurement of LLINs, RDTs and ACTs
Supply chain support: improvement of supply chain for VMWs

## Slide 22: PR support to SRs (3/3)
Financial management
Periodic expenditure verification with all SRs
Financial supportive supervision visits
Monitoring & Evaluation
Supportive supervision visits for data quality and program quality
Data quality desk reviews at all SRs

## Slide 23
RAI3E Status

## Slide 24: RAI3E (2021-2023) status (1/2)
Agreement signing
Project Cooperation Agreement UNOPS – MOH : signed
Grant Agreements signed : CMPE, CHIas, HPA, PEDA, MPSC, DPC – HMIS, WHO
Disbursement
Disbursement for Q1 from Bank of Lao MoH account to Sub Recipients:
  Completed on February 26th for CMPE, CHIas, PEDA, HPA;
  Completed on March 22nd for MPSC, DPC-HMIS;
Disbursement for Q2 is in progress from PR to BoL MOH account;

## Slide 25: RAI3E (2021-2023) status (2/2)
Implementation readiness
Induction Workshop with all SRs: completed on March 9th;
Bottom – up planning for Q1+Q2 workplans: completed for all 18 provinces and 148 districts ;
News VMWs for RAI3E: recruitment completed in Dec-2020;
Purchase Orders for key health products are issued, most of the products to be delivered in Q1 and Q2;
Procurement for LLINs for 2022 distribution – in progress, ETA Q4 2021;
Co Financing
Budget request for 2021 has been submitted from CMPE and is in progress of being approved at MoH;

## Slide 26: Government co-financing: 1.48 Million USD for 3 years
Activity | Amount in USD |  |  |  | Comments
 | 2021 | 2022 | 2023 | TOTAL | 
TOTAL | 643,836 | 516,251 | 288,123 | 1,448,210 | 
Procurement and PSM costs of RDTs for malaria diagnosis | - | 281,435 | 151,542 | 432,978 | * 880,000 qty of malaria RDTs to be procured in 2022 and 2023
Procurement and PSM costs of bednets | 462,670 | - | - | 462,670 | * 217,788 qty of LLINs to be procured for mass distribution
LLIN-mass distribution microplanning meetings at central level with targeted provinces (5 southern provinces) | 2,717 | - | - | 2,717 | * LLINs microplanning at the central with 5 southern provinces * 2 days meeting in Q4-2021 to prepare for LLINs mass distribution that will happen in Q1-2022
LLIN-mass distribution microplanning meetings at provincial level with targeted districts (5 southern provinces) | 4,968 | - | - | 4,968 | * 1 meeting in each province of 5 southern provinces * 1 person from each district (total 42 districts) * 2 days meeting in Q4-2021 to plan for the LLINs mass distribution that will happen in Q1-2022

## Slide 27: Government co-financing: 1.48 Million USD for 3 years
Activity | Amount in USD |  |  |  | Comments
 | 2021 | 2022 | 2023 | TOTAL | 
Annual Review and Planning Meeting with provinces | 19,288 | 19,288 | 19,288 | 57,864 | * 1 time per year; 3 days meeting;
Elimination certification preparation meeting/training for all districts in elimination provinces | 15,134 | 15,134 | - | 30,267 | * elimination certification meetings/trainings will be done for all the districts in the 13 central and northern provinces (106 districts)
Dissemination meeting for updated microscopy IQA guideline | 6,327 | - | 6,327 | 12,655 | * Dissemination of microscopy IQA guideline in 2021 and 2023
Microscopy training for PAMs, provincial hospital and district hospital laboratory staff | - | 59,885 | - | 59,885 | * 125 elimination district hospitals, 18 PAMS and provincial hospitals, 26 army hospitals, 10 police hospitals, 8 central hospitals, 1 university (Total: 188 sites) will be trained.

## Slide 28: Government co-financing: 1.48 Million USD for 3 years
Activity | Amount in USD |  |  | 
 | 2021 | 2022 | 2023 | TOTAL
Training of PAMS and DAMN on LMIS SOP | - | 32,594 | - | 32,594
Update training materials for PPM providers, and print | 3,050 | - | 3,050 | 6,100
Conduct training of trainers for PPM facilities with CMPE, PAMS and DAMS | 36,285 | 36,285 | 36,285 | 108,856
Conduct refresher training of providers in PPM network | 55,922 | 55,922 | 55,922 | 167,767
Translate and Print Job Aids for PPMs | 449 | - | - | 449
Conduct meeting with all the PPMs and FDD in elimination area to transition | 37,025 | - | - | 37,025

## Slide 29
RAI3E Challenges

## Slide 30: Possible Challenges
Government procurement of LLINs using co-financing amount - for mass distribution in 2022: timely approval of the budget and procurement process for WHO prequalified products;
New process for funds disbursement from MOH bank account at the Bank of Laos (change from BCEL);
Closeout of RAI2 – Outstanding responses for verifications of reported expenditures for FOCI investigations (expenditures not matching the DHIS2 reports, potential ineligible for $2,948);
Recurrent Malaria outbreaks in Attapeu and Sekong provinces;

## Slide 31: Possible Challenges
Government procurement of LLINs using co-financing amount - for mass distribution in 2022: timely approval of the budget and procurement process for WHO prequalified products;
New process for funds disbursement from MOH bank account at the Bank of Laos (change from BCEL);
Closeout of RAI2 – Outstanding responses for verifications of reported expenditures for FOCI investigations (expenditures not matching the DHIS2 reports, potential ineligible for $2,948);
Recurrent Malaria outbreaks in Attapeu and Sekong provinces;

## Slide 32: CMPE Priorities and Challenges
Priority Areas | Challenges
Program Management | Sustained engagement with provinces in weekly meetings; Timely fund availability at the sub-national level for foci & outbreak response;
Case Management | New RACD strategy; TES recruitment, most cases are in remote areas; Referral and compliance monitoring of Pv cases; Improving testing rate, i.e all fever cases are not being tested currently;
Vector Control | LLINs should be WHO prequalified; LLIHNs limited qty to cover forest goers; Limited HR resources & capacity for vector surveillance;

## Slide 33: CMPE Priorities and Challenges – Cont.
Priority Areas | Challenges
Surveillance & Response | Sub-national capacity in surveillance & response; Timeliness & quality of outbreak response;
Malaria Elimination | Technical capacity of HC & DAM for 1-3-7 implementation; Seasonal access issues; PHOEC & NCLE linkages & knowledge transfer (malaria emergency response plan)
Pf elimination | Planning, budgeting, approval and procurement – time sensitive To be able to start the Pf elimination accelerator strategies by Jan 2022;

## Slide 34: Khop Chai Lai Lai