## Workplan
Annual Performance Report of Lao CCM Work Plan from 1 January - 31 December 2021
Section 1. Fixed Costs and HR
No. | Source of Funds | Area of Responsibility | Cost Grouping | Descrition | Timeline/ No. Activity (Plan/implemented) | Budget received (USD) | Expenditure (USD) | Variance (USD) | Expenditure rate (%) | Status/Comment
1 | CCM Funding Agreement | Operations | Human resources | CCM Secretariat Staff | Monthly | 25800 | 21500 | 4300 | 83.3333 | Regular monthly reports are available
2 | CCM Funding Agreement | Operations | Indirect and Overhead costs | Other office-running costs (electricity, telephone, gas,..) | Monthly | 9707 | 6525.21 | 3181.79 | 67.2217 | Regular monthly reports are available
3 | CCM Funding Agreement | Operations | Communication Material and Publications | Printed material | Monthly | 2325 | 1240 | 1085 | 53.3333 | Regular monthly reports are available
4 | CCM Evolution | Oversight | Human resources | Oversight / Transition Officer (TA) | Monthly | 48000 | 8000 | 40000 | 16.6667 | Regular monthly reports are available. Additional Budget (CCM Evolution) was approved from the GF to cover the TA cost started from 1 July 2021 to 30 June 2023.
5 | COVID19RM | Engagement | Human resources | Engagement and Coordination Officer | Monthly | 15000 | 6500 | 8500 | 43.3333 | Regular monthly reports are available
Sub-Total Budget for Activities 1 | [5 empty] | 100832 | 43765.21 | 57066.79 | 43.4041
Section 2. Activities
No. | Source of Funds | Area of Responsibility | Cost Grouping | Description/Activities | Timeline/ No. Activity (Plan/Implemented) | Budget received (USD) | Expenditure (USD) | Variance (USD) | Expenditure rate (%) | Status/Comment
1 | CCM Funding Agreement | Oversight | Travel related Costs | Site visit 1 (Short distance) | 1/0 | 2423 | 0 | 2423 | 0 | No oversight field visit is conducted as planned this year (2 visits will be conducted) due to country lockdown restriction resulting from the nationwide spreading of COVID-19 at the communities.
| CCM Funding Agreement | Oversight | Travel related Costs | Site visit 2 (Long distance) | 1/0 | 3382 | 0 | 3382 | 0 | See above answer.
2 | CCM Funding Agreement | Oversight | Travel related Costs | Oversight Committee meetings | 4/4 | 281 | 140 | 141 | 49.8221 | Four OC meetings were organized for this fiscal year (including joint meetings with ExCom and RMC) according to the agenda and requirements. The variance amount is due to the joint meeting with shared costs.
| CCM Funding Agreement | Operations | Travel related Costs | CCM General Assemblies (Half-day CCM meeting at MOH) | 2/2 | 2389 | 2247.45 | 141.55 | 94.0749 | Two half-day CCM Meetings were organized at MOH as planned for this fiscal year. The variance amount is due to some members being unable to attend the meetings.
3 | CCM Funding Agreement | Operations | Travel related Costs | CCM General Assemblies (Half-day CCM meeting at Hotel) | 1/1 | 2394 | 1855 | 539 | 77.4854 | One half-day CCM Meetings was organized at the hotel as planned for this fiscal year. The variance amount is due to some members being unable to attend the meetings.
| CCM Funding Agreement | Operations | Travel related Costs | CCM General Assemblies (Full-day CCM meeting at Hotel) | 1 | 3898 | 0 | 3898 | 0
4 | CCM Funding Agreement | Operations | Travel related Costs | CCM General Assemblies (Ad-hoc CCM meetingl) | 2 | 4788 | 0 | 4788 | 0 | No ad-hoc CCM meeting is organized ths fiscal year.
5 | CCM Funding Agreement | Operations | Travel related Costs | Other Workshops, Meetings and Trainings (Resource Mobilization Committee - RMC meeting) | 4/2 | 281 | 20 | 261 | 7.1174 | Two RMC meetings were organized for this fiscal year (including joint meetings with ExCom and OC) according to the agenda and requirements. The variance amount is due to the joint meeting with shared costs.
6 | CCM Funding Agreement | Operations | Communication Material and Publications | CCM Website development & maintenance | Monlhly | 3772 | 3171.6 | 600.4 | 84.0827 | CCM website and CCM contact lists on the GF Partner Portal have been managed and updated regularly when required.
7 | CCM Funding Agreement | Operations | Travel related Costs | CCM Executive Committee meetings | 4/3 | 3104 | 690 | 2414 | 22.2294 | Three ExCom meetings were organized for this fiscal year (including joint meetings with OC and RMC) according to the agenda and requirements. The variance amount is due to the joint meeting with shared costs.
8 | CCM Funding Agreement | Engagement | Travel related Costs | Regular consultation meetings with CCM constituencies (CSO Coordinating Committee meeting) | 4/0 | 2800 | 0 | 2800 | 0 | The CSO received additional budget from the other sources to implement their activities. No meeting of the CSO Coordinating Committee was convened this year.
9 | CCM Funding Agreement | Oversight | External Professional Services | Local Consultant (on-site support) | 6/6 | 12000 | 12000 | 0 | 100 | Regular monthly reports are available. The CCM Funding Agreement was approved from the GF to cover the TA cost started from 1 January 2021 to 30 June 2021.
10 | CCM Evolution | Positioning | External Professional Services | Local consultant to Support CCM Positioning (maping national health governance bodies and platforms and developing positioning plan) |  | 10000 | 7500 | 2500 | 75 | The local Consultant to Support CCM Positioning has been recruited in July 2021 based on the Global Fund guideline. The Consultant has completed 2 deliverable outputs, e.g. maping existing national health governance bodies and platforms and developing positioning pathway plan
11 | CCM Evolution | Positioning | External Professional Services | Local Consultant to train civil society (pre- and post- General Assemblies) |  | 4800 |  | 4800 | 0 | No activity is conducted. CCM can update this activity costs by submitting the revised budget and request for no objection from the Global Fund.
12 | CCM Evolution | Engagement | External Professional Services | Implementation of CCM Secretariat Performance Management |  |  |  | 0 |  | In progress by using the Global Fund provided guidance notes on performance management
13 | CCM Evolution | Operations | Travel related Costs | Onsite support to coordinate CCM constituency elections |  |  |  | 0 |  | No activity is conducted. CCM can update this activity costs by submitting the revised budget and request for no objection from the Global Fund.
14 | COVID19RM | Engagement | External Professional Services | Consultation meetings with Civil Society |  | 2500 |  | 2500 | 0 | No activity is conducted. CCM can update this activity costs by submitting the revised budget and request for no objection from the Global Fund.
15 | COVID19RM | Engagement | Travel related Costs | Consultation meetings with National Response Coordination (including government and international partners) |  | 1500 |  | 1500 | 0 | No activity is conducted. CCM can update this activity costs by submitting the revised budget and request for no objection from the Global Fund.
Sub-Total Budget for Activities 2 | [5 empty] | 60312 | 27624.05 | 32687.95 | 45.8019
Grand Total Budget | [5 empty] | 161144 | 71389.26 | 89754.74 | 44.3015

## Timeline
Activities Timeline from 1 January - 31 December 2021
No. | Description/Activities | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | CCM Secretariat Staff
2 | Other office-running costs (electricity, telephone, gas,..)
3 | Printed material
4 | Oversight / Transition Officer (TA)
5 | Engagement and Coordination Officer
6 | Site visit 1 (Short distance) | bar: May
7 | Site visit 2 (Long distance) | bar: Nov
8 | Oversight Committee meetings | bar: Mar; Jun; Sep; Dec
9 | CCM General Assemblies (Half-day CCM meeting at MOH) | bar: Mar; Jun
10 | CCM General Assemblies (Half-day CCM meeting at Hotel) | bar: Sep
11 | CCM General Assemblies (Full-day CCM meeting at Hotel) | bar: Dec
12 | CCM General Assemblies (Ad-hoc CCM meetingl)
13 | Other Workshops, Meetings and Trainings (Resource Mobilization Committee - RMC meeting) | bar: Mar; Jun; Sep; Dec
14 | CCM Website development & maintenance
15 | CCM Executive Committee meetings | bar: Mar; Jun; Sep; Dec
16 | Regular consultation meetings with CCM constituencies (CSO Coordinating Committee meeting) | bar: Mar; Jun; Sep; Dec
17 | Local Consultant (on-site support) | bar: Jan to Jun
18 | Local consultant to Support CCM Positioning (maping national health governance bodies and platforms and developing positioning plan) | bar: Jul to Dec
20 | Local Consultant to train civil society (pre- and post- General Assemblies)
21 | Implementation of CCM Secretariat Performance Management
22 | Onsite support to coordinate CCM constituency elections
23 | Consultation meetings with Civil Society
24 | Consultation meetings with National Response Coordination (including government and international partners)