## Slide 1: Progress update and action plan (including COVID-19 mitigation) to achieve Y2
DLI-J: NTC

## Slide 2: Y2 implementation progress
DLI-J | Y2 (Jun 2021 to May 2022) |  | 
 | Target June 2021-May 2022 | Preliminary Result Jun.-Nov. 2021 | % of target for the reported period
TB notification # | 7,537 TB cases notified for the period of Jun/21-May 2022 for the whole country | 2,574 TB cases notified during the period of Jun-Nov 2021 (source TB tracker DHIS2) | 68%
Xpert coverage % | 100% for the period of Jun/21-May 2022 for the whole country | 99% in 2021 (source: aggregated quarterly report in DHIS2 Q1-Q3 2021) | 99%

## Slide 3: DLI J Condition1:Provinces that achieved the targeted number of notified TB cases of all forms
No. | Provinces | Baseline | 2021 |  |  |  |  |  |  | 2022 |  |  |  |  | Total | Target | Progress | % of target for the reported period
 |  |  | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |  |  |  | 
1 | 01 Vientiane Capital | 1,524 | 93 | 102 | 128 | 84 | 49 | 8 |  |  |  |  |  |  | 464 | 990 | 46% | 94%
2 | 02 Phongsali | 189 | 7 | 10 | 11 | 11 | 5 | 1 |  |  |  |  |  |  | 45 | 203 | 22% | 44%
3 | 03 Louangnamtha | 219 | 20 | 14 | 17 | 21 | 14 | 1 |  |  |  |  |  |  | 87 | 201 | 43% | 87%
4 | 04 Oudomxai | 334 | 31 | 23 | 29 | 24 | 30 | 1 |  |  |  |  |  |  | 138 | 365 | 37% | 76%
5 | 05 Bokeo | 169 | 5 | 15 | 19 | 13 | 4 | 1 |  |  |  |  |  |  | 57 | 202 | 28% | 56%
6 | 06 Louangphabang | 379 | 22 | 23 | 83 | 11 | 7 | 1 |  |  |  |  |  |  | 147 | 509 | 28% | 58%
7 | 07 Houaphan | 277 | 12 | 50 | 3 | 7 | 2 | 1 |  |  |  |  |  |  | 75 | 358 | 20% | 42%
8 | 08 Xainyabouli | 216 | 16 | 21 | 14 | 15 | 8 |  |  |  |  |  |  |  | 74 | 420 | 17% | 35%
9 | 09 Xiangkhouang | 84 | 1 | 3 | 4 | 3 | 4 |  |  |  |  |  |  |  | 15 | 224 | 6% | 13%
10 | 10 Vientiane | 439 | 15 | 15 | 197 | 19 | 8 | 2 |  |  |  |  |  |  | 256 | 566 | 45% | 90%
11 | 11 Bolikhamxai | 194 | 11 | 56 | 26 | 14 | 8 | 3 |  |  |  |  |  |  | 118 | 325 | 36% | 73%
12 | 12 Khammouan | 577 | 45 | 110 | 28 | 9 | 18 | 8 |  |  |  |  |  |  | 218 | 457 | 47% | 95%
13 | 13 Savannakhet | 1,190 | 50 | 37 | 37 | 45 | 21 | 57 |  |  |  |  |  |  | 247 | 1,116 | 22% | 44%
14 | 14 Salavan | 497 | 27 | 77 | 92 | 25 | 15 | 11 |  |  |  |  |  |  | 247 | 447 | 55% | 111%
15 | 15 Xekong | 209 | 4 | 2 | 8 | 5 | 7 |  |  |  |  |  |  |  | 26 | 126 | 20% | 41%
16 | 16 Champasak | 954 | 76 | 61 | 60 | 64 | 40 | 21 |  |  |  |  |  |  | 322 | 810 | 39% | 80%
17 | 17 Attapu | 94 | 5 | 9 |  | 4 |  |  |  |  |  |  |  |  | 18 | 159 | 11% | 23%
18 | 18 Xaisomboun | 18 |  | 1 | 1 | 17 | 1 |  |  |  |  |  |  |  | 20 | 60 | 33% | 67%
Total |  | 7,565 | 440 | 629 | 757 | 391 | 241 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 2,574 | 7,537 | 34% | 68%

## Slide 4
DLI J condition 2:Provinces which have achieved an increase of twenty (20) percentage points over the previous year; or reached or maintained one hundred percent (100%) GeneXpert coverage |  |  |  |  |  |  |  |  |  |  |  |  |  | 
No | Provinces | Baseline | 2021 |  |  |  |  |  |  |  |  | Tatal |  | 
 |  |  | Q1 (Jan – Mar) |  |  | Q2 (Apr – Jun) |  |  | Q3 (Jul – Sep) |  |  |  |  | 
 |  |  | No. of Xpert Test | No. of TT of SC | % | No. of Xpert Test | No. of TT of SC | % | No. of Xpert Test | No. of TT of SC | % | No. of Xpert Test | No. of TT of SC | %
1 | 01 Vientiane Cap | 92% | 2818 | 2819 | 100% | 1832 | 1861 | 98% | 2478 | 2505 | 99% | 7128 | 7185 | 99%
2 | 02 Phongsaly | 70% | 142 | 142 | 100% | 217 | 217 | 100% | 146 | 146 | 100% | 505 | 505 | 100%
3 | 03 Louangnamtha | 77% | 528 | 528 | 100% | 252 | 254 | 99% | 309 | 311 | 99% | 1089 | 1093 | 100%
4 | 04 Oudomxai | 33% | 608 | 608 | 100% | 260 | 260 | 100% | 469 | 469 | 100% | 1337 | 1337 | 100%
5 | 05 Bokeo | 49% | 199 | 199 | 100% | 39 | 44 | 89% | 233 | 233 | 100% | 471 | 476 | 99%
6 | 06 Louangphabang | 65% | 454 | 454 | 100% | 346 | 367 | 94% | 552 | 558 | 99% | 1352 | 1379 | 98%
7 | 07 Houaphan | 75% | 306 | 306 | 100% | 312 | 312 | 100% | 463 | 463 | 100% | 1081 | 1081 | 100%
8 | 08 Xainyabouli | 71% | 479 | 517 | 93% | 351 | 351 | 100% | 391 | 391 | 100% | 1221 | 1259 | 97%
9 | 09 Xiangkhouang | 83% | 344 | 351 | 98% | 107 | 107 | 100% | 230 | 235 | 98% | 681 | 693 | 98%
10 | 10 Vientiane Pro | 79% | 476 | 488 | 98% | 358 | 359 | 100% | 808 | 819 | 99% | 1642 | 1666 | 99%
11 | 11 Bolikhamxai | 68% | 209 | 224 | 93% | 192 | 201 | 96% | 486 | 486 | 100% | 887 | 911 | 97%
12 | 12 Khammouan | 72% | 668 | 668 | 100% | 531 | 536 | 99% | 741 | 741 | 100% | 1940 | 1945 | 100%
13 | 13 Savannakhet | 60% | 913 | 913 | 100% | 667 | 668 | 100% | 927 | 927 | 100% | 2507 | 2508 | 100%
14 | 14 Salavan | 56% | 1574 | 1576 | 100% | 333 | 334 | 100% | 592 | 593 | 100% | 2499 | 2503 | 100%
15 | 15 Sekong | 81% | 267 | 275 | 97% | 100 | 156 | 64% | 82 | 91 | 90% | 449 | 522 | 86%
16 | 16 Champasak | 95% | 1069 | 1069 | 100% | 803 | 803 | 100% | 1039 | 1039 | 100% | 2911 | 2911 | 100%
17 | 17 Attapue | 73% | 193 | 193 | 100% | 100 | 100 | 100% | 85 | 85 | 100% | 378 | 378 | 100%
18 | 18 Xaisomboun | 72% | 90 | 100 | 90% | 17 | 32 | 53% | 63 | 86 | 73% | 170 | 218 | 78%
Total |  | 74% | 11337 | 11430 | 99% | 6817 | 6962 | 98% | 10094 | 10178 | 99% | 28248 | 28570 | 99%

## Slide 5: Mitigation plan to achieve Y2 target
CHALLENGES
Drop in TB notification is due to:
  Drop in sending sputum specimen to Xpert testing
  Limited access of the patient to health facility.
  Limitation of activities due to COVID19 lockdown.
  Implementation at BMU not well functioned due to Covid situation.
  Limitation and re-tasking of human resource at all levels, particularly district hospital.
  Many activities were not implemented including active case-finding.
ActionS taken
NTC is continuing monitoring and coaching the implementation at all levels, using real time surveillance from DHIS2 TB Tracker and GeneXpert laboratories monthly reports.
Conducting quarterly video meeting in provinces to follow-up catch up plans from and districts level as well.
Reviewing plan of ACF and Supervision.
Restarting ACF at all levels as soon as possible.
Adapting activities for following the COVID-19 task force guidance such as wearing mask, avoiding crowding, social distancing.

## Slide 6: TB patient tracker and report on DHIS2
CHALLENGES
Delay to data entry
Data quality improvement
Action taken
Conducting weekly video meeting to follow up by coaching and exchange via WA group with implementing sites.
On site supervision visit provinces and districts where there is no Covid outbreak.
Set-up plan for retraining by tele-conference or social media discussion.

## Slide 7: GF and Co-financing budget for TB and HIV
 | YEAR 1 |  | YEAR 2 |  | YEAR 3 | 
 | Sum of GF Y1 cash | Sum of GoL Y1 cash | Sum of GF Y2 cash | Sum of GoL Y2 cash | Sum of GF Y3 cash | Sum of GoL Y3 cash
CHAS | 1,550,309.26 | 182,655.67 | 694,342.87 | 687,554.13 | 520,133.76 | 881,918.96
NTC | 748,341.56 | 247,588.00 | 660,756.42 | 461,493.45 | 533,346.23 | 646,519.13
Grand Total | 2,298,650.82 | 430,243.67 | 1,355,099.29 | 1,149,047.58 | 1,053,479.99 | 1,528,438.09

## Slide 8: Global Fund and Co-financing budget
 | YEAR 1 |  | YEAR 2 |  | YEAR 2 | 
 | Sum of GF Y1 cash | Sum of GoL Y1 cash | Sum of GF Y2 cash | Sum of GoL Y2 cash | Sum of GF Y3 cash | Sum of GoL Y3 cash
4.2 Anti-tuberculosis medicines | 227,792.26 | - | 217,460.43 | 213,568.20 | 236,402.57 | 232,952.57
5.6 Laboratory reagents | 17,771.40 | - | 270.00 | 22,092.80 | 20.00 | 22,342.80
5.8 Other consumables | 109,424.60 | - | - | 94,610.60 | - | 94,610.60
6.3 Microscopes | 10,000.00 | - | - | - | - | -
6.4 TB Molecular Test equipment | 344,030.00 | 228,700.00 | 401,555.00 | 102,155.00 | 259,340.00 | 259,340.00
6.6 Other health equipment | - | 9,000.00 | - | - | - | -
7.2 Freight and insurance costs (Health products) | 36,323.30 | 6,888.00 | 38,470.99 | 26,066.85 | 34,583.66 | 34,273.16
7.5 Quality assurance and quality control costs (QA/QC) | 3,000.00 | 3,000.00 | 3,000.00 | 3,000.00 | 3,000.00 | 3,000.00
Grand Total | 748,341.56 | 247,588.00 | 660,756.42 | 461,493.45 | 533,346.23 | 646,519.13

## Slide 9: Global Fund and Co-financing budget
 | YEAR 1 |  | YEAR 2 |  | YEAR 3 | 
 | Sum of GF Y1 cash | Sum of GoL Y1 cash | Sum of GF Y2 cash | Sum of GF Y3 cash | Sum of GoL Y3 cash | Sum of GoL Y3 cash
4.2 Anti-tuberculosis medicines | 227,792.26 | - | 217,460.43 | 213,568.20 | 236,402.57 | 232,952.57
5.6 Laboratory reagents | 17,771.40 | - | 270.00 | 22,092.80 | 20.00 | 22,342.80
5.8 Other consumables | 109,424.60 | - | - | 94,610.60 | - | 94,610.60
6.3 Microscopes | 10,000.00 | - | - | - | - | -
6.4 TB Molecular Test equipment | 344,030.00 | 228,700.00 | 401,555.00 | 102,155.00 | 259,340.00 | 259,340.00
6.6 Other health equipment | - | 9,000.00 | - | - | - | -
7.2 Freight and insurance costs (Health products) | 36,323.30 | 6,888.00 | 38,470.99 | 26,066.85 | 34,583.66 | 34,273.16
7.5 Quality assurance and quality control costs (QA/QC) | 3,000.00 | 3,000.00 | 3,000.00 | 3,000.00 | 3,000.00 | 3,000.00
Grand Total | 748,341.56 | 247,588.00 | 660,756.42 | 461,493.45 | 533,346.23 | 646,519.13

## Slide 10: TB Procurement 2022
NTC has submitted to PR (DPC, NPCO) the 2022 full needs for TB drugs (US$ 500k) and TB laboratory US$ 650k including GeneXpert tests
NTC requested quotation to Global Drug Facility for TB drugs order 2022 with expected amount $500,000
Product | Cost
Total TB drugs Order (FLDs + SLDs) | $ 385,289.43
PSM costs of TB drugs 30% | $ 105,821.80
TB laboratory consumables and reagents | $ 115,586.83
GeneXpert needs | $ 464,980.00
PSM costs of laboratory 25% | $ 116,245.00
Grant Total | $ 1,187,923.06
Ceiling budget from GF Y2 + Y3 | $ 1,194,102.65

## Slide 11
Thank you