## Slide 1: Lao CCM positioning Pathway Plan 2021-2030
CCM meeting
9th Dec 2021

## Slide 2: Outline presentation
What
Why
What for
When & How
Where are & What next
Conclusion

## Slide 3: What
The Lao CCM positioning is an incorporation of the current CCM structure in to the national health body-Sector wise coordination for health (SWC).

## Slide 4: Why
Base on Global Fund Guideline and CCM Policy - encourage country to:
  Position CCM with in existing health platform
  Engage DPs/CSO in CCM positioning
  Ensure Investment in 3 ATM programs
  develop the CCM positioning pathway
Base on the direction of the national health sector
  Simply the national structure
  Align government & DPs coordination with in the existing platform
  Not create a parallel structure with the existing platform

## Slide 5: What for
The objective of the CCM Positioning is to sustain effective coordination of CCM & GFATM program in health programs and investment.

## Slide 6
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
When & How: Three Process framework
CCM endorsemene
Knowledge Coordination Sustainable Structure
Map National Collect and analyse data Position CCM functions
Coordinating jointly in shared dialogue within a national body
platforms Select option
Define option
2021
2022
2030
2023

## Slide 7
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
How: Knowledge Process Framework
CCM endorsemene
Knowledge Coordination Sustainable Structure
Map National Collect and analyse data Position CCM functions
Coordinating jointly in shared dialogue within a national body
platforms Select the option
Define options
2021
2022
2030
2023

## Slide 8: Knowledge Process (cont)
Desk Review the GFATM Guidelines, CCM
Lao documents, Lao documents on AIDs
Effectiveness
Review 17 existing health committees
Define indicators
Scoring
Analyze

## Slide 9: Review 17 existing health structure / committees
No | Name of committees | Dated issued | Number
1 | Country Coordinating Mechanism (CCM) | 2002 | 
2 | Health Sector Wise Coordination (SWC), Health Sector Reform and Samsang Committee | Aug 17 | N1828/MoH
3 | Health and Nutrition Service Access (HANSA) committee | May 20 | N0969/MoH
4 | Technical Committee for Prevention Control Response & Case management (PCRC) on Covid 19 | Apr 20 | N0797/MoH
5 | Natural Disaster Prevent & Control Committee | Aug 13 | N1868/MoH
6 | Covid 19 Vaccine Committee | Oct 20 | N2521/MoH
7 | Single Door Coordination Investment Committee | Jul 20 | N1260/MoH
8 | Procurement Bidding Committee | Jan 17 | N0150/MoH
9 | Advancement Women Committee in health sector (AWC) | Nov 17 | N2609/MoH
10 | Responsible person and coordination committee for Non-Communicable Diseases (NCD) | Feb 14 | N474/MoH
11 | Human Trafficking Committee Sec | Nov 17 | N2603/MoH
12 | National Committee on HIV/AIDS | Nov 17 | N2603/PM
13 | National Task force Covid-19 | Jun 21 | N59/PM
14 | Secretariat of the Covid-19 National Task Force | Feb 20 | N02/PM
15 | National Committee on Advancement for women (NCAW) | Jun 17 | N47/PM
16 | National Committee on Nutrition (NCN) | Jul 14 | N93/PM
17 | Steering Committee for EU budget Support Nutrition STCEUBS) | Dec 18 | vice PM

## Slide 10
High Level Round Table Meeting
Covid -19 National Task force
Diseases specific committees*
NCAW
Procurement & bidding committee
SDC Investment committee
Human trafficking control Sec committee
Disaster prevention-control committee
HANSA committee
Health SWC
Prime Ministry
CCM
Ministry of Health
High level Multisectoral coordination
Govern-DPs coordination
Health sectoral coordination
Health sector-DPs coordination
NCN
STC EU BS
Mapping Existing Structures & CCM Positioning in Lao P.D.R in 2021
Formal linkage
Informal linkage for
communication and collaboration
CCM: Country Coordinating Mechanism, TF Sec Covid Task force Secretariat, HANSA: Health and Nutrition Services Access committee, NCAW: National Committee on Advancement for Women, NCN: National committee on nutrition, SDC: Single Door Coordination on investment committee, SWC: Sector Wise Coordination health reform & Samsang committee, STCEUBSN: Steering committee EU budget support for nutrition, * Non communicable disease, HIV/AIDS, technical committee on Covid-19, Covid 19 vaccine committees
Sec TF
NCAW

## Slide 11: Other Findings
Though Most of center of coordination of the existing structure located in Cabinet like CCM Sec
Too many coordinating donor platforms
Too many national bodies
Too many health programs coordination mechanism
Less function of some committees and its secretariat
Out of date of few committees

## Slide 12: Propose 4 options of CCM positioning
Option 1: Positioning CCM in Health SWC, Health Reform Samsang structure
Option 2: Positioning CCM in HANSA structure
Option 3: Positioning CCM in Technical Committee for PCRCM Covid-19
Option 4: Positioning CCM in Disaster Prevent & Control Committee

## Slide 13
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
Submit the proposal
Next Round GF funding
2021 2022 2023 2024…………………………… 2030 Year
Knowledge Coordination Transitional phase Sustainable Structure End ATM
Map National Collect and analyse data Position CCM functions Position CCM functions End GF Funded
Coordinating jointly in shared dialogue on within a national body within a national body
platforms selection for CCM positioning
Define option in health sector-wise coordination committee
Summary of Knowledge
CCM endorsement
Define 4 optional structures

## Slide 14
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
How: Coordination Process framework
CCM endorsemene
Knowledge Coordination Sustainable Structure
Map National Collect and analyse data Position CCM functions
Coordinating jointly in shared dialogue within a national body
platforms Select option
Define option
2021
2022
2030
2023

## Slide 15: Coordination Process
The Lao Positioning CCM in to Health SWC, Health Reform Samsang structure is selected through coordinating platform: Consultative meetings with a leader of ministry of health, ExCom, OC, RMC, ATM national programs and CCM sec
The selection is based on Majority agreement
and based on rational to the Lao context.

## Slide 16
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
Submit the proposal
Next Round GF funding
2021 2022 2023 2024…………………………… 2030 Year
Knowledge Coordination Transitional phase Sustainable Structure End ATM
Map National Collect and analyse data Position CCM functions Position CCM functions End GF Funded
Coordinating jointly in shared dialogue on within a national body within a national body
platforms selection for CCM positioning
Define option in health sector-wise coordination committee
Summary Coordination
CCM endorsement
Selected SWC for CCM positioning

## Slide 17
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
How: Sustainable Structure Process framework
CCM endorsemene
Knowledge Coordination Sustainable Structure
Map National Collect and analyse data Position CCM functions
Coordinating jointly in shared dialogue within a national body
platforms Select option
Define option
2021
2022
2030
2023

## Slide 18: Five Steps/stairs in Sustainable Structure
The sustainable structure requires a couple steps
1st step: the development of the Lao CCM positioning pathway plan and its timeline (Done)
2nd step: the revision of structure of the new Lao CCM Position in SWC (Done)
3rd step: the revision of SWC – CCM TOR (on going Jan 22)
4th step: the transitional phase (on going)
5th step: CCM full function in the new SWC structure
Notes: with in health SWC, aligned CCM in health program coordination and set up a single health sector DPs coordinating platform and building capacity of health SWC and CCM together in order to sustain effective coordination of health programs and investment.

## Slide 19
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
Development CCM positioning pathway
Update SWC CCM TOR
Incorporating CCM works stepwise in SWC
Submit the proposal
Next Round GF funding
2021 2022 2023 2024…………………………… 2030 Year
Knowledge Coordination Transitional phase Sustainable Structure End ATM
Map National Collect and analyse data Position CCM functions Position CCM functions End GF Funded
Coordinating jointly in shared dialogue on within a national body within a national body
platforms selection for CCM positioning
Define option in health sector-wise coordination committee
Stairs in Sustainable structure
CCM endorsement
Update CCM Structure
Transitional phase
CCM position in SWC

## Slide 20
Secretariat for SWG
CCM SEC
Sector Working Group (Policy level)
Chair: Minister , Co Chair Ambassadors Advisors
MOH Steering Committee
Minister, Vice Minister, DG, DDG
CCM
Health Planning & Financing TWG
High Level Round Table Meeting
MOH Steering Committee
Minister, Vice Minister, DG, DDG
Health Policy Dialogue (2 meeting/Y)
TB Sub TWG
Sector Working Group (Operational level)
Chair: Vice-Minister,
CCM
Human resources for Health TWG
Food & Drug TWG
Health Care TWG
Hygiene Health Promotion TWG
Communicable disease TWG
Oversight Committee
Health Strategy & Coordination (4 meetings/Y)
Technical Consultation Discussion & Recommendation
( >4 meetings/year)
HV Sub TWG
M Sub TWG
Sub TWG
Sub TWG
Sub TWG
ExCom
Structure of Positioning CCM in Health SWC Platform
Sub TWG
Sub TWG
Sub TWG

## Slide 21
Update CCM Structure
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CSO CCM
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update SWC CCM TOR
Incorporating CCM works stepwise in SWC
Submit the proposal
Next Round GF funding
2021 2022 2023 2024…………………………… 2030 Year
Knowledge Coordination Transitional phase Sustainable Structure End ATM
Map National Collect and analyse data to preparedness Position CCM functions Position CCM functions End GF Funded
Coordinating jointly in shared dialogue on within a national body within a national body
platforms selection for CCM positioning
Define option in health sector-wise coordination committee
Transitional Phase
CCM endorsement
Transitional phase to be preparedness

## Slide 22: 4th steps in Transitional Phase
MOH and SWC restructuring within 2021
Capacity building of CSO, population affected network
Building capacity of SWC and CCM
Set up a single health sector donor coordinating platform
Incorporating CCM works and coordination into SWC programs

## Slide 23
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CCM CSO population affected
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
Submit the proposal
Next Round GF funding
2021 2022 2023 2024…………………………… 2030 Year
Knowledge Coordination Transitional phase Sustainable Structure End ATM
Map National Collect and analyse data to preparedness Position CCM functions Position CCM functions End GF Funded
Coordinating jointly in shared dialogue on within a national body within a national body
platforms selection for CCM positioning
Define option in health sector-wise coordination committee
Optimal periods of the transitional phase
CCM endorsement

## Slide 24: Incorporating CCM works and coordination into SWC programs step by step: Main activities
Transferring the CCM structure, shifting CCM functions and principles with in the health SWC, aligned CCM in health program coordination.
Enlightening both CCM and SW: CCM members take part in the SWC policy levels meeting; CCM issues brought in to SWC policy level agenda;
Familiarizing GFATM program and GF financial cycle in SWC operational
Initiating OC in TWG of SWC: OC meeting and function under umbrella of SWC for health platform
Taking CCM GFATM works acquainted with in SWC platform

## Slide 25
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative meeting ExCom OC RMC TWG CCM Sec
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CCM CSO population affected
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM Structure & TOR
Incorporating CCM works stepwise in SWC
Submit the proposal
Next Round GF funding
2021 2022 2023 2024…………………………… 2030 Year
Knowledge Coordination Transitional phase Sustainable Structure End ATM
Map National Collect and analyse data Position CCM functions Position CCM functions End GF Funded
Coordinating jointly in shared dialogue on within a national body within a national body
platforms selection for CCM positioning
Define option in health sector-wise coordination committee
Whole Time frame
CCM endorsement

## Slide 26: VII. Where we are & what next

## Slide 27
Review existing national structure
Consultative meeting ExCom OC RMC TWG CCM Sec
Consultative Meeting Minister of Health
Consultative joint meeting
CCM endorsement
Consult with GF& GF Approval
MOH restructured
Capacity building SWC & CCM CSO population affected
Set up a single H-Donor platform
CCM position in SWC
Development CCM positioning pathway
Update CCM TOR
Incorporating CCM works stepwise in SWC
Submit the proposal
Next Round GF funding
2021 2022 2023 2024…………………………… 2030 Year
Knowledge Coordination Transitional phase Sustainable Structure End ATM
Map National Collect and analyse data Position CCM functions Position CCM functions End GF Funded
Coordinating jointly in shared dialogue on within a national body within a national body
platforms selection for CCM positioning
Define option in health sector-wise coordination committee
CCM endorsement
We are here
Here the next
Update CCM Structure

## Slide 28: In conclusion
Successful of the pathway of Lao CCM positioning in SWC for Health is that the end of the pathway shall be achieved a multisectoral partnership coordination improved, effectiveness and realization of ATM - health investment and GFATM grant oversight monitoring improved.
Successful of transferring and shifting CCM structure and function to SWC-in Health shall be in a short or a long term - influenced by :
  Commitment of policy makers, CCM & technical officer
  Preparedness and readiness of both SWC and CCM
  Calendar of the Global fund ending

## Slide 29: Thank You Very Much