## Slide 1
ສູນຄວບຄຸມວັນນະໂລກ
National TB Control Center (NTC)
The HANSA Project – DLI-J
The Global Fund COVID-19 Response Mechanism (C19RM), LAO-C-MOH

## Slide 2: The DLI-J Achievement
Chart: TB Notified cases
| Year 1 | Year 2
Target | 7565 | 7537
Achieved | 6052 | 4506
Column1
From now to May 31

## Slide 3: The DLI-J Achievement

## Slide 4
Budget by Module - Intervention | Year 1 | Year 2 | Year 3 | Total Budget | %
COVID 19- COVID Diagnostics and testing | 95.277 | 123.856 | 106.856 | 325.989 | 23,33%
COVID19-Case management, clinical operations and therapeutics | 290.300 | 00 | 00 | 290.300 | 20,78%
COVID19-Laboratory systems | 8.646 | 00 | 00 | 8.646 | 0,62%
COVID19-Mitigation for TB programs | 263.981 | 180.072 | 180.072 | 624.125 | 44,68%
COVID19-Health products and waste management systems | 66.963 | 00 | 00 | 66.963 | 4,79%
Program management-Grant management | 9.000 | 35.999 | 35.999 | 80.998 | 5,80%
Total | 734.167 | 339.927 | 322.927 | 1.397.021 | 100%
NTC C19RM Budget (LAO-C-MOH 2021 -2023)

## Slide 5: C19RM Activities Status (1 update)
No. | Description | Implementer | Budget 2021-2022 (USD) | Status of Activities | Expenditure of Q1/2022
1. | Maintaining Specimen transportation from district to provincial GeneXpert laboratories | NTC | 70.919,86 | SOP had been developed and send to implementing sites on 15 February 2022 Will start to conduct in end of March 2022 | 00
2. | Conducting ACF among high-risk group testing for Covid and TB (BASE ALLOC) | NTC | 31.890,92 | NTC is conducting at ODX | 4.863 $
3. | Conducting ACF among high-risk group testing for Covid and TB (ABOVE ALLOC) | NTC | 53.151,53 | NTC will conduct in 2022 | 00
4. | Community outreach for awareness raising among high risk group by 2 CSO organizations. | CSO | 5.873,92 | On going carried out RRDPA has carried out at Hinhub district on 23-26/02/22 , 131 attendees MAP has carried out at Vanvieng district 14-16/03/22 ,82 attendees | 1.956 $
5. | Transportation of DR-TB patients from home to treatment unit and return (BASE ALLOC) | NTC | 23.110,96 | NTC started conduct in SVK for First site | 200 $
6. | Transportation of DR-TB patients from home to treatment unit and return (ABOVE ALLOC) | NTC | 7.969,30 | NTC will conduct in 2022 | 00

## Slide 6: C19RM Activities Status (2 update)
No. | Description | Implementer | Budget 2021-2022 (USD) | Status of Activities | Expenditure of Q1/2022
7. | Scaling-up of GeneXpert connectivity solution 2 days Practice workshop in all 164 TB Units: 10 subnational workshop (in Vientiane and Province) inviting 2 persons by TB unit; (BASE ALLOC) | NTC | 17.621,76 | NTC will conduct in Q2/2022 | 00
8. | Training of the 23 Gene Xpert laboratories on new SOPs and IPC and quality control for TB, COVID, HIV Viral load; 3 labs technicians per laboratory: | NTC | 15.914,54 | NTC will conduct in Q2/2022 | 00
9. | Data quality improvement for laboratories: Training on data management of GeneXpert testing and results | NTC | 13.382,92 | 1 session has been conducted at Bolikhamxai Province including 7 districts of Lab technicians , total 18 participants date 2-4 /02/22 | 3.162 $
10. | C19RM 2020 Roll Over - TB tracker practice workshop in all (164) TB | NTC | 28.761,27 | NTC conducted 2 sessions in HP&XK on Feb 2022 | 6.270 $

## Slide 7: C19RM Procurement Status (1)
No. | Description | Implementer | Budget (USD) | Status
1. | Portable digital X-ray machine set and accessories for outreach TB and Covid screening | NTC | 180.000,00 | Pending NPCO confirmation of payment status by GF
2. | PSM costs (12.5%) Procurement agent and handling fees | NTC | 22.500,00 | Pending NPCO confirmation of payment status by GF
3. | PSM costs (12.5%) Freight and insurance costs (Health products) | NTC | 22.500,00 | Pending NPCO confirmation of payment status by GF
4. | GeneXpert module replacement | NTC | 10.800,00 | Justification request to summit to GF to change supplier from WAMBO to CEPHEID
5. | PSM costs 12.5% for GeneXpert modules | NTC | 1.350,00 | Justification request to summit to GF to change supplier from WAMBO to CEPHEID
6. | GeneXpert Machine (4 modules, laptop, 10 color) | NTC | 58.500,00 | Pending request price quote from WAMBO

## Slide 8: C19RM Procurement Status (2)
No. | Description | Implementer | Budget (USD) | Status
7. | PSM for GXp machines: 12.5% | NTC | 7.312,50 | Pending request price quote from WAMBO
8. | Vortex mixer | NTC | 4.116,00 | Justification request to summit to GF to change supplier from WAMBO to Local
9. | PSM 12.5% for vortex mixer | NTC | 514,50 | Justification request to summit to GF to change supplier from WAMBO to Local
10. | 1 Teleconference set: 10,000 US$ | NTC | 10.000,00 | In the process of evaluation for the bidding documents

## Slide 9: C19RM Procurement Status (Refund)
No. | Description | Implementer | Budget (USD) | Status | Q1/2022
1. | (bl#243 LAO-T-MOH) Civil works for renovation of 2 MDR-TB units (bl#243): 65,000 US$ | NTC | 65.000,00 | Completed | 
2. | (bl#244 LAO-T-MOH) 16 beds for 2 MDR units: 6,524 US$ | NTC | 6.525,00 | Completed | 
3. | (bl#209 LAO-T-MOH) 4 EKG machines: for MDR units | NTC | 5.157,60 | Completed | 
4. | (bl#246 LAO-T-MOH) 1 Autoclave for 1 MDR unit | NTC | 2.800,80 | Completed | 
5. | (bl#237 LAO-T-MOH) 2 Monitors for ICU bed in two new MDR-TB units including PSM costs | NTC | 3.993,81 | Completed | 
6. | (bl#227 from LAO-T-MOH) equipment/computers to support DHIS2: 38 Notebook computers for data entry in TB tracker at district level : 39,267 US$ | NTC | 39.267,00 | Completed | 

## Slide 10: C19RM Procurement Budget under NCLE
No. | Description | Implementer | Budget (USD) | Status
1. | GX C-19 Xpress tests cartridges | NCLE | 180.250,00 | Received goods
2. | PSM costs (12.5%) Procurement agent and handling fees | NCLE | 22.531,25 | Received goods
3. | PSM costs (12.5%) Freight and insurance costs (Health products) | NCLE | 22.531,25 | Received goods
4. | Centrifuge for plasma spin (15 tubes) for GeneXpert laboratory 650US$ x 15 items | NCLE | 9.750,00 | Justification request to summit to GF to change supplier from WAMBO to Local
5. | PSM 12.5% for centrifuge | NCLE | 1.218,75 | Justification request to summit to GF to change supplier from WAMBO to Local
6. | UPS for GeneXpert machine: local procurement including PSM costs | NCLE | 13.140,00 | Justification request to summit to GF to change supplier from WAMBO to Local

## Slide 11: Proposed Issues/Challenges
Not Reach the targets (DLI-J)
Some TB Drugs stock out
  H 100 mg & H 300 mg
  RH for children
  Amecacine 500 mg
  3. Procurement Process delay (C19 RM2 Budget)

## Slide 12: Action Plans for the challenges 1
Issues | Actions Taken
Drop in TB notification: Fund Transfer procedure was delay to implementing sites, included provincial and district level Many activities were not implemented, including active case-finding Less specimens from district to Xpert sites at provincial hospitals Limited access of the patient to health facilities due to lockdown condition, patient could not freely move from home to health facilities Low coverage of X-ray machines especially at district level (20%) | Conducting quarterly video meeting with each province to follow-up funding flow from province to districts and implementation and reporting of activities CDC and implementing sites as provincial and district TB units re-adjust priority plan to mitigate impact by following the COVID-19 task force guidance such as wearing mask, avoiding crowding, social distancing Reviewing plan of ACF and Supervision by restarting ACF at all levels Combining training on IPC and EBS with TB identification and referral at all levels. In order to build the capacity in term of health education to improve the quality of services Integrated with other programs via specific task force at implementing sites On site supervision visit provinces and districts where there is no outbreak.

## Slide 13
ຂອບໃຈ
Thank you