## Slide 1: RAI3E Malaria Update for December 2021 CCM Meeting
25 March 2022

## Slide 2: Presentation outline
Program overall indicators and results - 2021
Other Program Achievements for 2021 and Program Priorities for 2022
Budget vs Expenditures
Co – Financing Requirement
Risk Management
Additional Slides for Reference

## Slide 3: 1. Program overall indicators and results - 2021

## Slide 4: 1. Program overall indicators and results – 2021
Impact indicators
Inpatient malaria deaths
Malaria test positivity rate
API
Reported malaria cases
Outcome indicator
ABER
Coverage indicators
LLINs continuous distribution
# testing in all sectors
% treated in all sectors
% case investigated within 3 days
% foci investigated within 7 days

## Slide 5: 1. Program overall indicators and results – 2021 – Impact Indicators
Impact indicator 4 - Reported malaria cases
Target (Jan-Dec 2021) | Result (Jan-Dec 2021) | Achievement | Grant rating
3,768 | 3,924 | Target not achieved | N/A
Area | All species | Pf & mixed | Pv
Central and North | 149 | 55 | 94
South | 3,775 | 1,310 | 2,465
Country level | 3,924 | 1,365 | 2,559
Species | 2021 | 2020 | % changed
Pf & mixed | 1,365 | 1,605 | -15%
Pv | 2,559 | 1,919 | 33%

## Slide 6: 1. Program overall indicators and results – 2021 – Impact Indicators
Impact indicator 2 - Malaria test positivity rate
Target (Jan-Dec 2021) | Result (Jan-Dec 2021) | Achievement | Grant rating
0.59% | 0.61% | Target not achieved | N/A
Zero positivity rate (No case found)
Phongsaly Luangnamtha Oudomxay Bokeo Huaphanh Xayaboury
Highest positivity rate by province |  |  | 
Province | Positivity Rate 2021 | Positivity rate 2020 | % changed (2021 vs 2020)
Attapeu | 1.67 | 2.06 | -19%
Sekong | 1.15 | 1.33 | -14%
Savannakhet | 0.65 | 0.43 | 51%
Khammouane | 0.56 | 1.04 | -46%
Saravane | 0.51 | 0.35 | 46%
Malaria positivity rate = total positive / total testing

## Slide 7: 1. Program overall indicators and results – 2021 – Impact Indicators
Impact indicator 3 - Annual Parasite Incidence (API)
Target (Jan-Dec 2021) | Result (Jan-Dec 2021) | Achievement | Grant rating
1.596 | 1.308 | Target achieved | N/A
Zero positivity rate (No case found)
Phongsaly Luangnamtha Oudomxay Bokeo Huaphanh Xayaboury
Highest API by province | 
Province | API all species
Attapeu | 12.224
Sekong | 9.304
Saravane | 1.370
Savannakhet | 1.366
Khammouane | 1.158
API = Total positive / Pop at risk
Remark: Cannot compare % changed between 2020 and 2021 as denominator is different (2020: Total pop vs 2021 Pop at risk)

## Slide 8: 1. Program overall indicators and results – 2021 – Impact Indicators
Impact indicator 1 - Inpatient malaria deaths
Death case: Nong district, Savannakhet Province on September 2021
Target (Jan-Dec 2021) | Result (Jan-Dec 2021) | Achievement | Grant rating
0 | 1 | Target not achieved | N/A

## Slide 9: 1. Program overall indicators and results – 2021 – Outcome Indicators
Outcome 1 - Annual blood examination rate (ABER)
Target (Jan-Dec 2021) | Result (Jan-Dec 2021) | Achievement | Grant rating
27.26 | 21.48 | Target not achieved | N/A
5 Highest ABER by province |  |  | 
Province | ABER 2021 | ABER 2020 | % changed
Houaphanh | 184.99 | 151.05 | 22%
Sekong | 80.87 | 78.4 | 3%
Attapeu | 73.25 | 62.46 | 17%
Luang Namtha | 66.27 | 82.1 | -19%
Bokeo | 64.02 | 60.15 | 6%
5 Lowest ABER by province |  |  | 
Province | ABER 2021 | ABER 2020 | % changed
Vientiane. C | 0.67 | 1.02 | -35%
Phongsaly | 7.03 | 11.67 | -40%
Bolikhamxay | 7.51 | 4.92 | 53%
Xaysomboun | 7.99 | 3.98 | 101%
Vientiane. P | 9.13 | 9.97 | -8%
ABER = Total testing*100 / Pop at risk

## Slide 10: 1. Program overall indicators and results – 2021 – Coverage Indicators
Coverage indicator 1 - LLINs continuous distribution
Target (Jan-Dec 2021) | Result (Jan-Dec 2021) | Achievement | Grant rating
99,605 | 38,137 | 38.29% | B2
Type | Distributed Quantity
Pregnant woman | 23,543
Covid19 | 14,594
Total | 38,137
- The nets for MMPs (24,605) and Military (50,000) could not be delivered due to the supplier suspension;
- The distribution of nets for pregnant women (25,000) are slightly below target due to some Covid travel restrictions;

## Slide 11: 1. Program overall indicators and results – 2021 – Coverage Indicators
Coverage indicator 2 - Testing in all sectors
Target (Jul-Dec 2021) | Result (Jul-Dec 2021) | Achievement | Grant rating
353,842 | 369,472 | 104.42% | A1
Area | # Testing (Jul-Dec 21) | % against total
South | 308,138 | 83%
Central and north | 61,334 | 17%
Total | 369,472 | 
Sector | # Testing (Jul-Dec 21) | # Testing (Jul - Dec 20) | % changed
All sectors testing | 369,472 | 314,405 | 18%
Sector name | Target | Result | % achievement
Public sector | 240,614 | 224,047 | 93%
Community sector | 76,540 | 109,312 | 143%
Private sector | 38,926 | 36,113 | 93%
Total – all sectors | 356,080 | 369,472 | 104%

## Slide 12: 1. Program overall indicators and results – 2021 – Coverage Indicators
Coverage indicator 3 - Treatment in all sectors
Target (Jul-Dec 2021) | Result (Jul-Dec 2021) | Achievement | Grant rating
100% | 100% | 100% | A2
Area | # of positive cases | % of total positive cases
Southern provinces | 2,432 | 97%
Central and Northern provinces | 73 | 3%
Total | 2,505 | 
3% increase in positive cases compare to Jul-Dec 2020 (#2,432)
 | Result 2020 (Jul-Dec) | Result 2021 (Jul-Dec) | % change
positivity rate | 0.8% | 0.7% | -11.7%
Pf & mixed % | 50.6% | 27.0% | -46.6%
Pv % | 49.4% | 73.0% | 47.8%

## Slide 13: 1. Program overall indicators and results – 2021 – Coverage Indicators
Coverage indicator 4 - % case investigation within 3 days
Target (Jul-Dec 2021) | Result (Jul-Dec 2021) | Achievement | Grant rating
75% | 85.71% | 114% | A1
Province | Total Positive | # Case Investigation done within 3 days | % Case Investigation done within 3 days
06 Louangphabang | 1 | 1 | 100.00%
09 Xiangkhouang | 1 | 0 | 0.00%
12 Khammouan | 70 | 68 | 97.00%
13 Savannakhet | 11 | 8 | 73.00%
14 Salavan | 1 | 1 | 100.00%
15 Xekong | 1 | 1 | 100.00%
16 Champasak | 19 | 10 | 53.00%
18 Xaisomboun | 1 | 1 | 100.00%
Total | 105 | 90 | 85.71%
86% Result above the target improved from the previous reporting period (Jan - Jun 2021 : result 64%)

## Slide 14: 1. Program overall indicators and results – 2021 – Coverage Indicators
Coverage indicator 5 - % foci investigation within 7 days
Target (Jul-Dec 2021) | Result (Jul-Dec 2021) | Achievement | Grant rating
78% | 72% | 92% | A2
Province | # Indigenous Case | # Foci | # Foci investigated and responded within 7 days | % Foci investigation and responded within 7 days
06 Louangphabang | 1 | 1 | 1 | 100%
12 Khammouan | 64 | 22 | 16 | 73%
13 Savannakhet | 3 | 3 | 3 | 100%
15 Xekong | 1 | 1 | - | 0%
16 Champasak | 1 | 1 | - | 0%
18 Xaisomboun | 1 | 1 | 1 | 100%
Total | 71 | 29 | 21 | 72%
72% improved from the previous reporting period (Jan - Jun 2021 : result 45%), but it is still below the target and requires more improvement;

## Slide 15: 1. Program overall indicators and results
Grant rating: RAI3E Laos Jul-Dec 2021
Indicator | Grant Rating
# LLINs continuous distribution | B2
# Testing in all sectors | A1
% Treatment in all sectors | A2
% case investigation within 3 days | A1
% foci investigation within 7 days | A2
Overall grant rating Jul-Dec 2021 | B1
Reference | 
Rating | % achievement
A1 | > 100%
A2 | 100 - 90%
B1 | 60 - 89%
B2 | 30 - 59%
C | < 30%
Jul-Dec 2020 : Overall grant rating: B1
Jan-Jun 2021: Overall grant rating: B1

## Slide 16: 2. Other Programmatic Achievements 2021 and Priorities for 2022

## Slide 17
Trainings: ICCM, Surveillance and DHIS2
  Completed in the Southern Provinces at all levels (Province, District, HC, VMW) in 2021 as planned, and 80% in the Northern Provinces;
The delayed trainings in the Northern Provinces are in process to be completed in quarter 1 of 2022;
Surveillance
Outbreak responses (67) were conducted in the south;
Weekly SMS reporting in high burden villages & health facilities;
Entomological surveillance ongoing , partially interrupted to Covid19;
2. Other Programmatic Achievements - 2021

## Slide 18
Program Management
Planning meetings with Provinces and Districts were conducted to develop 6 months work plans (mostly online);
Weekly meetings conducted by CMPE with provinces to discuss main technical issues;
Finalized Closeout and Audit Reports for RAI2 (2018-2020);
Grant Agreements were amended to include the additional budget for PF Accelerator activities (USD 515,000);
Pv radical cure – G6PD quantitative roll out
Health centers - south: completed in 2021;
Health centers – north: partially delayed due to Covid 19, planned to be completed in April 2022;
2. Other Programmatic Achievements - 2021 – Cont’d

## Slide 19
Vector control
LLINs mass campaign – 922,100 nets in 43 districts;
LLINs continuous distribution and PF Accelerator – 101,923 nets;
Case management
Improve testing rate in the public sector;
Improve PV Referral cases for the VMW’s managed by CMPE;
Scale up of Pf elimination acceleration activities (Pilot Completed in 2021);
Finalize Re-stratification exercise;
2. Programmatic Priorities - 2022

## Slide 20
Surveillance
Maintain good rates for case investigation and improve rates for FOCI investigation;
Continue and improve the weekly SMS reporting and outbreak alert system in high burden villages and health facilities
2. Programmatic Priorities – 2022 – Cont’d
Program Management
Reprogram the budget savings and submission for GF approval (includes updated procurement forecast and performance framework);
Improve the disbursement process at the Bank of Lao: the average disbursement time is 18 days for the first 5 quarters of the grant (it should be 10 days);

## Slide 21: 3. Budget vs. expenditure

## Slide 22: 4. Budget vs. expenditure Jan – Dec 2021 – Summary by SR
Implementer | Budget 2021 | Expenditures 2021 | Currency Gain/Loss 2021 | Net Savings 2021 | Burn Rate | Note
CMPE | $2,363,265 | $1,645,897 | $242,553 | $474,815 | 80% | Detail on next slide
CHIas | $288,531 | $255,067 | $31,361 | $2,103 | 99% | 
HPA | $366,905 | $302,356 | $47,392 | $17,157 | 95% | 
PEDA | $295,080 | $263,505 | $30,706 | $869 | 100% | 
DCDC | $39,044 | $32,577 | $3,228 | $3,239 | 92% | 
DPC | $87,840 | $63,554 | $6,287 | $17,999 | 80% | Production and Dissemination of Annual Statistical Report delayed to 2022
MPSC | $78,646 | $42,808 | $5,588 | $30,250 | 62% | Purchase computers delayed to 2022, trainings and supervision delayed or done online
WHO | $523,699 | $387,645 |  | $136,054 | 74% | HIS TA Carry Over to 2022
TOTAL | $4,043,010 | $2,993,409 | $367,115 | $682,486 | 83% | 

## Slide 23: 4. Budget vs. expenditure Jan – Dec 2021 – CMPE Detail
Category | Main Source of Budget Balance (2021) | Note
Procurement | $220,797 | $152K – Savings from nets for continuous distribution (not procured) $68K – Savings from other procurement
PF Accelerator Activities | $48,859 | Activities delayed (carry over to 2022)
Other Activities | $203,619 | $60K – Savings from meetings/trainings done online $128K – Delayed ICCM and Surveillance trainings (Carry Over to 2022) $9K – iDES not done $5K – PV Referral not implemented
TOTAL | $473,275 | 

## Slide 24: 4. Budget vs. expenditure Jan – Dec 2021 – Carry Over and Net Savings
Implementer | Net Savings 2021 | Carry over to 2022 | Savings after Carry Over | Note
CMPE | $474,815 | $230,401 | $244,414 | Carry Over to 2022 for delayed ICCM and Surveillance trainings, PF Accelerator Activities, Annual Meeting, other outstanding advances
CHIas | $2,103 | $2,103 | $0 | 
HPA | $17,157 | $15,386 | $1,771 | 
PEDA | $869 |  | $869 | 
DCDC | $3,239 |  | $3,239 | 
DPC | $17,999 | $11,079 | $6,920 | Production and Dissemination of Annual Statistical Report delayed to 2022
MPSC | $30,250 | $12,902 | $17,348 | Purchase computers delayed to 2022, trainings and supervision delayed or done online
WHO | $136,054 | $134,164 | $1,890 | HIS TA Carry Over to 2022
TOTAL | $682,486 | $406,035 | $278,543 | 

## Slide 25: 4. Co – Financing Requirement

## Slide 26: 4. Co – Financing Requirement
The budget is approved for 2022. The request to start the procurement process for RDTs to be delivered in 2022 was submitted by CMPE to the DOF

## Slide 27: 5. Risk Management

## Slide 28: 5. Major Risks and Management Actions
Risk | Management Action
Not meeting the 2023 PF elimination target due to increased PF cases in a few districts in the south | PF Accelerator Elimination activities (TDA, IPTF) to be conducted in high burden districts
Disruption in testing and treatment at the community level due to lack of PPE for Village Malaria Workers, HCs or PPMs | Coordination between CMPE, DCDC, CSOs and Provincial authorities for timely provision of PPEs to all malaria workers
Delays in trainings, meetings and supervision visits due to Covid restrictions | Remote coaching provided continuously by electronic means; Planning meetings conducted online;
Reduced testing rates due to Covid 19 travel restrictions and reduced availability of staff | Testing of all fever cases; Continuous supply of commodities

## Slide 29: 5. Major Risks and Management Actions – Cont’d
Risk | Management Action
Outbreak responses delayed due to the Covid 19 travel restrictions | Districts will lead the outbreak response if provinces cannot travel. HCs will lead the outbreak response if districts cannot travel. VMWs will conduct the RACD if HCs can't travel to villages.
Delays in the disbursement process through MOH account at the Bank of Laos | DCDC and PR UNOPS coordinate closely to DOF and with the National Treasury for improvements of the disbursement process.
Increased travel costs for field activities due to high fuel costs | Reallocation of budget savings through the reprograming evercise.
Delays in the procurement of RDTs budgeted as part of the Co – Financing Requirement | CMPE and DCDC continue to coordinate with DOF for the timely procurement process

## Slide 30: 6. Additional Slides for Reference

## Slide 31: 1b. Program overall indicators and results - 2021

## Slide 32: 1b. Program overall indicators and results
Coverage indicator 2 - Testing in all sectors (All sectors)
Testing by province | Target | Result | % achievement
01 PHO Vientiane. C | 2,573 | 1,374 | 53%
02 PHO Phongsaly | 6,557 | 4,667 | 71%
03 PHO Luangnamtha | 3,975 | 3,715 | 93%
04 PHO Oudomxay | 5,951 | 5,696 | 96%
05 PHO Bokeo | 2,441 | 2,183 | 89%
06 PHO Luangprabang | 9,466 | 6,441 | 68%
07 PHO Huaphanh | 4,134 | 3,660 | 89%
08 PHO Xayabury | 4,279 | 4,159 | 97%
09 PHO Xiengkhuang | 4,742 | 4,823 | 102%
10 PHO Vientiane. P | 9,627 | 6,107 | 63%
11 PHO Borikhamxay | 3,991 | 4,850 | 122%
Testing by province | Target | Result | % achievement
12 PHO Khammuane | 13,241 | 12,391 | 94%
13 PHO Savannakhet | 63,964 | 73,901 | 116%
14 PHO Saravane | 55,654 | 61,785 | 111%
15 PHO Sekong | 27,833 | 40,561 | 146%
16 PHO Champasack | 92,201 | 77,690 | 84%
17 PHO Attapeu | 44,619 | 54,201 | 121%
18 PHO Xaysomboun | 832 | 1,268 | 152%
Total | 356,080 | 369,472 | 104%

## Slide 33: 1b. Program overall indicators and results
Coverage indicator 2 - Testing in all sectors (Public sector)
Testing by province | Target | Result | % achievement
01 PHO Vientiane. C | 2,573 | 1,374 | 53%
02 PHO Phongsaly | 4,434 | 3,242 | 73%
03 PHO Luangnamtha | 2,860 | 2,323 | 81%
04 PHO Oudomxay | 5,876 | 5,601 | 95%
05 PHO Bokeo | 2,441 | 2,183 | 89%
06 PHO Luangprabang | 8,398 | 6,071 | 72%
07 PHO Huaphanh | 4,134 | 3,660 | 89%
08 PHO Xayabury | 3,221 | 3,521 | 109%
09 PHO Xiengkhuang | 4,742 | 4,823 | 102%
10 PHO Vientiane. P | 9,627 | 6,107 | 63%
11 PHO Borikhamxay | 3,991 | 4,850 | 122%
Testing by province | Target | Result | % achievement
12 PHO Khammuane | 11,566 | 10,603 | 92%
13 PHO Savannakhet | 34,259 | 42,314 | 124%
14 PHO Saravane | 28,321 | 27,616 | 98%
15 PHO Sekong | 20,639 | 16,620 | 81%
16 PHO Champasack | 57,290 | 39,805 | 69%
17 PHO Attapeu | 35,485 | 42,104 | 119%
18 PHO Xaysomboun | 757 | 1,230 | 162%
Total | 240,614 | 224,047 | 93%

## Slide 34: 1b. Program overall indicators and results
Coverage indicator 2 - Testing in all sectors (Community sector)
Partner name | # tested | % contribution | # of VMWs | tests/ VMW/ month | % achievement against the target
HPA-CC | 22,748 | 20.8% | 400 | 9 | 155%
PEDA | 27,758 | 25.4% | 400 | 12 | 190%
CHIAs | 22,626 | 20.7% | 400 | 9 | 155%
CMPE | 36,180 | 33.1% | 999 | 6 | 122%
Total | 109,312 | 100% | 2,199 | 8 | 143%

## Slide 35: 1b. Program overall indicators and results
Coverage indicator 2 - Testing in all sectors (Private sector)
Testing by province | Target | Result | % achievement
02 PHO Phongsaly | 348 | 163 | 47%
03 PHO Luangnamtha | 1,115 | 1,392 | 125%
06 PHO Luangprabang | 418 | 58 | 14%
08 PHO Xayabury | 1,058 | 638 | 60%
13 PHO Savannakhet | 11,643 | 8,811 | 76%
14 PHO Saravane | 6,439 | 6,230 | 97%
15 PHO Sekong | 1,852 | 5,364 | 290%
16 PHO Champasack | 12,525 | 10,847 | 87%
17 PHO Attapeu | 3,528 | 2,610 | 74%
Total | 38,926 | 36,113 | 93%
Total reported PPM: 447

## Slide 36: 1b. Program overall indicators and results
Summary

## Slide 37: 7. CSOs indicators and results - 2021

## Slide 38: 7. CSOs indicators and results
9 Indicators/CSO
# testing
% treated
% Pv referral
% no RDT stock out
% no ACT 6x4 stock out
# VMW trained on ICCM
% functioning VMW
# supervision
# staff trained on PSEA

## Slide 39: 7. CSO indicators and results - 2021

## Slide 40: 7. CSO indicators and results - 2021

## Slide 41: 7. CSO indicators and results - 2021

## Slide 42: 7. CSO indicators and results - 2021

## Slide 43: 7. CSO indicators and results - 2021

## Slide 44: 8. DPC-HIS, WHO and MPSC indicators and results - 2021

## Slide 45: 8. DPC-HIS, MPSC and WHO indicators and results - 2021
DPC-HIS
MPSC
Key Activities |  |  | Milestones/Targets |  |  | Progress |  | Reasons for Programmatic deviation and any other comments |  |  |  |  |  |  | 
Generate annual health statistic report |  |  | Annual health statistics report for 2020 is finalized and disseminated |  |  | Advancing (2) |  | The draft report is finalized and currently processing the endorsement from the Minister. Finalization was delayed due to Covid 19 and prolonged stakeholder consultation to finalize the analysis of 5 year data (for the HDP VIII 2016-2020) and for increased number of indicators being reported from 34 to 50. |  |  |  |  |  |  | 
Key Activities |  |  | Milestones/Targets |  |  | Progress |  | Reasons for Programmatic deviation and any other comments |  |  |  |  |  |  | 
Establish functioning electronic web-based stock recording and reporting system |  |  | 85 % of the health facilities rolled out with integrated PSM program for inventory management is functioning |  |  | Completed (3) |  | 98.3% of the sites (184 out of 187 sites) with mSupply is functioning. Health facilities are using eLMIS properly, but we are facing some issue on using mSupply system such broken computers and Staff transition. |  |  |  |  |  |  | 
Train health staff on PSM system strengthening |  |  | PSM strengthening training is conducted for staff from Xiengkhoung, Houphan ( 21 health facilities province and district level) |  |  | Started (1) |  | Xiengkhoung province completed, Houphan province COVID-19 outbreak this activites will be implementing in Q1/2022. 9 health facilities in Xiengkhoung province received training. All relevant staff were trained |  |  |  |  |  |  | 

## Slide 46: 8. DPC-HIS, MPSC and WHO indicators and results - 2021
3. WHO
Indicators | Target | Result | Achievement | Remark
Number of surveillance trainings conducted by CMPE with the support from WHO TAs | 2 | 2 | 100% | 
Number of ICCM trainings conducted by CMPE with the support from WHO TAs | 2 | 2 | 100% | 
Malaria restratification completed with the support of WHO TAs | 2 | 2 | 100% | 
Malaria restratification completed with the support of WHO TAs | 1 | 0 | 0 | The stratification exercise which was planned for Q4 2021 was postponed until Q1 2022. This change was due to both inability for the program and partners to meet face to face which is important for in depth collaborative exercises such as this, and also the decision that a full set of annual data from 2021 would benefit the analysis and restratification work.

## Slide 47: 9. PF Elimination Accelerator - Detail

## Slide 48
Specific activities include:
Community engagement & social mobilization;
Village census;
Distribution of LLINs & LLIHNs ;
Targeted Drug Administration (TDA) - 2 rounds for males & females aged 7-49yrs;
Intermittent Preventive Treatment for forest / field goers (IPTf) aged 7-49yrs;
Active fever screening every 2 weeks;
9. PF Elimination Accelerator - Detail

## Slide 49
Target population :
- 63 villages in 7 districts, 5 provinces;
- Total population ≈ 24,000;
- Reported ~70% P.f./mix cases in 2020-2021;
- Males & females aged 7-49yrs targeted for TDA and IPTf according to the demographics of malaria burden in Lao: Males & females sleep in the forest / Whole families sleep in the cultivation fields;
Drug of choice :
ASMQ was used for TDA in pilot project in KM in 2021, but following low tolerance of the side effects, the drug of choice has been changed to Pryamax;
9. PF Elimination Accelerator - Detail

## Slide 50: 10. RSC Guidance for Reprograming Priorities

## Slide 51: 22. RSC Guidance and Schedule
RAI3E Savings Reprogramming Priorities endorsed by RSC:
Support to accelerated/aggressive/”last mile” interventions.
Surveillance strengthening (assessments and system sensitivity/comprehensiveness)
Data collection on mobile and migrant populations.
Expansion of the role of community-based health workers.
Operationalization of radical cure for P vivax.
Strengthening and increasing the frequency of reporting.
Exploring synergies with and possible contributions​ of the private sector

## Slide 52: 10. RSC Guidance and Schedule
15 March – RSC Chair will send the list of priorities for funding to PRs and SR
The guidance will request the SRs to send their proposals for new activities to UNOPS-PR by 15 April.
3 May - UNOPS-PR shares Consolidated Plan for Reprogramming with RSC Members, showing both already-budgeted activities and proposed new activities.
11-12 May – RSC endorses reprogramming plan with any additional guidance and requests UNOPS-PR to implement. Reprogramming is subject to Global Fund approval.

## Slide 53: Thank You!