## Slide 1: Lao PDR CCM Draft Oversight Plan 2021-2023 - Overview
23rd June 2022

## Slide 2: Background
CCM Evolution threshold assessment (2020) identified need for additional support to the oversight function
It is a Global Fund eligibility requirement that all CCMs have an Oversight Plan
Previous Oversight Plan expired in December 2020
A new plan (2021-2023) has been drafted for consideration and endorsement by the CCM
The new plan is structured according to the CCM’s current guidance

## Slide 3: Context
The new plan;
concerns oversight of 3 grants:
  National
  LAO-C-MOH: Improving health services access to strengthen the sustainability and quality of the national TB and HIV response
  Regional
  QSE-M-UNOPS: Regional Artemisinin Initiative 3 Elimination (RAI3E)
  QSE-T-IOM: TEAM2: Tuberculosis Elimination among Migrants
acknowledges the not-yet-completed CCM re-positioning process (will need updating when the process is completed.)

## Slide 4: Contents Overview
Introduction
Framework and Concepts
Oversight Processes
  Site visits
  Risk management
  Co-financing tracking
  Community-Based Monitoring
Stakeholder Roles
Annexes

## Slide 5: Framework and Concepts
7 Core Principles
Accountability
Strategic focus
Risk-based
Continuous across grant cycle
Engagement of relevant technical expertise
Avoidance of conflict of interest
Supportive and constructive approach

## Slide 6: Processes
Site visits (no change)
Risk management (new)
Co-financing tracking (stronger emphasis)
Community-Based/Led Monitoring (new)

## Slide 7: Risk Management
Key Risks from Funding Request
  Decentralization Risk: The risk of reduced support for TB /HIV programs as management responsibility decentralizes
  Co-Financing Risk: The risk of delays in realization of domestic funding commitments particularly in relation to procurement
  CSO Engagement Risk: The risk of limited CSO resourcing and engagement
Main questions for Oversight Committee:
  Are the risks still key?
  Have the planned mitigations been implemented?
  Are the mitigations reducing the risks?

## Slide 8: Community-Based/Led Monitoring
Important for identifying critical key population service access issues
An initial call has taken place with CHIAS
It was not then clear who would implement CLM and what form it would take
Key questions for the oversight process:
  Frequency of CLM data output
  Scope of CLM (populations/ facilities/ services covered)
  Type of data generated

## Slide 9: Roles
Secretariat
Oversight Committee Members
Implementers
CCM
Key Populations and People Living with Disease

## Slide 10: Annexes
Summary of active grants
Current Oversight Committee TOR
Field visit tools
CCM workplan 2022
Key risks for HANSA grant
Oversight Officer TOR

## Slide 11: Next Steps
Discussion/Endorsement of plan by CCM
Modifications once CCM re-positioning process has been completed
Training for Oversight Officer on risk management
Formalization of CBM/CLM data flow into Oversight Committee
Consideration of whether co-financing tracking can be further strengthened