## Slide 1
CCM Meeting Update from Global Fund Mission 23 June 2022

## Slide 2
Objectives of Mission 13-23 June 2022
1. HANSA monitoring mission
Review year 2 implementation progress and follow up on actions from the mission in November 2021
Site visit to Oudomxay
Propose recommendations & adjustments for year 3 implementation
2. C19RM Reprogramming
Review and discuss the C19RM reprogramming to optimize funding utilization

## Slide 3
Objectives of Mission 13-23 June 2022
3. Co-financing of TB and HIV health products
4. Looking forward 2024-2026

## Slide 4
1. HANSA monitoring mission

## Slide 5
1. HANSA monitoring visit – TB & HIV
Overall findings & achievements
Despite the challenges in implementation due to the Covid-19 lockdowns and travel restrictions, the TB and HIV programs accelerated implementation in year 2
Roadmaps were developed by NTC, CHAS and partners to catch up
DLI J: achievement of the TB case notification targets is reported at 90% and 100% for GeneXpert diagnosis
DLI K: over-achievement of targets reported for HIV testing among KPs (102% for FSW and 121% for MSM) and 106% for ART coverage for year 2

## Slide 6
1. HANSA monitoring visit - TB
Challenges
Sputum specimen transportation to GeneXpert testing
Increase TB diagnosis capacity in district hospital and health centers
Catch up with ACF in high prevalence districts and prisons
Conducting contact tracing
Case finding in children

## Slide 7
1. HANSA monitoring visit - TB
Recommendations
NTC with the support of technical partners including WHO, CHAI and CSOs, to submit a revised implementation strategy for year 3 under HANSA. The revised implementation strategy should consider the following elements to be rolled out during the last year of the current grant and the next GF investment:
Concrete steps to integrate TB services in PHC service delivery and ensure availability of services at the community level;
Increase TB case notification and treatment through a two-pronged approach to intensify case finding in the health facility, including contact tracing and active case finding by strengthening the local/community response to conduct ACF;

## Slide 8
1. HANSA monitoring visit - TB
Recommendations
iii) Optimize and increase case finding among children;
iv) Optimize usage of GeneXpert as the primary diagnosis tool for all presumptive TB cases and to increase MDR-TB diagnosis;
v) Improve quality of care for MDR-TB patients including enrollment of diagnosed patients on treatment, adopt new short treatment regimens and provide patient-centered care and enablers (food or transport subsidies); and
vi) Ensure complementarity of activities funded under C19RM to ensure these directly support HANSA and the national Covid response.

## Slide 9
1. HANSA monitoring visit - HIV
Challenges
Reaching KPs due to the lockdowns
Access and referrals to the target groups have decreased
Delays in fund flow
Reaching target groups (FSW and MSM) has not been achieved as compared to the national strategic target (92% by 2022)

## Slide 10
1. HANSA monitoring visit - HIV
Recommendations
By 30 June 2022, DPC and CHAS to confirm access to additional GF funding for Technical Assistance support to design and implement innovative approaches to reach key populations with HIV services.
The scope of work for the TA should be developed jointly between GF, CHAS, CSOs, WHO, and UNAIDS to ensure that it fits the needs and priorities of the country and supports achievement of the NSP targets.
Timelines for TA: July 2022 – December 2023

## Slide 11
1. HANSA monitoring visit - HIV
Recommendations
CHAS with the support of technical partners including WHO, CHAI and CSOs, to submit a revised implementation strategy for year 3 under HANSA. The revised implementation strategy should consider the following elements to be rolled out during the last year of the current grant and the next GF investment:
Concrete steps to integrate HIV services in PHC service delivery through the decentralization of HIV testing and treatment services at the HC and community level, including universal access to PMTCT services;
Review and update year 3 targets for HIV testing and ART coverage under HANSA to ensure an ambitious scope and further progress towards elimination;

## Slide 12
1. HANSA monitoring visit - HIV
Recommendations
iii) Review and update strategic information for key populations to improve program design and targeting, including disaggregated data for TGs, sub-national data and hotspot mapping;
iv) Scale up innovative community-based approaches to reach KP with HIV prevention, testing and treatment services;
v) Scale up TB/HIV collaborative activities, including provision of TPT for PLHIV, HIV testing for all TB patients and full ART coverage for co-infected patients; and
vi) Ensure complementarity of activities funded under C19RM to ensure these directly support HANSA and the national Covid response.

## Slide 13
2. C19RM reprogramming

## Slide 14
2. C19RM reprogramming
General comments
US$ 7.1 M of C19RM funding for 2021-2023 period
19% reported expenditure rate
US$ 5.4 M (70% of total budget) has been allocated in Y2 (2022) - feasibility of absorption
Travel related cost accounts for 19% of total budget, making this cost-input the most budgeted. It is mainly distributed for support towards Malaria programs (6%), HIV program (4%), TB program (3%), and CBOs monitoring (2%). These activities relate to advocacy, training, household visits for drug delivery, transportation of VMWs, IEC material, and monitoring.
HR cost at the PR and SR level accounts for 7% of the total budget.

## Slide 15
2. C19RM reprogramming
DPC to work with SRs ensure a cohesive strategy focused on program priorities:
Opportunities to strengthen and improve TB, HIV and malaria program results
Ensuring synergies with other COVID-19 related investments: e.g. PPE (13% of total budget), please consider forecast and current stocks
Strengthen diagnostics capacity (x-ray machines, GeneXpert machines, replacement modules) to support multiple programs
Reinforcement of laboratory information system (e.g. Xpert connectivity solution)
Address gaps in cold chain storage facilities at the central warehouse level for time and temperature-sensitive laboratory reagents, test kits etc.

## Slide 16
3. Co-financing of TB & HIV health products

## Slide 17
3. Co-financing of TB & HIV health products
Government of Lao PDR committed US$ 3.1 M of domestic funding for procurement of HIV and TB commodities for the 2021-2023 period

## Slide 18
3. Co-financing of TB & HIV health products
The following risks have been raised with MOH, DOF & MOF:
delays in disbursement of domestic funds for procurement of 2023 commodities may result in delays in ordering and arrival of health products, putting at risk patients’ access to life-saving treatment;
unfavorable exchange rate evolution resulting in higher commodity prices in Lao Kip.
Recommendation: DPC, CHAS and NTC to work closely with DOF and MOF to ensure funding availability and timely ordering of commodities based on the current stocks. MOF to develop a strategy to manage the unfavorable exchange rate, given that this is a likely issue across other health programs and sectors.

## Slide 19
4. Looking forward 2024-2026

## Slide 20
4. Looking forward 2024-2026
Informing the next GF investment in Lao PDR for the 2024-2026 period
September 2022: GF’s 7th replenishment campaign to raise at least US$18 billion to fight HIV, TB and malaria and build stronger systems for health, and reinforce pandemic preparedness
November 2022: HANSA Mid-Term Review informed by 3 learning exercises - DLI learning, HANSA evaluation & community consultations
GF allocation letter to be shared with Lao PDR CCM end-2022
Dec 2022 - Q1 2023: preparation & submission of GF Funding Request for 2024-2026
Q2-Q3 2023: negotiation & approval of next GF grant

## Slide 21
4. Looking forward 2024-2026
Recommended next steps
CCM to ensure compliance with eligibility requirements: representation of key populations, people living with/affected by the diseases & non-government constituencies; inclusive dialogue for FR development; & transparent and documented PR selection process.
HANSA Mid-Term Review: DPC & CCM to lead MTR to ensure a national discussion and prioritization exercise based on the findings and recommendations from 3 learning exercises (DLI learning, HANSA evaluation & community consultations)
3. Funding Request development: CCM & WHO to engage a team of consultants

## Slide 22
AIS Sign-off
Concept Review
Disclosure of Concept PID -Disclosure of Concept ESRS
Decision Review - Disclosure of Appraisal PID - Disclosure of Appraisal ESRS - Begin Appraisal
Authorize Negotiations
Approval
GF Board approval
GAC
Quality Enhancement Review
Submission to TRP
Allocation Letter
TRP meeting
Q4
Q1
Q2
Q3
Q4
2023
2022
WB timeline
GF timelines

## Slide 23
THANK YOU