## HANSA Risk Tracker
HANSA Grant Risk and Mitigation Tracker
Date:
Risk | Severity | Likelihood | Risk Level | Mitigations | Mitigation Status | Mitigation Result | Severity | Likelihood | Risk Level
Decentralization Risk TB and HIV programme receive less focus and specific support at central level while decentralization process and provincial/district management capacity takes time to hand over ownership and responsibilities for addressing the two epidemics. | Moderate | Likely | High | Develop specific indicators related to GF investment in TB and HIV with defined targets per year: (DLI J for TB notification and GeneXpert coverage for each province and DLI K for HIV for coverage of key populations). |  |  | Minor | Highly Unlikely | Low
|  |  |  | Progressively shift share of DLI funding value from NTC to PHD and DHO in accordance with HANSA DLI verification protocol |  |  | Minor | Unlikely | Low
[7 empty] | Minor | Likely | Medium
[7 empty] | Minor | Highly Likely | Medium
[7 empty] | Moderate | Highly Unlikely | Low
[7 empty] | Moderate | Unlikely | Medium
Co-Financing Risk Domestic funding delay of procurement by domestic co-financing | Major | Likely | High | Procurement of essential tests and drugs of TB and HIV to be supported by GF procurement budget during the first year (including 6 months buffer) until mid 2022 and then progressively handed over to GoL to give more time to secure the domestic funding. |  |  | Moderate | Likely | High
|  |  |  | Training by WB of the DPC (MoH) procurement unit, procurement planning and monitoring, transparency and publication, staff DOI, check of specifications including value for money, careful planning of consultants’ recruitment. |  |  | Moderate | Highly Likely | High
[7 empty] | Major | Highly Unlikely | Medium
[7 empty] | Major | Unlikely | High
[7 empty] | Major | Likely | High
[7 empty] | Major | Highly Likely | Very High
CSO Engagement Risk Limited/delayed access to funding and involvement of CSOs to implement community-based TB and HIV activities | Minor | Likely | Medium | Set up a mechanism for CSO subcontracting by MoH DPC (a prerequisite for the provision of the first-year advance funding of DLI funds in both DLI J for TB and DLI K for HIV) |  |  | Critical | Highly Unlikely | Medium
[7 empty] | Critical | Unlikely | High
[7 empty] | Critical | Likely | Very High
[7 empty] | Critical | Highly Likely | Very High
[7 empty] | Severity | Likelihood | Risk Level
[7 empty] | Minor | Highly Unlikely | Low
[7 empty] | Moderate | Unlikely | Medium
[7 empty] | Major | Likely | High
[7 empty] | Critical | Highly Likely | Very High
Not Implemented
Implementation in Progress
Implementation Completed
Risk Level Reduced
Risk Level Remained the Same
Risk Level Increased
Risk Actualised