## Slide 1: An Overview of Risk Management
Oversight & Resource Mobilization Committees
LAO PDR CCM
30th August 2022

## Slide 2: What is Risk?
“A risk is something uncertain – it might happen or it might not. …[It] matters because, if it happens, it will have an effect on objectives.”
– Institute of Risk Management

## Slide 3: Key Characteristics of Risk
It lies in the uncertain future
It is dynamic (changes over time)
It is relative (to a point of view, to a point in time, and to your grant objectives.)

## Slide 4: What is Risk Management?
“Any activity taken to identify and then control the level of risk which objectives face”
–Institute of Risk Management

## Slide 5: Why Manage Risk?
To increase your chances of achieving your grant objectives
To protect your grant funds and assets
To reduce the chances of unpleasant and costly surprises
To improve organizational readiness
To improve stakeholder confidence in your management capacity

## Slide 6: The Risk Management Process

## Slide 7: 1. Establishing the Context
This involves reviewing:
Your grant objectives
Historical grant performance
Any OIG/LFA reports
Any PR/SR/SSR capacity/performance assessments
Your grant implementation map (look for potential stress points/bottlenecks)

## Slide 8: 2. Risk Assessment

## Slide 9: 2.1 Risk Identification Contributing Factors v Risks

## Slide 10: 2.1 Risk Identification Sample Risk Statements:
  “Poor quality storage facilities, which may render test kits ineffective causing us to miss testing targets.”
  “Historic high staff turnover, which could cause failure to reach output targets and loss of technical capacity.”
  “Highly discriminatory operating environment, which has the potential to result in under utilization of services by marginalized populations.”

## Slide 11: 2.2 Risk Analysis – Likelihood + Severity
This involves 2 questions for each risk identified:
What is the chance (likelihood) that this risk will occur in the next 12 months?
Highly Unlikely – Unlikely – Likely - Highly Likely
If it does occur, how severe will its impact on our grant objectives be?
Minor – Moderate – Major - Critical

## Slide 12: 2.3 Risk Evaluation

## Slide 13: Risk Ratings
A risk rating is a guide to action: the higher the risk level the more urgent the need to treat the risk
Rating risks enables you to be strategic about which ones to invest in addressing
Risk ratings vary over time – you need to reassess risks annually

## Slide 14: Exercise 1: Rating the Risks already Identified for the HANSA Grant

## Slide 15: Key Risks to HANSA Grant
Key Risks to HANSA Grant (from Funding Request)
Decentralization Risk: The risk of reduced focus and support for TB/HIV programs as management responsibility shifts from central down to provincial/district level
Co-Financing Risk: The risk of delays in realization of domestic funding commitments particularly in relation to procurement
CSO Engagement Risk: The risk of limited CSO resourcing and engagement

## Slide 16: Decentralization Risk: The risk of reduced focus and support for TB/HIV programs as management responsibility shifts from central down to provincial/district level
Risk Levels |  | Severity |  |  | 
 |  | Minor | Moderate | Major | Critical
Likelihood | Highly Unlikely | Low | Low | Medium | Medium
 | Unlikely | Low | Medium | High | High
 | Likely | Medium | High | High | Very High
 | Highly Likely | Medium | High | Very High | Very High
Risk1: Evaluate this Risk
How likely is it that this risk will actualise?
If this risk actualizes, how severe will its impact be?

## Slide 17: Co-Financing Risk: The risk of delays in realization of domestic funding commitments particularly in relation to procurement
Risk Levels |  | Severity |  |  | 
 |  | Minor | Moderate | Major | Critical
Likelihood | Highly Unlikely | Low | Low | Medium | Medium
 | Unlikely | Low | Medium | High | High
 | Likely | Medium | High | High | Very High
 | Highly Likely | Medium | High | Very High | Very High
Risk2: Evaluate this Risk
How likely is it that this risk will actualise?
If this risk actualizes, how severe will its impact be?

## Slide 18: CSO Engagement Risk: The risk of limited CSO resourcing and engagement
Risk Levels |  | Severity |  |  | 
 |  | Minor | Moderate | Major | Critical
Likelihood | Highly Unlikely | Low | Low | Medium | Medium
 | Unlikely | Low | Medium | High | High
 | Likely | Medium | High | High | Very High
 | Highly Likely | Medium | High | Very High | Very High
Risk3: Evaluate this Risk
How likely is it that this risk will actualise?
If this risk actualizes, how severe will its impact be?

## Slide 19: Risk Rating Results

## Slide 20: 3. Treating Risks

## Slide 21: 3 Ways of Reacting to Risk
AVOID: Stop doing the thing that gives rise to the risk
IGNORE: Carry on doing the thing that gives rise to the risk, regardless:
REDUCE: Plan and implement actions that reduce the risk (mitigate.)

## Slide 22: Treatment Approaches
Focus on addressing the contributing factors that give rise to the risk
Treatment actions can reduce chance (likelihood) and/or severity of impact: even if you can’t control likelihood you can still reduce potential impact
Common treatment approaches involve capacity building and/or systems strengthening

## Slide 23: Planned Mitigations for HANSA Grant Key Risks (from Funding Request)
Risks | Proposed Mitigations
Decentralization Risk (less focus and support for TB/HIV) | Indicators related to GF investment in TB/HIV have been developed with annual targets. Progressive shift of share of DLI Funding Value over time. (National level share ↓, provincial and district share ↑)
Co-Financing Risk (domestic procurement delays) | Procurement of essential tests/drugs of TB/HIV supported by GF budget during 1st year. Then progressively handed over to GoL. Training by WB of the DPC procurement unit, procurement planning and monitoring, transparency and publication, staff DOI, check of specifications including value for money, careful planning of consultants’ recruitment.
CSO Engagement Risk (ltd access to funds/ ltd involvement) | Setting up of a mechanism for subcontracting CSOs by MoH DPC is a prerequisite for the first-year advance funding of DLI funds in both DLI J for TB and DLI K for HIV

## Slide 24: 2 Key Questions for Monitoring Mitigations
Did it happen? (Was the mitigation implemented as planned?)
Did it work? (Did it reduce the risk?)
  Reducing Risk =
    Reducing likelihood
    Reducing severity of (potential) impact
    Reducing both likelihood and severity

## Slide 25: Exercise 2: Monitoring the Mitigations already Planned to Manage Key Grant Risks

## Slide 26: Mitigation Implementation Monitoring

## Slide 27: Treatment Impact

## Slide 28: Communication & Consultation

## Slide 29: Throughout the Risk Management Cycle
Actively involve different departments in risk identification and assessment
  A richer perspective on risk
  A stronger chance of buy-in
Involve a broad range of stakeholders for a more balanced assessment: CCM, PR, SR, Govt, CSO, service beneficiaries and target populations
Share the mitigation plan appropriately
Update key stakeholders about actions taken and the results

## Slide 30: Finally: Monitor & Review

## Slide 31: What to Monitor
Change in risk likelihood or severity of impact? New risks?
Implementation of mitigation plans – are things going as planned?
Impact of mitigation actions – did they reduce the risk as expected?
The operating environment – any critical developments?
Lessons learned should inform next risk assessment cycle

## Slide 32: The Ongoing Risk Management Cycle

## Slide 33: Summary: 3 Key Risk Management Tasks for Oversight
Monitoring Risks
Have they actualised/happened?
(If not) Has the risk level changed (likelihood and/or severity)? – Annual Assessment
Monitoring Mitigations
Have they been implemented? (Checked regularly in Oversight Committee Meetings)
(If yes) Did they reduce the risk level (likelihood and/or severity)
Agreeing New Mitigations
(If the risk level has increased) What additional mitigations will be implemented?
(If no change in risk level after mitigation implementation) What additional mitigations will be implemented?

## Slide 34: Two Tools to Support Risk Management in Oversight
Co-financing commitment tracker
  Tracks annual domestic budget approvals and expenditure against annual co-financing commitments for HIV and TB
HANSA grant risk and mitigation tracker
  Logs risk rating for each of the three HANSA grant risks and tracks progress and impact of mitigations
  User selects Severity and Impact levels for each risk – risk rating is automatic based on selection
  Allows addition of new mitigations

## Slide 35: Questions?