## Sheet1
Integrated Timelines for GF Funding Request Preparation, Cycle Year 2024-2026
Key Activities
Date | HIV/TB | RAI4E | CCM
September 2022
2022-09-30 |  |  | Full-day CCM Plenary Meeting
October 2022
November 2022
1-2 Nov 2022 |  | MTR (Mid-term review) Validation meeting on National Malaria Program
22-23 Nov 2022 |  | 20th Regional Steering Committee Meeting Meeting in Bangkok
2022-11-30 |  |  | Oversight Committee (OC) Meeting
December 2022
2022-12-07 |  | Global Fund Allocation Letter arrives (TBC) | Prepare annual evaluation of the CCM Integrated Performance Framework (IPF)
13-15 Dec 2022 | Annual Review Meeting the National HIV Program
2022-12-14 |  | National Consultation on Priorities and Allocation
Mid Dec 2022 | Expected GF allocation letter circulation
2022-12-15 |  |  | Full-day CCM Plenary Meeting
By end Dec 2022 | Desk review of programmatic and financial data
January 2023
By end Jan 2022 | Field visit at district and health centre levels in selected provinces
February 2023
2023-02-02 |  | Country Dialoque on RAI4E Country Component
2023-02-06 |  | 1st draft FR submission to CCM and RSC | OC and CCM review and comment on the 1st draft FR for RAI4E through E-mail
By the 1st week of Feb 2023 | Partners consensus workshop (WS) to prioritize the next GF funding request
3 -27 Feb 2023
9-10 Feb 2023 |  | Regional Dialogue on RAI4E Funding Request by the Writing Committee in Bangkok | OC and RMC meeting on 9 Feb. to review and comment on the draft FR for RAI4E
2023-02-17 |  | 2nd draft FR submission to CCM and RSC | OC and CCM review and comment on the 2nd draft FR for RAI4E through E-mail
2023-02-21 |  |  | CCM Meeting to review and endorse the draf FR for RAI4E
By 3rd week Feb 2023 | Draft MTR report share with stakeholders
By last week Feb 2023 | HIV and TB NSP Updates (2026-2030)
By last week Feb 2023 | 1st draft FR share with CCM and GF CT
March 2023
2023-03-01 |  |  | OC and CCM review and comment on the draft FR for TB and HIV through E-mail
2023-03-06 |  | Final FR submission to RSC | OC Meeting to review the draf FR for TB and HIV
9-10 Mar 2023 | Final draft FR submit to CCM | 21st Regional Steering Committee Meeting (Vientiane, Lao PDR)
2023-03-14 |  |  | CCM Meeting to review and endorse FR for TB and HIV
2023-03-20 | DEADLINE FOR SUBMISSION OF TB AND HIV FUNDING REQUEST TO GLOBAL FUND | DEADLINE FOR SUBMISSION OF REGIONAL RAI4E FUNDING REQUEST TO GLOBAL FUND | DEADLINE FOR SUBMISSION OF ALL NEW FUNDING REQUEST TO GLOBAL FUND