## Roadmap_Coordination
| 2022 |  |  |  | 2023 | [47 empty] | 2024
| December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Jan - Dec
Global Fund |  | CCM Meeting 15 Dec | Allocation Letter |  |  |  |  | HANSA 2 Design mission |  |  | CCM Endorsement & review of FR |  |  |  | FR Submission 20 March |  | TRP Clarification period |  |  | TRP Meeting* |  |  |  |  | TRP Outcome* |  | Grant Making: Incorporating TRP recommendations Finalazing grant documents | [10 empty] | GAC Meeting |  |  |  | Board Approval |  |  |  | Preparation and signing of Grant Docs
HANSA Evaluation | Interim Report | [6 empty] | Final Report
Community Consultation | Draft report | Presentation of findings to CCM
HIV Differentiated Service Delivery TA - IQVIA | Development: Situational report Checklist Field Visits |  | Field Visits |  | Field Visits |  | Report - Field Visits | Draft Report DSD model and strategy |  |  |  | Final Report |  |  |  | Workshop
HIV/TV joint MTR |  | Desk Review HIV and TB |  |  |  |  | Field visits |  |  | Partner's workshop | Draft MTR submission | NSP Update
UNAIDS | [7 empty] | AEM Modelling Workshop 30 Jan to 3 Feb
WHO
World Bank | Concept Note Package Preparation | [6 empty] | HANSA 2 Design mission