## Sheet1
Integrated Timelines for GF Funding Request Preparation, Cycle Year 2024-2026
Key Activities
Date | TB and HIV Programs | Malaria Program (RAI4E) | CCM
September 2022
2022-09-30 |  |  | Full-day CCM Plenary Meeting
October 2022
November 2022
1-2 Nov 2022 |  | MTR (Mid-term review) Validation meeting on National Malaria Program
22-23 Nov 2022 |  | 20th Regional Steering Committee Meeting in Bangkok
2022-11-30 |  |  | Oversight Committee (OC) Meeting
December 2022
2022-12-07 |  | Global Fund Allocation Letter arrives (TBC) | Prepare annual evaluation of the CCM Integrated Performance Framework (IPF)
13-15 Dec 2022 | Annual Review Meeting the National HIV Program
2022-12-14 |  | National Consultation on Priorities and Allocation
Mid Dec 2022 | Expected GF allocation letter circulation
2022-12-15 |  |  | Full-day CCM Plenary Meeting
By end Dec 2022 | Desk review of programmatic and financial data
January 2023
By end Jan 2022 | Field visit at district and health centre levels in selected provinces
February 2023
2023-02-02 |  | Country Dialogue on RAI4E Country Component
2023-02-06 | Kick-off meeting of the HANSA2 preparation mission | 1st draft RAI4E Funding Request submission to CCM and RSC | OC and CCM review and comment on the 1st draft RAI4E Funding Request through E-mail
2023-02-08 | Partners consensus workshop (WS) to prioritize the next GF funding request
9-10 Feb 2023 |  | Regional Dialogue on RAI4E Funding Request by the Writing Committee in Bangkok
2023-02-15 |  |  | OC Meeting to review and comment on the draft RAI4E Funding Request
2023-02-17 |  | 2nd draft RAI4E Funding Request submission to CCM and RSC | OC and CCM review and comment on the 2nd draft RAI4E Funding Request through E-mail
2023-02-21 |  |  | CCM Plenary Meeting to review and consider for endorsement of the draft RAI4E Funding Request Country Component
By 3rd week Feb 2023 | Draft TB and HIV Mid-term Review (MTR) report share with stakeholders
By last week Feb 2023 | TB and HIV National Strategic Plan (NSP) Updates (2026-2030)
By last week Feb 2023 | First draft TB and HIV Funding Request (combine with PAD) share with CCM and GF CT
March 2023
2023-03-01 |  |  | OC and CCM review and comment on the draft FR for TB and HIV through E-mail
2023-03-06 |  | Final RAI4E Funding Request submission to RSC
2023-03-07 |  |  | OC Meeting to review and comment on the draft TB and HIV Funding Request (combine with PAD)
9-10 Mar 2023 | Final draft TB and HIV Funding Request (combine with PAD) submit to CCM | 21st Regional Steering Committee Meeting (Vientiane, Lao PDR)
2023-03-14 |  |  | CCM Plenary Meeting to review and consider for endorsement of the TB and HIV Funding Request (combine with PAD)
2023-03-20 | DEADLINE FOR SUBMISSION OF TB AND HIV FUNDING REQUEST (combine with PAD) TO GLOBAL FUND | DEADLINE FOR SUBMISSION OF REGIONAL RAI4E FUNDING REQUEST TO GLOBAL FUND | DEADLINE FOR SUBMISSION OF ALL NEW FUNDING REQUEST TO GLOBAL FUND