## Slide 1: National TB Center (NTC) Progress of HANSA Project Implementation-DLI-J
Ad-hoc CCM plenary Meeting on 26 October 2023

## Slide 2: Contents
Progress of HANSA1 Project Implementation-DLI-J (TB) 2021-2023
Co - financing period 2018- 2020 and 2021- 2023

## Slide 3
Progress of HANSA1 Project Implementation –
DLI-J (TB) 2021-2023

## Slide 4: HANSA1 project DLI-J TB- condition 1: TB notification targets and achievements
Chart: TB notified (new and relapse all forms)
| Year 1 | Year 2 | Year 3
Target | 3107 | 7537 | 7449
Achieved | 2548 | 6876 | 9517
Progress | 0.82 | 0.91 | 1.28
Y1 Jan 2021-May 2021
Y2 Jun 2021-May 2022
Y1 Jun 2022- May 2023

## Slide 5: TB DLI-J Condition 1: Y3 achievement by provinces
DLI J Indicator 1: Number of notified TB cases of all forms (i.e. bacteriologically confirmed and clinically diagnosed new and relapse cases) HANSA 1 Year 3 (Jun 2022 – May 2023)

## Slide 6
  Condition2: Proportion (%) of presumptive TB or MDR‐TB patients examined by GeneXpert (source: DHIS2)
Chart: Xpert testing coverage
| Year 1 | Year 2 | Year 3 | Year 1-3
No. of presumtive TB | 15137 | 34498 | 43071 | 92706
No. of Xpert Test | 14952 | 34498 | 42832 | 92282
99 %
99,5 %
HANSA1 project DLI-J TB- condition 2: GeneXpert coverage targets and achievements

## Slide 7: GeneXpert testing for Routine and ACF Presumptive TB Jan 2021 to May 2023
Chart: 
| 44197 | 44228 | 44256 | 44287 | 44317 | 44348 | 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047
Central Hosp | 801 | 818 | 901 | 551 | 540 | 597 | 807 | 934 | 657 | 394 | 349 | 359 | 546 | 670 | 715 | 722 | 887 | 957 | 1116 | 1209 | 1183 | 836 | 886 | 923 | 960 | 871 | 1296 | 761 | 1336
Prov Hosp | 1116 | 1000 | 1222 | 849 | 842 | 1009 | 1071 | 973 | 806 | 788 | 731 | 703 | 771 | 931 | 881 | 711 | 1049 | 1204 | 1088 | 1305 | 1368 | 1322 | 1312 | 1049 | 1071 | 1230 | 1540 | 1031 | 1257
District Hosp | 1105 | 995 | 1262 | 642 | 629 | 899 | 1097 | 1378 | 1152 | 998 | 1022 | 1199 | 930 | 1046 | 1164 | 965 | 1573 | 1556 | 1611 | 2070 | 2406 | 2175 | 2169 | 1888 | 1514 | 1773 | 2175 | 1301 | 1947
Active case finding | 229 | 180 | 232 | 0 | 0 | 0 | 376 | 366 | 44 | 0 | 161 | 110 | 98 | 255 | 313 | 332 | 690 | 192 | 336 | 319 | 185 | 227 | 156 | 126 | 368 | 510 | 391 | 62 | 225
Total GX tests | 3251 | 2993 | 3617 | 2042 | 2011 | 2505 | 3351 | 3651 | 2659 | 2180 | 2263 | 2371 | 2345 | 2902 | 3073 | 2730 | 4199 | 3909 | 4151 | 4903 | 5142 | 4560 | 4523 | 3986 | 3913 | 4384 | 5402 | 3155 | 4765

## Slide 8
Co - financing period
2018-2020 and 2021-2023

## Slide 9: Government Co- financing committed and expended overview ( in USD) 2018 -2020
Program | Co- financing 2018 - 2020 |  |  |  |  |  |  | 
 | 2018 |  | 2019 |  | 2020 |  | 2018 - 2020 | 
 | Committed | Expended | Committed | Expended | Committed | Expended | Committed | Expended
Tuberculosis | 782,194 | 432,675 | 401,096 | 514,388 | 620,136 | 456,339 | 1,803,426 | 1,403,402

## Slide 10: Government Co- financing committed and expended overview ( in USD) 2021 -2023
Program | Co- financing 2021 - 2023 |  |  |  |  |  |  | 
 | 2021 |  | 2022 |  | 2023 |  | 2021 - 2023 | 
 | Committed | Expended | Committed | Expended | Committed | Expended | Committed | Expended
Tuberculosis | 157,688 | 109,900 | 476,142.40 | 285,088.11 | 658,232.11 | 577,494.42 | 1,292,062.51 | 972,482.53

## Slide 11
ຂອບໃຈ