## Slide 1: Report of Joint Oversight Field Visit
Activities supported by the Global Fund to Fight AIDS, Tuberculosis and Malaria (GFATM)
Borlikhamxay Province
Date 06-10 November 2023
Prepared by: CCM Secretariat

## Slide 2: Participants:
Representative of CCM Members and CCM Secretariat:
President of Lao Red Cross, CCM Chair
Department of Planning and Finance, MOH
Department of Communicable Disease Control, MOH
Inspection Department, Lao Federation of Trade Unions, CCM Member
Center for Malaria Parasitology and Entomology (CMPE), MOH
Center for HIV/AIDS and STI (CHAS), MOH
National Tuberculosis Control Center, MOH
Chair of APL+, CCM and OC Member
President of Association for the Development and Promotion of Women’s Leadership, CCM
CCM Secretariat.

## Slide 3: Visiting Sites
Provincial Health Department;
ARV center at provincial hospital;
Viengthong District Health Office/Hospital
Houyhoi Health Center
Chomthong Health Center
Borlikhan District Health Office/Hospital
Phouhomexay Health Center
Houykhoun Health Center

## Slide 4: Main Purpose:
To oversee the overall implementation progress, key issues and challenges of the activities supported by the Global Fund at provincial, district and health center level by focusing on: Finance; Procurement; Implementation; Reporting​ and Results​.

## Slide 5: HIV/AIDS

## Slide 6: Key Achievements
Under leadership from the central, provincial and district level, the projects were successfully implemented
Received some budget from the government and HANSA project
Supported of 5 project volunteers
Provincial level, there are two working units for the implementation of HIV/AIDS and STI namely: Secretariat Unit and Treatment Unit for infected patients.
Secretariat Unit
A comprehensive center for HIV/AIDS and STI
Reports on VCT and STI testing services

## Slide 7: Key Achievements (Conti.)
Project management, financial and activity planning
Organize partnership meetings, coordinate with relevant departments and district secretariats
Monitor and encourage the district team
Summarize the VCT/STI data recorded in the DHIS2 system and send a report to CHAS monthly.
Treatment Unit
There are some service units such as POC, VCT/PICT and ARV treatment
Provide blood test and treatment services for HIV patients free of charge
1 volunteer (PEER)
Record data into the HIVCAM/DHIS2

## Slide 8: Key Achievements (Conti.)
Supported by the HANSA project in 2023
Mobile activities to provide knowledge to change the behavior of target groups in the community and blood tests for HIV infection among MSM, TG quarterly
The activity implementation of DLI-K Y2 and Y3 has met the target
Volunteers find target groups to educate and mobilize for the blood tests
Secretariat, colleagues, districts and volunteers are promoting for mobile health education information for target groups
Monitor to promote preventive work in risk groups (2 times/year)

## Slide 9: Key Issues
The budget is limited and the HIV/AIDS activity has not yet reached health centers
The supply of condoms is still insufficient to meet demand
Difficulty in reaching target groups due to:
the outbreak of Covid-19
Most restaurants are closed
Some FSWs are in remote areas where volunteers cannot reach
Some FSWs are frequent moves to work in other places
Some FSWs do not cooperate, for example, they do not voluntarily accept blood tests for HIV

## Slide 10: Key Issues
Frequent turnover of staffs, old staff have retired, new ones who have not been trained yet
Provincial hospital does not have enough bedroom and counselling room for patients and a staff is responsible for many tasks
Devices such as computers are insufficient to support their work
Patients sometimes lack of drugs because there is not available in the CHAS, and the patients are required to buy the drugs for themselves
The problem of incentive disbursement to some volunteers who work to achieve the target and some do not achieve the target but they received the same amount of incentive.

## Slide 11: Proposals
Request more budget to support in HIV/AIDS and STI activity
Request more budget for retraining staff in the HIV/AIDS and STI
Provincial hospital needs bedrooms and counseling rooms for TB and HIV patients and requests more staffs
Increase incentive to access, find target groups to access health services and refer more infected people for treatment
Increase the supply of condoms to meet demand
There should be a follow-up of patients referred for verification at the provincial hospital and patients who are taking drug to prevent drug shortages, incorrect taking drugs and lost follow-up patients
There should follow-up evaluation every period from the central, provincial, district and health center regular and continuous
District level requests for a laptop to support in reporting.

## Slide 12: Tuberculosis

## Slide 13: Key Achievements
Under leadership from the central, provincial and district level, the projects were successfully implemented
Received budget from the government, HANSA project and humanities project
The policy of free diagnosis and treatment of TB
Analytical equipment is sufficient to meet the demand
Sufficient TB drug can be provided regularly and on time
There is a recording system and TB Tracker data entry
There is a GeneXpert to for sputum testing to find TB suspecting case to diagnose

## Slide 14: Key Achievements (Conti.)
All TB patients received voluntary counseling for HIV testing
There is a TB control network from the provincial, district and health center level
Reporting is using the DHIS2 system at the district/province/central level
The district level monitor and supervise health centers regularly
Management and follow-up TB patients in the DHIS2 system by individual data entry (TB Tracker) which is very convenient in reporting and using data
Each health center has a refrigerator to collect sputum samples

## Slide 15: Key Issues
Patients receive a delayed diagnosis and combined with co-infection (TB/HIV)
Receive a delayed budget and the budget for IEC materials and monitoring activities at the village level is still limited;
Screening for TB suspected cases and sending sputum samples from health centers and district hospitals to diagnostic testing at provincial hospitals with GeneXpert have not met the target
The number of notified TB cases all form (new and relapse) did not meet the targeted indicator

## Slide 16: Key Issues (Conti.)
Insufficient staff at TB unit, one staff is responsible for many duties, the staffs have been replaced frequently and some staff in the district level have not yet understood the policy of sputum sample delivery due to their new duties
Some reports are not on time, there is a discrepancy between the number in hard-copied and the system is different
Tuberculosis information has not yet reached the local people especially in remote areas, there are still many people who do not know and understand about tuberculosis.
The involvement of local authorities is also limited

## Slide 17: Proposals
Request central level to conduct a quarterly monitoring
Request for a budget for retraining TB work for health center levels
Request the central level to implement ACF together with the provincial, district and health centers and at the prison and detention camp
Request more budget for sending samples or incentive for collecting samples ( health center to collect samples at villages or sending samples from villages to health center)

## Slide 18: Malaria

## Slide 19: Key Achievements
Receive technical guidance, project management from the DCDC, CMPE and Provincial Health Department
RAI3E projects support the budget such as: surveillance, response, malaria elimination areas
Received support from KOFIH to survey mosquitoes in villages in 4 target districts in 2022
The technical staffs at provincial and district level participated in the seminar meeting and learned lessons
The provincial and district levels have a quarterly meeting for learn lessons to supervise and monitor on project management

## Slide 20: Key Achievements (Conti.)
There is a surveillance system. The tests and drugs for Malaria treatment are available
No Malaria cases were reported and no death cases of Malaria were reported
The implementation of the activity has achieved the goal according to the plan
Timely reporting and the reporting is using the DHIS2 system
There is joining WhatsApp group together with central, provincial and district levels to daily report to the group.

## Slide 21: Key Issues
The budget for monitoring at the provincial, district and health center levels is limited
Blood tests in some months are still low in some health facilities
Malaria infection is transmitted from other provinces that causes difficulty to prevent and control
There are still some areas that have not been regularly surveyed, especially the target villages of the district
Have not received LLINs. There is still not enough liquid insecticide in some areas and some districts
Local people still have not intended to surveillance and control mosquitoes continuously

## Slide 22: Key Issues
Malaria control and prevention is still the responsibility of the public health sector and not the responsibility of the general public
Malaria officials at the district level in some districts have not well done their responsibilities
Preparation of Malaria elimination document uploaded on google drive, some districts are still facing difficulty.

## Slide 23: Proposals
Propose to the central level to arrange for anthelmintics and provide a budget for malaria prevention and control activities in a timely manner and request for spraying machines and liquid
Request the budget for emergency cases such as investigating cases, monitoring the creation of processes and spraying anthelmintics in villages where there is an epidemic
Request communication materials for IEC such as: , USB and advertising material speaker;
Request for medicine, chemicals and materials to control the occurrence of various diseases
Increase the incentive for sending the report.

## Slide 24: Recommendation from OFV Team
Provincial level, to add more staff to some units in the operation work of 3 diseases
Central level, capacity building on technical aspect including DHIS2 for staff in each level
Strengthening integration and collaboration between units and partners concerned at provincial, district and health centers
Conduct orientation workshop to build common understanding on the programs
Prepare detail work plan and share responsibility with units and partners concerned

## Slide 25: Recommendation from OFV Team
Provincial level, regularly monitoring and supervision districts and health centers
Provincial and district level, to review, verification and approve data in DHIS2 system regularly
Should be provided with adequate tools especially computers to ensure timely reporting
To ensure that the medicine and RDTs are sufficient
Provincial level to create a management mechanism for volunteer workers to achieve the goal
Increase budget absorption in 4th quarter

## Slide 26: Recommendation from OFV Team (Conti.)
Focus on TB suspected case finding among the risk groups and all their relatives
To use the existing staff in the CDC sector to work as integrated manner;
District and health center level, to use the government's promotional budget portion to implement the activities
Integrate TB activities with other activities to provide TB information to the community
There was a lessons learn on PBC budget disbursement model in the HANSA2 project, create a management plan and monitoring the project activities, recommend the input of information in the system and the hard-copy accurately and completely.

## Slide 27: Providing comments Thanks