## Slide 1: Update on Matching Fund under HANSA2
The 1st CCM Plenary Meeting on 28 March 2024
at Crowne Plaza hotel
NCLE team

## Slide 2: Matching Fund Proposal - Lao PDR Laboratory Systems Strengthening
No. | National LSS Interventions (all sources) | Matching Fund activities to complement existing investments | HANSA/ existing funds | Matching Fund request
1 | Establish integrated transportation of samples for infectious disease (18 province) | Implement integrated sample transportation from DH upward, building on existing TB sample transport down to HC (HANSA-funded) Refreshing relevant national guidelines Baseline assessment of current specimen transport mechanisms & optimization analysis Training, implementation, monitoring & supervision Procurement of equipment & consumables for diagnostic specimen management & transportation Sample transportation costs (mechanism TBD) | $ 450,000 | $ 640,000
2 | Laboratory integration and efficiencies of services | Move towards integration of lab services to rationally allocate limited resources across vertical programs and general laboratory Updating/revising national norms & standards, including basic testing package and requisite capacity, waste management guidelines Standardization of essential diagnostic tests, utilization of existing infrastructure and equipment for multi-disease testing Integration of training, supervision (complementing HANSA-funded TB lab training) Procurement of equipment & consumables for lab waste management Development & implementation of maintenance plan for all equipment (complementing HANSA-funded GX warranty) | $ 567,000 | $ 605,000

## Slide 3: Matching Fund Proposal - Lao PDR Laboratory Systems Strengthening
No. | National LSS Interventions (all sources) | Matching Fund activities to complement existing investments | HANSA/ existing funds | Matching Fund request
3 | Strengthen laboratory data systems and information sharing | Progress toward a national LIMS system, connecting all provincial laboratories, and use of data for decision-making Procurement of equipment & services (phased expansion of LIMS to connect all PH) Integration with existing DHIS2 & surveillance data systems, sample tracking (linked with sample transport) | $ 327,800 | $ 370,000
4 | Strengthen Quality Management System | Targeted quality activities in service of #1-3 above Revise guidelines and provide training on laboratory and specimen management procedures (supports #1, #6) Integrate EQA programs (integrating HIV, TB, and other diseases) (#2) | $ 992,950 | $ 200,000
5 | Institutionalize biosafety, biosecurity and bio-risk assessment | Targeted biosafety activities in service of #1-3 above Biosafety cabinet certification & replacement HEPA filters (#2) Capacity building for biosafety cabinet field certifiers - basic accreditation (#2, supports bringing TB activities closer to general lab) | $ 237,000 | $ 125,000
6 | Enhance surveillance preparedness and response to disease outbreaks | Targeted surveillance activities in service of #1-3 above Training in TB/HIV genomic sequencing for public health response and treatment (#2, complementing current plan to establish a surveillance lab at NCLE) Procurement of consumables | $ 2,175,000 | $ 60,000
 | Total |  | $ 4,749,750 | $ 2,000,000

## Slide 4: Meeting summary for an update b/w on Laboratory System Strengthening (LSS) Activities Matching Funds, Lao PDR on 14 March 2024
Activity | Status Update | Action point(s) | Comments
Recruitment of 6 QMU Staff | Recruitment process underway (direct appointment). DPF/NPCO has prepared the draft contracts and is waiting for the CVs and justifications. | Given the delay, DPF/NPCO to update the recruitment timelines. | 
Lab TA | NCLE wants to have a direct contract with CHAI. As a result, the TORs need to be updated to add the expected deliverables and payment schedule. DPF plans to provide CHAI with the RFP and EOI to submit a proposal (financial and technical). | DPF/NPCO to clarify whether this is in line with the MoH/HANSA procurement guidelines. | 
Bank account | NCLE submitted a request to DPF for support. NPCO check with BoL and MoF on the criteria for opening a bank account. HANSA 2 legal agreement has not been signed. Bank account will be open after signing of the HANSA 2 legal agreement. | DPF/NPCO to explore if they can use GF grant agreement to open the bank account. | 
LIMS | Awaiting report from the LIMS pilot in 3 sites. Based on pilot, a detailed scale up plan to 18 Provincial Hospitals needs to be developed and presented during a stakeholder alignment meeting. | DPF/NPCO to liaise with NCLE & CHAI and confirm the timelines for pilot close-out, scale-up plan and stakeholder meeting. | LIMS activities under MF should only start after stakeholder alignment and adoption of the plan.
SI TA ToR | The scope of the ToR will be determined once the final DNO report is available. | DPF/NPCO to liaise with NCLE & CHAI and share timelines for DNO completion and stakeholder meeting (URGENT) | GF to participate in the stakeholder meeting.
GXP Service & maintenance | Updated inventory of GXP status and functionality received from NCLE. Some of the data are still missing – important as this will impact budget needed for service & maintenance. | GF will request DPF/NPCO to update the file, in coordination with NCLE, NTC & CHAS. GF will provide further guidance on negotiation with Cepheid. | Approved budget for this activity under MF likely to be insufficient.

## Slide 5: Pending issues:
NCLE in coordination with NTC sent update inventory list of GPX on 6 March 2024,
BUT, GF had responded via email on 15 March 2024 as bellowed:
Requested DPF to support NCLE in coordinating with the different centers to complete the file and provide remaining details on calibration status, software version, UPS etc. (columns N, O, P, R and U) for the GXP machines.
It is important to have this data, not only for the lab indicator but also because it will have an impact on the budget as we negotiate the service and maintenance agreement for the coming years.
Please confirm if you can submit this by Tuesday, 26 March.
In the meantime, please be informed that we are discussing the possibility of arranging the warranty extension plus via GDF and will come back with further guidance on this.